## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/EAS/TRI/TRI/06 | Rehabilitation / Improvement of Trincomalee - Pulmoddai Road (47+500 - 49+500) | Trincomalee |  | Southern Group Civil Construction (Pvt) Ltd | 20% | 131314798.09 | 138997580.74 | Awarded | Emergency |  |  |  | 2026-05-06 | 2026-11-02 | 2026-11-02
RDA/DRP/EAS/TRI/TRI/07 | Rehabilitation / Improvement of Retaining Walls of Bridges at Upparu, Ralkuli, and Gangai | Trincomalee |  | Nathans Construction | 82% | 85089780.29 | 99606470.35 | Awarded | Emergency |  |  |  | 2026-05-06 | 2026-11-02 | 2026-11-02
RDA/DRP/EAS/TRI/TRI/04 | Rehabilitation / Improvement of Town & Gravets Road (B140) (Inner Harbour Road) (0+200 - 0+560) | Trincomalee |  | Motec Engineering & Construction | 65% | 40407339.17 | 45878059.68 | Awarded | Emergency |  |  |  | 2026-06-02 | 2026-08-04