## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/CEN/KDY/KAD/11 | Rehabilitation / Improvement of Nawalapitiya - Dolosbage Road ( B -318) ( 10+500 - 19+350 ), Dedugala Dolosbage Road ( B -588) ( 10+100 - 12+410 ) | Kandy | Kadugannawa | Tiasa Construction (Pvt) Ltd | 26.5% | 193404194.96 | 275515701.42 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-25 | 2026-09-23
RDA/DRP/CEN/KDY/KUN/21 | Improvement of Pitiyegedara-Waththegama-Iriyagasthenna Road (0+000-5+400) | Kandy | Kundasale | Jayasinghe Construction (Pvt) Ltd | 12% | 257721453.96 | 314486807.16 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-30 | 2026-10-28
RDA/DRP/CEN/KDY/KUN/22 | Improvement to Damaged Road Section on Weeragantota - Randenigala Road. (From CH 19+000 To CH 27+200) | Kandy | Kundasale | SD Civil Construction (Pvt) Ltd | 67% | 224968435.78 | 333005906.52 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-25 | 2026-09-23
RDA/DRP/CEN/KDY/KUN/25 | Construction of Gabion Retaining Wall on Katugastota Madawala Bamberella Road(LHS 9+600 - 9+655), (15+450 - 15+500), (10+235 - 10+300) and Wattegama Matale road (0+400 - 0+435) | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 59% | 157909825.01 | 178738774.63 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-06 | 2026-11-01
RDA/DRP/CEN/KDY/KUN/27 | Improvement to Structures on Kandy - Jaffna Road 6+500 - 9+910 | Kandy | Kundasale | Gihan Enterprise | 66% | 113434139.4 | 122896558.88 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-30 | 2026-10-27
RDA/DRP/CEN/MTL/MTL/32 | Rehabilitation / Improvement of Kandy Jaffna (A-009)(17+710 - 46+450), Thalgodapitiya - Yatawatta - Dombawela (B-409) (15+030 - 26+800), Palapathwela - Galewela Road B-346)(0+000 - 8+100) Roads | Matale | Matale | Lahiru Construction and Consultants (Pvt) Ltd | 68% | 292279354.08 | 395635536.56 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/MTL/MTL/33 | Rehabilitation / Improvement of Wattegama Matale Road (5+280 - 13+160) and Ukuwela Railway station (0+000 - 0+190) | Matale | Matale | Jayasinghe Construction (Pvt) Ltd | 30% | 165006430.79 | 188777407.11 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-07-31
RDA/DRP/CEN/MTL/MTL/35 | Rehabilitation / Improvement of Rattota Gammaduwa Road (7+100 - 11+260) | Matale | Matale | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 63% | 266607902.15 | 291904507.83 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/MTL/NAL/51 | Rehabilitation /Improvement of Retaining wall , drains and shoulder construction Bowathenna Access Road (B-064) (0+000-2+410) | Matale | Nalanda | Platinum Holdings Lanka (Private) Limited | 90% | 17458592.78 | 25992198.15 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-18 | 2026-10-14
RDA/DRP/CEN/NUE/HAN/57 | Rehabilitation / Improvement of Keerthibandarapura Naranthalawa Road ( B -511 ) ( 0+000 - 4+100 ) | Nuwara Eliya | Hanguranketha | Samindra Construction | 30% | 47755538.96 | 44694533.62 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-30 | 2026-10-28
RDA/DRP/CEN/NUE/NUE/66 | Rehabilitation / Improvement of Nuwara Eliya Town Road (0+000 - 1+695 ) (0+000 - 0+240 ) | Nuwara Eliya | Nuwara Eliya | KSJ Construction (Pvt) Ltd | 69% | 161841095.7 | 205630098.81 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-07-31
RDA/DRP/CEN/NUE/NUE/67 | Rehabilitation / Improvement of Harangala - Kalapitiya - Kumbaloluwa Road (10+480 km - 17+140 km) | Nuwara Eliya | Nuwara Eliya | KSJ Construction (Pvt) Ltd | 78% | 239417811.34 | 302933613.6 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/NUE/NUE/68 | Rehabilitation / Improvement of Thawalanthenna Thalawakelle Road (0+000 - 8+000) & (10+000 - 33+200) | Nuwara Eliya | Nuwara Eliya | Green Scene Construction (Pvt) Ltd | 40% | 213999600.01 | 296813201.99 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/NUE/NUE/69 | Rehabilitation / Improvement of Ulapane Pussallawa Road (6+440 - 15+950) | Nuwara Eliya | Nuwara Eliya | Southern Group Civil Construction (Pvt) Ltd | 56% | 266045892.19 | 365868062.33 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/NUE/NUE/86 | Rehabilitation / Improvement of Approch road to R'way station (Watagoda/ Thalawakele) Road | Nuwara Eliya | Nuwara Eliya | Pragathi Civil Construction | 20% | 33765626.86 | 41996395.31 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-12 | 2026-09-10
RDA/DRP/CEN/NUE/NUR/97 | Rehabilitation/Improvement of Nawalapitiya Ginigathena Road (B-319)(7+200-12+200) | Nuwara Eliya | Norwood | Jayawansa Construction (Pvt) Ltd | 62% | 93758217.76 | 104490700.33 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-17 | 2026-09-15
RDA/DRP/SAB/KEG/KEG/14 | Rehabilitation / Improvement of Damaged Locations in Colombo Kandy Road from 56+050-98+950 | Kegalle | Kegalle | Tudawe Brothers (Pvt) Ltd | 65% | 261228130.78 | 267884733.58 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-07 | 2026-08-05 | 2026-08-06
RDA/DRP/UVA/BAD/BAD/02 | Rehabilitation / Improvement of Demodara SpringValley Badulla Road (16+145-20+800) - selected Sections) (B-097) | Badulla | Badulla | Priyankara Industries & Contractors | 66% | 241775532.44 | 286001165.69 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-26 | 2026-09-22 | 2026-09-22
RDA/DRP/UVA/BAD/MAH/27 | Rehabilitation / Improvement of Dambagahapitiya Pinnagolla arawa Meegahakeula Road (8+200-8+250) (B-086)/ Bibile-Uraniya-Mahiyanganaya Road | Badulla | Badulla | EMA Construction (Pvt) Ltd | 79.5% | 73623757.9 | 103692871.49 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-26 | 2026-09-21 | 2026-09-21
RDA/DRP/SAB/RAT/PEL/20 | Rehabilitation / Improvement of Pelmadulla - Pelmadulla - Embilipitiya - Nonagama (2+050 - 4+320) & Retaining wall Construction on Pelmadulla - Embilipitiya - Nonagama Road 5/4 - 5/5 (LHS) | Ratnapura | Ratnapura | K.E.P. Construction | 31% | 194327188.51 | 224909805.06 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-06 | 2026-07-06 | 2026-08-06
RDA/DRP/UVA/BAD/BAN/19 | Rehabilitation / Improvement of Bandarawela Liyangahawela Poonagala Road (5+000 -10+000) (B-042) | Badulla | Badulla | Senura Civil Engineering (Pvt) Ltd | 40% | 216526489.67 | 220745970.7 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-26 | 2026-09-23 | 2026-09-23
RDA/DRP/SAB/KEG/KEG/16 | Rehabilitation / Improvement of Kegalle Siyambalapitiya Dewalegama Road, Polgahawela Kegalle Road and Mawanella Aranayaka Horewela Road | Kegalle | Kegalle | Creates Consultant and Construction | 60% | 258281578.64 | 278060284.2 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-18 | 2026-08-16 | 2026-08-16
RDA/DRP/UVA/MON/MON/28 | Rehabilitation / Improvement of Colombo Galle Hambanthota Wellawaya Road (305+650-305+850) (AA-002), Wellawaya Ella Kumbalwela Road (0+800-1+825) (AA-023) and Kumbukkana Okkampitiya Maligawila Road (2+250-2+450) (B-513) | Monaragala | Monaragala | EMA Construction (Pvt) Ltd | 59% | 86302421.23 | 118529679.67 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-06 | 2026-10-02 | 2026-10-02
RDA/DRP/SAB/KEG/RUW/29 | Rehabilitation / Improvement of Dehiowita - Daraniyagala - Nooriya Road (From 13+845 to 23+850) | Kegalle | Kegalle | SSP Engineers (Pvt) Ltd | 70% | 217629047.45 | 227460547.85 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-25 | 2026-06-25 | 2026-07-29
RDA/DRP/UVA/BAD/BAD/01 | Rehabilitation / Improvement of Badulla Karametiya Andaulpotha Road (0+000-20+000 - Selected Sections) (B-036) | Badulla | Badulla | JD Builders | 71% | 210946129.78 | 292708768.01 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-30 | 2026-09-27 | 2026-09-27
RDA/DRP/UVA/BAD/BAD/04 | Rehabilitation / Improvement of Dikwella Jagulla Thalpitigala Road (0+000-6+600 - Selected Sections) (B-100) | Badulla | Badulla | PH Engineering & Construction (Pvt) Ltd | 67.5% | 272601362.28 | 318107616.89 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-30 | 2026-09-27 | 2026-09-27
RDA/DRP/UVA/BAD/BAD/05 | Rehabilitation / Improvement of Dikwella Jagulla Thalpitigala Road 6+600-15+000 - Selected Sections) (B-100) | Badulla | Badulla | PH Engineering & Construction (Pvt) Ltd | 57.5% | 219248828.55 | 259321056.45 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-27 | 2026-09-25 | 2026-09-25
RDA/DRP/UVA/BAD/BAN/14 | Rehabilitation / Improvement of Bandarawela Welimada Road (0+000-6+000) (B-044) | Badulla | Badulla | Senarathna Contractors | 73.5% | 232880104.48 | 274546113.13 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-27 | 2026-09-24 | 2026-09-24
RDA/DRP/SAB/RAT/EMB/04 | Rehabilitation / Improvement of Galle - Deniyaya-Madampe Road (88+000-95+000) | Ratnapura | Ratnapura | SN Projects Lanka (Pvt) Ltd | 22% | 290799045.34 | 318792416.26 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-07 | 2026-07-07
RDA/DRP/SAB/RAT/EMB/12 | Rehabilitation / Improvement of Galle -Deniyaya-Madampe Road (95+000-100+000) | Ratnapura | Ratnapura | SN Projects Lanka (Pvt) Ltd | 26% | 290733855.4 | 319465519.22 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-07 | 2026-07-07
RDA/DRP/SAB/KEG/KEG/13 | Rehabilitation / Improvement of damage locations at Ambepussa Kurunegala Trincomalee Road, Warakapola Kandalama Road, Warakapola Buypass Road, Morontota Arandara Road, Galigamuwa Ruwanwella Road, Gevilipitiya Hettimulla Road, Kegalle Bulattkohupitiya, Karawanella Road, Mawanella Hemmathagama Gampola Road and Rambukkana Mawanella Road in Kegalle Executive Engineers Division. | Kegalle | Kegalle | Senarath Engineering (Pvt) Ltd | 75% | 247437818.24 | 258512761.66 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-29 | 2026-08-29 | 2026-08-29
RDA/DRP/SAB/RAT/RAT/22 | Rehabilitation / Improvement and Asphalt Overlaying on Ayagama Kukulegama Road | Ratnapura | Ratnapura | Keangnam Engineering & Construction (Pvt) Ltd | 42.9% | 280145000.74 | 316600518.19 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-27 | 2026-06-26 | 2026-09-25
RDA/DRP/SAB/RAT/RAT/26 | Rehabilitation / Improvement of Malwala - Carney Road (Ch. 11+000 - Ch. 14+972) | Ratnapura | Ratnapura | SSP Engineers (Pvt) Ltd | 85.8% | 184511228.94 | 199494622.85 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-07 | 2026-07-07 | 2026-07-07
RDA/DRP/SAB/RAT/RAT/25 | Rehabilitation / Improvement and Asphalt Overlaying on Malwana Charney (6+020 - 11+000) & Construction of Gabion Wall at 2+510, 2+847 | Ratnapura | Ratnapura | Wijeratne Construction | 62% | 242356869.5 | 269615801.69 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-07 | 2026-07-07 | 2026-07-07
RDA/DRP/UVA/BAD/BAD/03 | Rehabilitation / Improvement of Peradeniya Badulla Chenkaladi Road (90+000-123+000) (AA-005) | Badulla | Badulla | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 61% | 277749116.37 | 282102670.39 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-26 | 2026-09-23 | 2026-09-23
RDA/DRP/UVA/BAD/BAD/06 | Rehabilitation / Improvement of Baragala Haliela Road (25+525-38+000 - Selected Sections) (AA-016) and Bandarawela Uva Highland Etampitiya Road (5+000-16+100) (B-043) | Badulla | Badulla | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 57% | 254882804.5 | 302416798.7 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-26 | 2026-09-24 | 2026-09-24
RDA/DRP/SAB/RAT/PEL/21 | Rehabilitation / Improvement of Pabahinna - Kubalgama - Rajawaka - Kapugala Road (2+000-7+700) & Retaining wall Construction of Colombo - Rathnapura - Wellawaya- Batticaloa Road (156/2 (RHS), 155/6, 133/7 - 133/8 (RHS), 122/5- 122/4 (RHS) | Ratnapura | Ratnapura | Samdam Engineering & Constructions (Pvt) Ltd | 32% | 184536305.86 | 215458780.2 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-06 | 2026-07-06 | 2026-08-06
RDA/DRP/UVA/BAD/BAN/16 | Rehabilitation / Improvement of Rendapola Ambewela Road (0+000-1+435) (B-507) and Peradeniya Badulla Chenkaladi Road (76+000-90+000) (AA-005) | Badulla | Badulla | Subasingha Contractors (Pvt) Ltd | 66% | 297237284.97 | 293827930.5 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-02 | 2026-09-30 | 2026-09-30
RDA/DRP/UVA/BAD/BAN/22 | REHABILITATION/IMPROVEMENT OF WELIMADA KIRKLEES ROAD ( From 0+000 to 17+250) | Badulla | Badulla | Suhada Enterprises | 77% | 246717227.79 | 288759369.79 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-27 | 2026-09-24 | 2026-09-24
RDA/DRP/UVA/MON/BIB/25 | Rehabilitation / Improvement of Colombo Rathnapura Wellawaya Batticaloa Road (259+080-292+800) (AA-004), Siyabalanduwa damana Ampara Road (0+000-24+000) (AA-025) and Bibila Medagama Nakkala Road (0+000-33+240) (B-056) and Passara Monaragala Road (7+120-26+240) (AA-022) | Monaragala | Monaragala | Ediriweera Construction | 51% | 74036604.05 | 103821878.45 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-07 | 2026-10-05 | 2026-10-05
RDA/DRP/SAB/RAT/RAT/24 | Rehabilitation / Improvement and Asphalt Overlaying on Kalawana - Deepdeen Rakwana (4+255-9+809) | Ratnapura | Ratnapura | SSP Engineers (Pvt) Ltd | 85% | 236752750.59 | 264741911.81 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-07 | 2026-06-24 | 2026-07-07
RDA/DRP/SAB/KEG/RUW/28 | Rehabilitation / Improvement of Bulathkohupitiya Dedugala Road, Warakapola Ruwanwella Road, Alawathura- Yatapana - Kotiyakumbura Road and Avissawella - Hatton - Nuwaraeliya Road | Kegalle | Kegalle | Southern Group Civil Construction (Pvt) Ltd | 50% | 260537133.84 | 284539377.98 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-10 | 2026-09-11 | 2026-09-11
RDA/DRP/SAB/KEG/RUW/35 | Yatiyanthota - Poonagala - Meenagala Road (from 13+400 to 18+200) | Kegalle | Kegalle | Southern Group Civil Construction (Pvt) Ltd | 25% | 170714785.54 | 172314426.38 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-10 | 2026-09-11 | 2026-09-11
RDA/DPR/NCP/ANU/ANU/02 | Rehabilitation / Improvement and Construction of Drainge Canal for Kumbichchan Kulama Spillway on Maitreepala Senanayake Mawatha (1+970 - 2+090 km) | Anuradhapura | Anuradhapura | SMA Construction (Pvt) Ltd | 50% | 138891057.65 | 178990814.77 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-20 | 2026-10-19 | 2026-10-19
RDA/DPR/NCP/ANU/ANU/03 | Rehabilitation / Improvement Construction of Drainge Canal for Thambuttegama Tank Spill on Padeniya - Anuradhapura Road (59+420 - 59+610) & Construction of Drainge Canal for Protection Road on Andarawewa - Balaluwewa Road(16+580 - 16+680) | Anuradhapura | Anuradhapura | SMA Construction (Pvt) Ltd | 38% | 132437825.5 | 174596369.9 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-20 | 2026-10-19 | 2026-10-19
RDA/DRP/WP/GAM/NEG/19 | Rehabilitation / Improvement of Negombo-Mirigama Road (5+000-6+000) and Negombo-Giriulla Road (29+000-34+000) | Gampaha | Gampaha | Tudawe Brothers (Pvt) Ltd | 20% | 206184462.57 | 222010882.78 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-04 | 2026-11-02
RDA/DRP/WP/GAM/NIT/21 | Rehabilitation / Improvement of Hanwella Urapola Road (3+000 - 10+100), Structure Construction on Delgoda Dompe Giridara Road (0+000- 10+070) and Urapola Wathuragama Road (0+000- 7+080 ) and Drain Construction on Negombo-Mirigama road (21+000 - 30+580) | Gampaha | Gampaha | Tudawe Brothers (Pvt) Ltd | 28% | 221768903.84 | 231075356.57 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-04 | 2026-11-02
RDA/DRP/WP/GAM/GAM/10 | Rehabilitation / Improvement of Old Minuwangoda Gampaha - Miriswatta Road (9+000 - 10+000) and Minuwangoda - Gampaha Road (0+000 - 5+300) | Gampaha | Gampaha | Senarath Engineering (Pvt) Ltd | 2% | 92177672.52 | 110481340.2 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-24 | 2026-07-24
RDA/DRP/WP/GAM/GAM/12 | Rehabilitation / Improvement of Acces Road to Peliyagoda interchange (0+000 - 2+100), Colombo - Kandy Road (6+500-19+000) and Kelaniya - Waragoda Road (0+000-3+220) | Gampaha | Gampaha | Senarath Engineering (Pvt) Ltd | 2% | 151956608.92 | 170010323.36 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-24 | 2026-07-24
RDA/DRP/WP/GAM/NIT/20 | Rehabilitation / Improvement of Bothale Mirigama Road (3+750-4+800), Warakapola Kandalama Road (7+000-8+000), (8+500-9+000) & (9+500-10+900), Negombo Mirigama Road and Construction of Gabion Wall on Colombo - Kandy Road at 54+950,Warakapola Kandalama Road at Culvert No. 10/4 LHS and Widening of Culvert Nos. 4/1 LHS 4/3 Bothsides and Reconstruction of Culvert No. 4/2 on Veyangoda Banduragoda Road | Gampaha | Gampaha | Jeyanthan Construction | 46% | 217881464.96 | 245395696.16 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-04 | 2026-09-03
RDA/DRP/WP/GAM/NIT/22 | Rehabilitation / Improvement of Delgoda Dompe Giridara Road (Selected Sections between 2+000-12+100) | Gampaha | Gampaha | Senarath Engineering (Pvt) Ltd | 1% | 264745054.48 | 294920837.23 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-24 | 2026-10-23
RDA/DRP/WP/GAM/NIT/23 | Rehabilitation / Improvement of Kalagedihena Veyangoda Road (0+000 -3+000), Pasyala Attanagalla Road (0+000 - 6+400) and Colombo - Kandy Road (38+620 -38+720) | Gampaha | Gampaha | Senarath Engineering (Pvt) Ltd | 1% | 258218314.97 | 305207472.65 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-24 | 2026-10-23
RDA/DRP/SAB/KEG/RUW/30 | Rehabilitation of Dehiovita - Daraniyagala - Nooriya Road (from 23+850 to 27+960) due to catastrophic disaster cyclone Ditwa | Kegalle | Kegalle | Accon Engineering (Pvt) Ltd | 68% | 169223910.8 | 179826720.59 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-22 | 2026-08-21 | 2026-08-21
RDA/DRP/SAB/KEG/RUW/31 | Rehabilitation of Kegalle - Bulathkohupitiya - Karawanella Road due to catastrophic disaster cyclone Ditwa | Kegalle | Kegalle | Tudawe Brothers (Pvt) Ltd | 18% | 269890586.86 | 284390126.9 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-01 | 2026-08-31 | 2026-08-31
RDA/DRP/WP/COL/AVI/02 | Rehabilitation / Improvement of Damage Sections on Colombo - Hanwella Low Level Road (AB010) (23+000 - 26+715) & Hanwella Cross Road (B145) (0+000 - 0+800) | Colombo | Colombo | Keangnam Engineering & Construction (Pvt) Ltd | 29% | 279374027.9 | 299392762.2 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-21 | 2026-07-21 | 2026-08-08
RDA/DRP/WP/COL/AVI/03 | Rehabilitation / Improvement and Asphalt Overlaying on Colombo - Horana Road (B084) (10+500 - 13+500) | Colombo | Colombo | Keangnam Engineering & Construction (Pvt) Ltd | 3% | 176739557.41 | 201633881.18 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-21 | 2026-06-23 | 2026-07-11
RDA/DRP/WP/COL/AVI/04 | Rehabilitation / Improvement and Asphalt Overlaying on Mampe Kottawa Road (B267) (0+750 - 3+400) (5+100 - 6+120)) | Colombo | Colombo | Keangnam Engineering & Construction (Pvt) Ltd | 65% | 94697340.01 | 108030624.38 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-21 | 2026-06-23 | 2026-07-11
RDA/DRP/WP/COL/AVI/05 | Rehabilitation / Improvement and Asphalt Overlaying on Panagoda Henpita Road (B354) (0+000 - 6+440) | Colombo | Colombo | Keangnam Engineering & Construction (Pvt) Ltd | 3% | 225228168.18 | 250078803.62 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-21 | 2026-06-23 | 2026-07-11
RDA/DRP/NWP/KURU/KURU/04 | Rehabilitation / Improvement of Muththettugala Hiripitiya Road (B300) (10+880 - 11+080) & Vilakatupotha Ganewatta Kumbukgete road (B478) (9+100 - 9+400) | Kurunegala | Kurunegala | TMC Construction (Pvt) Ltd | 62% | 97503423.17 | 105193927.73 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-21 | 2026-07-22 | 2026-07-22
RDA/DRP/NWP/KURU/MAHO/05 | Rehabilitation / Improvement of Galgamuwa - Nikawewa Road (B126) (6+000-20+000), Danikithawa - Ambanpola Road (B089) (20+925 - 21+000), Nikaweratiya - Moragollagama - Siyambalangamuwa Road (B326) (40+760 - 48+240), Malsiripura - Rambe Road (B610) (7+500 - 9+650), Ibbagamuwa - Kumbukgate - Madagalla Road (B159) (16+450 - 28+680), Hiripitiya - Galtenwewa Road (B609) (9+580-9+680), Padeniya - Anuradapura Road (AA028) (8+480-8+800) and Katugasthota - Kurunegala - Puththalama Road (AA010) (73+745-73 -870) in Maho EE Division | Kurunegala | Kurunegala | St. Anthony's Construction | 70% | 151515024.36 | 166163663.09 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-05 | 2026-09-01 | 2026-09-01
RDA/DRP/SAB/RAT/EMB/01 | Rehabilitation / Improvement of Kalawana - Deepdeen - Rakwana Road (15+000-46+000) | Ratnapura | Ratnapura | SSP Engineers (Pvt) Ltd | 62% | 287333615.63 | 291908137.8 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-15 | 2026-08-14 | 2026-08-14
RDA/DRP/SAB/RAT/EMB/02 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya - Nonagama Road (40+500-43+300) | Ratnapura | Ratnapura | Anura Construction | 21% | 260511600.34 | 297894808.58 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-24 | 2026-07-24 | 2026-07-24
RDA/DRP/EAS/TRI/TRI/06 | Rehabilitation / Improvement of Trincomalee - Pulmoddai Road (47+500 - 49+500) | Trincomalee |  | Southern Group Civil Construction (Pvt) Ltd | 20% | 131314798.09 | 138997580.74 | Awarded | Emergency |  |  |  | 2026-05-06 | 2026-11-02 | 2026-11-02
RDA/DRP/EAS/TRI/TRI/07 | Rehabilitation / Improvement of Retaining Walls of Bridges at Upparu, Ralkuli, and Gangai | Trincomalee |  | Nathans Construction | 82% | 85089780.29 | 99606470.35 | Awarded | Emergency |  |  |  | 2026-05-06 | 2026-11-02 | 2026-11-02
RDA/DRP/WP/COL/COL/06 | Rehabilitation / Improvement of Allen Avenue (B011) (0+000- 2+000) | Colombo | Colombo | Jayasinghe Construction (Pvt) Ltd | 5% | 144822585.09 | 146669652.6 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-10 | 2026-08-09
RDA/DRP/WP/COL/COL/09 | Rehabilitation / Improvement of Koralawella Egodauyana Road (B235) section 2 (3+000 - 6+300) | Colombo | Colombo | Jayasinghe Construction (Pvt) Ltd | 5% | 155082468.4 | 160664947.64 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-10 | 2026-08-09
RDA/DRP/WP/COL/AVI/01 | Rehabilitation / Improvement and Drain and Shoulder Construction at Locations Within 38+200 - 60+950 on Colombo - Ratnapura - Wellawaya - Batticaloa Road (AA004) | Colombo | Colombo | Greenwawe Construction (Pvt) Ltd | 26% | 210347639.08 | 239974678.56 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-10 | 2026-07-12 | 2026-07-23
RDA/DRP/UVA/BAD/BAN/18 | Rehabilitation / Improvement and Retainning Wall Construction Construction on Palugama Boralanda Haputhala Road (B353) (0+000 - 26+550), Haputale Dambatanna Road (B147) (1+700 - 1+735 RHS and 0+220 - 0+240 LHS) and Colombo Rathnapura Wellawaya Batticaloa Road (AA004) (167+750 - 213+750) | Badulla | Badulla | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 50% | 147759561.52 | 153768755.88 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-06 | 2026-11-03 | 2026-11-03
RDA/DRP/UVA/BAD/BAN/21 | Rehabilitation / Improvement of Wellawaya - Ella - Kumbalwela (14+000-30+0000 (AA-023), Ella - Passara (B113) (0+000 -5+000) and Beragala Hali-Ela (A016) (0+000 -25+000) | Badulla | Badulla | Suhada Enterprises | 56% | 321850877.98 | 321810896.4 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-06 | 2026-11-03 | 2026-11-03
RDA/DRP/NCP/POL/POL/09 | Rehabilitation / Improvement and Reconstruction of Culvert No. 104/2, Construction of New Drainage At 83km, and Concrete Hard Shoulder at 83 Km on Maradankadawala - Habarana - Thirikkondiyadumadu Road (A-11) (82+110 - 82+860 (B/S) | Polonnaruwa | Polonnaruwa | Abeywardhana Construction | 56% | 94457054.66 | 119605688.26 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-05 | 2026-05-08 | 2026-05-08
RDA/DRP/SAB/RAT/EMB/08 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya - Naonagama Road (AA018) (43+700-47+000) | Ratnapura | Ratnapura | Anura Construction | 15% | 259436963.35 | 286890596.52 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-10 | 2026-08-09 | 2026-08-09
RDA/DRP/SAB/RAT/EMB/10 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya - Nonagama Road (AA018) (50+500 - 53+100) & Embilipitiya - Moraketiya - Kiriibbanara - Uda Mauara Road (B549) (0+000-5+500) | Ratnapura | Ratnapura | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 23.7% | 260776583.43 | 271949863.68 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-10 | 2026-08-11
RDA/DRP/EAS/BAT/BAT/01 | Rehabilitation / Improvement and Surfacing from 56+900 km to 58+300km and from 58+640 km to 59+440 km on Bitticaloa - Thurukkondamadu - Trincomalee Road | Batticaloa |  | S S K Construction | 70% | 113074919.76 | 144552679.21 | Awarded | Emergency |  |  |  | 2026-05-25 | 2026-08-24
RDA/DRP/SAB/RAT/EMB/05 | Rehabilitation / Improvement of Pelmadulla-Embilipitiya-Nonagama Road (30+000-32+850) | Ratnapura | Ratnapura | Anura Construction | 10% | 248600718.52 | 272308017.25 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-29 | 2026-09-28 | 2026-09-28
RDA/DRP/SAB/RAT/EMB/06 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya-Nonagama Road (33+500-36+500) | Ratnapura | Ratnapura | Anura Construction | 10% | 237998681.32 | 258434888.71 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-29 | 2026-09-28 | 2026-09-28
RDA/DRP/SAB/RAT/EMB/07 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya-Nonagama Road (37+000-40+000) | Ratnapura | Ratnapura | Anura Construction | 15% | 276583785.23 | 299052002.52 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-29 | 2026-09-28 | 2026-09-28
RDA/DRP/SAB/RAT/EMB/09 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya - Naonagama Road (47+100 - 50+400) | Ratnapura | Ratnapura | Anura Construction | 6% | 269913795.48 | 290570516.98 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-09 | 2026-08-28 | 2026-08-28
RDA/DRP/SAB/RAT/EMB/11 | Rehabilitation / Improvement of Weligepola-Hadagiriya - Kapugala (2+000-11+000) | Ratnapura | Ratnapura | D K S Construction | 42% | 273586576.22 | 328908478.03 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-01 | 2026-09-30 | 2026-12-30
RDA/DRP/WP/COL/COL/07 | Rehabilitation / Improvement of Colombo Hanwella Road (0+370 - 20+400) | Colombo | Colombo | INK Engineering | 12% | 146665907.47 | 140313104.48 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-25 | 2026-08-24 | 2026-08-24
RDA/DRP/EAS/TRI/TRI/04 | Rehabilitation / Improvement of Town & Gravets Road (B140) (Inner Harbour Road) (0+200 - 0+560) | Trincomalee |  | Motec Engineering & Construction | 65% | 40407339.17 | 45878059.68 | Awarded | Emergency |  |  |  | 2026-06-02 | 2026-08-04
RDA/DRP/NWP/CHI/CHI/08 | Rehabilitation / Improvement of Baththuluoya - Udappuwa - Andimunai Road (B614) at 6+100 in Chilaw EE Division | Puttalam | Chilaw | ST MARY Construction | 56% | 83944711.21 | 84197870.47 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-12 | 2026-08-15 | 2026-10-14
RDA/DPR/NCP/ANU/ANU/01 | Rehabilitation / Improvement of Andarawewa - Balaluwewa Road (B501) (21+330 - 21+ 580 km) | Anuradhapura | Anuradhapura | Ranuja Construction | 16% | 99497834.48 | 85106787.1 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-23 | 2026-10-22 | 2027-10-21
RDA/DRP/NCP/POL/HAB/04 | Rehabilitation / Improvement of washed out section between 30/1 & 30/2 Bridges on Dambulla - Bakamoona - Kalagahawela Road (B-615) & at 27/5 Bridge (26+500-27+000) on Naula - Elahera - Pallegama -Hettipola Road (B-312) | Polonnaruwa | Polonnaruwa | Lahiru Construction and Consultants (Pvt) Ltd | 90% | 49203550.22 | 51855122.27 | Awarded | Emergency | Yes | Yes | Yes | 2026-02-06 | 2026-01-09 | 2026-01-09
RDA/DRP/NCP/ANU/MAR/06 | Rehabilitation / Improvement and Retaining wall Construction of bridge No. 3/1 & Gabion wall Construction on Madatugama Pubbogama Andiyagala Road (B-556) (1+900km) RHS | Anuradhapura | Anuradhapura | W.M.B. Contractors & Transporter | 90% | 112693093.11 | 91709767.42 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-30 | 2026-09-29 | 2026-09-29
RDA/DRP/NCP/ANU/MED/07 | Rehabilitation / Improvement of Flood Damaged - Shoulder & Embankment Protection for Puttalam - Trincomalee Road (AA012) (131+100-131+400 LHS/RHS) (139+020-139+100 LHS) , Kandy -Jaffna Road (AA009) ( 148+775-149+050) and Kebithigollewa - Padaviya Road (B211) (17+400-17+550) | Anuradhapura | Anuradhapura | The Crown Construction | 47% | 38223285.38 | 45054035.76 | Awarded | Emergency | Yes | Yes | Yes | 2026-02-06 | 2026-01-09 | 2026-01-09
RDA/DRP/SAB/RAT/PEL/17 | Rehabilitation / Improvement of Balangoda - Bowatta -Kalthota Road (B038) (24+000-26+000) | Ratnapura | Ratnapura | DKS Nishantha Construction | 60% | 92061086.61 | 101146022.11 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-12 | 2026-09-12
RDA/DRP/UVA/BAD/BAN/20 | Rehabilitation / Improvement of Bandarawela - Liyangahawela - Poonagala Road (B042) (10+000 -15+000) | Badulla |  | D K S Construction | 44.5% | 283401035.13 | 301203263.92 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-20 | 2026-10-17
RDA/DRP/NCP/POL/POL/10 | Rehabilitation / Improvement and Construction of New Drainage At 65-78km on Maradankadawala Habarana Thirikkondiyadumadu Road (A011)Road | Polonnaruwa | Polonnaruwa | A.D.M Construction | 55% | 29767050.53 | 33973362.07 | Awarded | Emergency | Yes | Yes | Yes | 2026-02-06 | 2026-01-09 | 2026-01-09
RDA/DRP/EAS/AMP/AMP/01 | Rehabilitation / Improvement of Ampara Uhana Mahoya Road (from 2+400 to 2+800) & (from 3+700 to 3+900), Siyambalanduwa Damana Ampara Road (from 43+000 to 45+000), (from 33+000 to 34+000), (from 35+500 to 36+500) & (from 52+000 to 53+000) and Chadayanthalawa Uhana Road (from 11+100 to 11+500) | Ampara |  | Ediriweera Construction | 90% | 27878955.02 | 31793559.86 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-12 | 2026-09-10
RDA/DRP/WP/GAM/GAM/13 | Rehabilitation / Improvement and Culvert Constructions on Aluthgama- Vigoda Road at 1+650, on Katunayake - Veyangoda Road at 15+940, on Minuwangoda - Miriswatta - Katana Road at 3+700, on Dunagaha- Nilpanagoda Road at 4+900, on Kadawatha - Mawaramandiya Road at 2+800 and on Makola - Udupila Road at 3+200 | Gampaha | Gampaha | Venus Enterprise | 60% | 34489854.85 | 39535250.16 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-18 | 2026-09-17
RDA/DRP/NCP/POL/POL/11 | Rehabilitation / Improvement and Construction of New Drainage on Polonnaruwa-Thambala -Sungawila -Somawathiya- Road | Polonnaruwa | Polonnaruwa | A.D.M Construction | 40% | 44474738.82 | 57461708.21 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-12 | 2026-09-11 | 2026-09-11
RDA/DRP/SP/GAL/HIN/03 | Rehabilitation / Improvement of Gabbion Walls along Udugama - Hiniduma (9+920- 9+938-LHS), (7+450-7+472-LHS), (5+150-5+17 LHS) | Galle | Galle | Ceylon Construction Industry Development (Pvt) Ltd | 98% | 19453314.54 | 22102879.06 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-06 | 2026-10-05