## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/CEN/KDY/KAD/11 | Rehabilitation / Improvement of Nawalapitiya - Dolosbage Road ( B -318) ( 10+500 - 19+350 ), Dedugala Dolosbage Road ( B -588) ( 10+100 - 12+410 ) | Kandy | Kadugannawa | Tiasa Construction (Pvt) Ltd | 26.5% | 193404194.96 | 275515701.42 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-25 | 2026-09-23
RDA/DC/DRP/SLOPE/PD(CP)/KDY/KAD/35 | Construction of Slope failure mitigation measures along Aladeniya-Eriyagama Road (B005) at Ch 3+700 RHS. | Kandy | Kadugannawa | Weebadda Construction | 0% | 26072370 | 28669432.07 | Awarded | PD(CP) - Slope
RDA/DC/DRP/SLOPE/CP/KDY/KAD/PACKAGE 14B | MITIGATION FOR FAILURE LOCATIONS ALONG NAWALAPITIYA DOLOSBAGE ROAD (B318) (15+000 - 16+000) DUE TO "DITWAH" CYCLONE - PACKAGE 14B | Kandy | Kadugannawa | HMA Enterprises (Pvt) Ltd | 0% | 139111261.28 | 130000000 | Awarded | DC - Slope