## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/CEN/NUE/HAN/57 | Rehabilitation / Improvement of Keerthibandarapura Naranthalawa Road ( B -511 ) ( 0+000 - 4+100 ) | Nuwara Eliya | Hanguranketha | Samindra Construction | 30% | 47755538.96 | 44694533.62 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-30 | 2026-10-28
RDA/DC/DRP/SLOPE/CP/NUE/HAN/PACKAGE 26E | REHABILITATION OF SELECTED ROAD SECTIONS ON THENNEKUMBURA RIKILLAGASKADA RAGALA ROAD (B413) (50+100-70+950 ) AND SLOPE FAILURES DUE TO "DITWAH" CYCLONE-PACKAGE 26E | Nuwara Eliya | Hanguranketha | Nagma Engineering (Pvt) Ltd | 0% | 332123863.5 | 322400000 | Awarded | DC - Slope
RDA/DC/DRP/SLOPE/CP/NUE/HAN/PACKAGE 26C | MITIGATION FOR FAILURE LOCATIONS ALONG THENNEKUMBURA RIKILLAGASKADA RAGALA ROAD (B413) (48/11 - 48/12) & (67/10 - 67 km) DUE TO "DITWAH" CYCLONE-PACKAGE 26C | Nuwara Eliya | Hanguranketha | Finex Engineering (Pvt) Ltd | 0% | 180175018.14 | 159300000 | Awarded | DC - Slope