## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/NCP/POL/POL/09 | Rehabilitation / Improvement and Reconstruction of Culvert No. 104/2, Construction of New Drainage At 83km, and Concrete Hard Shoulder at 83 Km on Maradankadawala - Habarana - Thirikkondiyadumadu Road (A-11) (82+110 - 82+860 (B/S) | Polonnaruwa | Polonnaruwa | Abeywardhana Construction | 56% | 94457054.66 | 119605688.26 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-05 | 2026-05-08 | 2026-05-08
RDA/DRP/NCP/POL/HAB/04 | Rehabilitation / Improvement of washed out section between 30/1 & 30/2 Bridges on Dambulla - Bakamoona - Kalagahawela Road (B-615) & at 27/5 Bridge (26+500-27+000) on Naula - Elahera - Pallegama -Hettipola Road (B-312) | Polonnaruwa | Polonnaruwa | Lahiru Construction and Consultants (Pvt) Ltd | 90% | 49203550.22 | 51855122.27 | Awarded | Emergency | Yes | Yes | Yes | 2026-02-06 | 2026-01-09 | 2026-01-09
RDA/DRP/NCP/POL/POL/08 | Rehabilitation / Improvement and Reconstruction of 31/1 Culvert, Construction Of Retaining Walls At 31/2 (RHS) on Manampitiya Aralaganwila Maduruoya Road | Polonnaruwa | Polonnaruwa | Sawsiri Construction | 100% | 17459311.37 | 17399611.61 | Awarded | Emergency | Yes | Yes | Yes | 2026-02-06 | 2026-01-09 | 2026-01-09
RDA/DRP/NCP/POL/POL/10 | Rehabilitation / Improvement and Construction of New Drainage At 65-78km on Maradankadawala Habarana Thirikkondiyadumadu Road (A011)Road | Polonnaruwa | Polonnaruwa | A.D.M Construction | 55% | 29767050.53 | 33973362.07 | Awarded | Emergency | Yes | Yes | Yes | 2026-02-06 | 2026-01-09 | 2026-01-09
RDA/DRP/NCP/POL/POL/11 | Rehabilitation / Improvement and Construction of New Drainage on Polonnaruwa-Thambala -Sungawila -Somawathiya- Road | Polonnaruwa | Polonnaruwa | A.D.M Construction | 40% | 44474738.82 | 57461708.21 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-12 | 2026-09-11 | 2026-09-11