## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/NOR/VOU/VOU/15 | Rehabilitation /Improvement of Kandy-Jaffna Road (AA009) & Madawachchiya-Mannar-Thalaimannar Road (AA014) | Vavuniya | Vavuniya | Jana Civil Work Contractors & Material Suppliers | 19% | 42832926.51 | 46307621.71 | Awarded | Emergency | Yes | Yes | Yes | 2026-08-27 | 2026-12-23