## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/UVA/BAD/BAD/02 | Rehabilitation / Improvement of Demodara SpringValley Badulla Road (16+145-20+800) - selected Sections) (B-097) | Badulla | Badulla | Priyankara Industries & Contractors | 66% | 241775532.44 | 286001165.69 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-26 | 2026-09-22 | 2026-09-22
RDA/DRP/UVA/BAD/MAH/27 | Rehabilitation / Improvement of Dambagahapitiya Pinnagolla arawa Meegahakeula Road (8+200-8+250) (B-086)/ Bibile-Uraniya-Mahiyanganaya Road | Badulla | Badulla | EMA Construction (Pvt) Ltd | 79.5% | 73623757.9 | 103692871.49 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-26 | 2026-09-21 | 2026-09-21
RDA/DRP/UVA/BAD/BAN/19 | Rehabilitation / Improvement of Bandarawela Liyangahawela Poonagala Road (5+000 -10+000) (B-042) | Badulla | Badulla | Senura Civil Engineering (Pvt) Ltd | 40% | 216526489.67 | 220745970.7 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-26 | 2026-09-23 | 2026-09-23
RDA/DRP/UVA/BAD/BAN/15R | Rehabilitation / Improvement of Bandarawela Welimada Road (6+000-20+200) (B-044) | Badulla | Badulla | Subasingha Contractors (Pvt) Ltd | 12% | 228783135.84 | 237954791.68 | Awarded | Emergency |  |  |  | 2026-09-04 | 2027-03-05
RDA/DRP/UVA/MON/MON/28 | Rehabilitation / Improvement of Colombo Galle Hambanthota Wellawaya Road (305+650-305+850) (AA-002), Wellawaya Ella Kumbalwela Road (0+800-1+825) (AA-023) and Kumbukkana Okkampitiya Maligawila Road (2+250-2+450) (B-513) | Monaragala | Monaragala | EMA Construction (Pvt) Ltd | 59% | 86302421.23 | 118529679.67 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-06 | 2026-10-02 | 2026-10-02
RDA/DRP/UVA/BAD/BAN/17R | Rehabilitation / Improvement of Welimada Boralanda Ohiya Horton Plains (0+000 -32+470)(B-508) | Badulla | Badulla | Shabi Lanka Construction | 7% | 148910781.64 | 116248771.28 | Awarded | Emergency |  |  |  | 2026-09-04 | 2027-01-07
RDA/DRP/UVA/BAD/BAD/01 | Rehabilitation / Improvement of Badulla Karametiya Andaulpotha Road (0+000-20+000 - Selected Sections) (B-036) | Badulla | Badulla | JD Builders | 71% | 210946129.78 | 292708768.01 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-30 | 2026-09-27 | 2026-09-27
RDA/DRP/UVA/BAD/BAD/04 | Rehabilitation / Improvement of Dikwella Jagulla Thalpitigala Road (0+000-6+600 - Selected Sections) (B-100) | Badulla | Badulla | PH Engineering & Construction (Pvt) Ltd | 67.5% | 272601362.28 | 318107616.89 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-30 | 2026-09-27 | 2026-09-27
RDA/DRP/UVA/BAD/BAD/05 | Rehabilitation / Improvement of Dikwella Jagulla Thalpitigala Road 6+600-15+000 - Selected Sections) (B-100) | Badulla | Badulla | PH Engineering & Construction (Pvt) Ltd | 57.5% | 219248828.55 | 259321056.45 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-27 | 2026-09-25 | 2026-09-25
RDA/DRP/UVA/BAD/BAN/14 | Rehabilitation / Improvement of Bandarawela Welimada Road (0+000-6+000) (B-044) | Badulla | Badulla | Senarathna Contractors | 73.5% | 232880104.48 | 274546113.13 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-27 | 2026-09-24 | 2026-09-24
RDA/DRP/UVA/BAD/BAD/03 | Rehabilitation / Improvement of Peradeniya Badulla Chenkaladi Road (90+000-123+000) (AA-005) | Badulla | Badulla | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 61% | 277749116.37 | 282102670.39 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-26 | 2026-09-23 | 2026-09-23
RDA/DRP/UVA/BAD/BAD/06 | Rehabilitation / Improvement of Baragala Haliela Road (25+525-38+000 - Selected Sections) (AA-016) and Bandarawela Uva Highland Etampitiya Road (5+000-16+100) (B-043) | Badulla | Badulla | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 57% | 254882804.5 | 302416798.7 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-26 | 2026-09-24 | 2026-09-24
RDA/DRP/UVA/BAD/BAN/16 | Rehabilitation / Improvement of Rendapola Ambewela Road (0+000-1+435) (B-507) and Peradeniya Badulla Chenkaladi Road (76+000-90+000) (AA-005) | Badulla | Badulla | Subasingha Contractors (Pvt) Ltd | 66% | 297237284.97 | 293827930.5 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-02 | 2026-09-30 | 2026-09-30
RDA/DRP/UVA/BAD/BAN/22 | REHABILITATION/IMPROVEMENT OF WELIMADA KIRKLEES ROAD ( From 0+000 to 17+250) | Badulla | Badulla | Suhada Enterprises | 77% | 246717227.79 | 288759369.79 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-27 | 2026-09-24 | 2026-09-24
RDA/DRP/UVA/MON/BIB/25 | Rehabilitation / Improvement of Colombo Rathnapura Wellawaya Batticaloa Road (259+080-292+800) (AA-004), Siyabalanduwa damana Ampara Road (0+000-24+000) (AA-025) and Bibila Medagama Nakkala Road (0+000-33+240) (B-056) and Passara Monaragala Road (7+120-26+240) (AA-022) | Monaragala | Monaragala | Ediriweera Construction | 51% | 74036604.05 | 103821878.45 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-07 | 2026-10-05 | 2026-10-05
RDA/DRP/UVA/BAD/BAN/18 | Rehabilitation / Improvement and Retainning Wall Construction Construction on Palugama Boralanda Haputhala Road (B353) (0+000 - 26+550), Haputale Dambatanna Road (B147) (1+700 - 1+735 RHS and 0+220 - 0+240 LHS) and Colombo Rathnapura Wellawaya Batticaloa Road (AA004) (167+750 - 213+750) | Badulla | Badulla | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 50% | 147759561.52 | 153768755.88 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-06 | 2026-11-03 | 2026-11-03
RDA/DRP/UVA/BAD/BAN/21 | Rehabilitation / Improvement of Wellawaya - Ella - Kumbalwela (14+000-30+0000 (AA-023), Ella - Passara (B113) (0+000 -5+000) and Beragala Hali-Ela (A016) (0+000 -25+000) | Badulla | Badulla | Suhada Enterprises | 56% | 321850877.98 | 321810896.4 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-06 | 2026-11-03 | 2026-11-03
RDA/DRP/UVA/BAD/BAD/11 | Rehabilitation / Improvement of (1) PASSARA MADULSIMA METIGAHATENNA ROAD (18+030-26+430) | Badulla | Badulla | Jayanetti Construction | 70% | 149405885.14 | 159486625.18 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-25 | 2026-11-22 | 2026-11-22
RDA/DRP/UVA/BAD/BAD/09 | Rehabilitation / Improvement of (1) ELLA PASSARA ROAD (23+800-27+080) | Badulla | Badulla | Nimsara Construction & Engineering (Pvt) Ltd | 66% | 254650056.89 | 257551081.92 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-25 | 2026-11-22 | 2026-11-22
RDA/DRP/UVA/BAD/BAD/08 | Rehabilitation / Improvement of Dikwella Jagulla Thalpitigala Road (B100) (15+000 - 23+665) and Badulla Kandy (New Rajamawatha) Road (0+000 - 6+000) | Badulla | Badulla | SF Construction (Pvt) Ltd | 48.5% | 188749480 | 177976215.86 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-25 | 2026-12-20 | 2026-12-20
RDA/DRP/UVA/BAD/BAD/13 | Rehabilitation / Improvement of Ella Passara Road (B113) (9+500 - 27+000) | Badulla | Badulla | SF Construction (Pvt) Ltd | 66.5% | 290901643.58 | 292073080.75 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-25 | 2026-11-22 | 2026-11-22
RDA/DRP/UVA/BAD/BAN/20 | Rehabilitation / Improvement of Bandarawela - Liyangahawela - Poonagala Road (B042) (10+000 -15+000) | Badulla |  | D K S Construction | 44.5% | 283401035.13 | 301203263.92 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-20 | 2026-10-17
RDA/DRP/UVA/BAD/BAN/24 | Rehabilitation / Improvement of Rendapola Ambewela Road | Badulla |  | Gamage Builders | 36% | 290409872.96 | 271955137.78 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-01 | 2026-12-30
RDA/DRP/UVA/BAD/BAN/23 | Rehabilitation / Improvement of Colombo Rathnapura Wellawaya Batticaloa Road (AA004) (201+000 - 204+000) | Badulla |  | D K S Construction | 21% | 322192938.69 | 325833013.16 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-03 | 2027-01-07
RDA/DRP/UVA/BAD/BAN/31 | Rehabilitation / Improvement of Colombo Rathnapura Wellawaya Batticaloa Road (AA004) (212+000 - 213+500) | Badulla |  | Nimna Holdings (Pvt) Ltd | 16% | 239935072.9 | 232794296.45 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-04 | 2027-03-05