## Sheet1
All Projects
Date: 2026-11-04
Contract No | Contract Name | Province | District | PD Region | CE Region | EE Division | Category | Programme | Contractor | Consultant | Estimate (LKR) | Contract Amount (LKR) | Status | Progress % | LOA Date | Planned Finish
RDA/DRP/CEN/KDY/KAD/11 | Rehabilitation / Improvement of Nawalapitiya - Dolosbage Road ( B -318) ( 10+500 - 19+350 ), Dedugala Dolosbage Road ( B -588) ( 10+100 - 12+410 ) | Central Province | Kandy | Central Province | Kandy | Kadugannawa | Emergency | DRRRP | Tiasa Construction (Pvt) Ltd | Team Leader | 275515701.42 | 193404194.96 | Awarded | 26.5% | 2026-03-17 | 2026-09-23
RDA/DRP/CEN/KDY/KAN/14 | Rehabilitation /Improvement of Katugasthota Medawala road ( B 0206)( 0 + 000 - 9+370) | Central Province | Kandy | Central Province | Kandy | Kandy | Emergency | DRRRP | Alucon Industries (Pvt) Ltd | Team Leader | 72827654.9 | 74836014.77 | Awarded | 9% | 2026-08-14 | 2027-03-01
RDA/DRP/CEN/KDY/KDY/15 | Rehabilitation / Improvement of Galagedara Rambukkana ( B 122) ( 0+000 - 18+000) | Central Province | Kandy | Central Province | Kandy | Kandy | Emergency | DRRRP | Jayawansa Construction (Pvt) Ltd | Team Leader | 79953569.86 | 79071437.68 | Awarded | 6% | 2026-08-14 | 2027-03-09
RDA/DRP/CEN/KDY/KDY/19 | Rehabilitation / Improvement of Poojapitiya Alawathugoda road ( B 377) ( 0+000 - 8+000) | Central Province | Kandy | Central Province | Kandy | Kandy | Emergency | DRRRP | Jayawansa Construction (Pvt) Ltd | Team Leader | 64393315.7 | 67935586.77 | Awarded | 5% | 2026-09-14 | 2027-03-18
RDA/DRP/CEN/KDY/KUN/20 | Rehabilitation / Improvement to Structures on Madolkelle - Kabaragala - Kandenuwara Road (B 257) (4+000 - 8+000) | Central Province | Kandy | Central Province | Kandy | Kundasale | Emergency | DRRRP | Samindra Construction | Team Leader | 28660618.7 | 31558227.98 | Awarded | 53% | 2026-07-06 | 2026-11-15
RDA/DRP/CEN/KDY/KUN/21 | Improvement of Pitiyegedara-Waththegama-Iriyagasthenna Road (0+000-5+400) | Central Province | Kandy | Central Province | Kandy | Kundasale | Emergency | DRRRP | Jayasinghe Construction (Pvt) Ltd | Team Leader | 314486807.16 | 257721453.96 | Awarded | 12% | 2026-03-12 | 2026-10-28
RDA/DRP/CEN/KDY/KUN/22 | Improvement to Damaged Road Section on Weeragantota - Randenigala Road. (From CH 19+000 To CH 27+200) | Central Province | Kandy | Central Province | Kandy | Kundasale | Emergency | DRRRP | SD Civil Construction (Pvt) Ltd | Team Leader | 333005906.52 | 224968435.78 | Awarded | 67% | 2026-03-12 | 2026-09-23
RDA/DRP/CEN/KDY/KUN/24R | Rehabilitation / Improvement of Flood damage on Katugastota - Madawala - Bamberella Road (B205) (0-000 - 7+200 and 13+000 - 13+045) | Central Province | Kandy | Central Province | Kandy | Kundasale | Emergency | DRRRP | Nimsara Construction & Engineering (Pvt) Ltd | Team Leader | 80438429.85 | 79507501.11 | Awarded | 5% | 2026-08-31 | 2027-03-14
RDA/DRP/CEN/KDY/KUN/25 | Construction of Gabion Retaining Wall on Katugastota Madawala Bamberella Road(LHS 9+600 - 9+655), (15+450 - 15+500), (10+235 - 10+300) and Wattegama Matale road (0+400 - 0+435) | Central Province | Kandy | Central Province | Kandy | Kundasale | Emergency | DRRRP | S N O Builders (Pvt) Ltd | Team Leader | 178738774.63 | 157909825.01 | Awarded | 59% | 2026-06-16 | 2026-11-01
RDA/DRP/CEN/KDY/KUN/27 | Improvement to Structures on Kandy - Jaffna Road 6+500 - 9+910 | Central Province | Kandy | Central Province | Kandy | Kundasale | Emergency | DRRRP | Gihan Enterprise | Team Leader | 122896558.88 | 113434139.4 | Awarded | 66% | 2026-06-16 | 2026-10-27
RDA/DRP/CEN/KDY/KUN/29 | Improvement to Structures on Kandy - Mahiyanganaya - Padiyaththalawa Road (24+000-71+500) and Moragahamula victoria damtop | Central Province | Kandy | Central Province | Kandy | Kundasale | Emergency | DRRRP | S N O Builders (Pvt) Ltd | Team Leader | 100543979.99 | 91559621.04 | Awarded | 61% | 2026-06-16 | 2027-01-03
RDA/DRP/CEN/MTL/MTL/31R | Rehabilitation / Improvement of Matale - Udupihilla Road (AB026) (0+000 - 6+000) | Central Province | Matale | Central Province | Matale | Matale | Emergency | DRRRP | Alucon Industries (Pvt) Ltd | Team Leader | 0 | 63704849.78 | Awarded | 7.5% | 2026-08-14 | 2026-11-30
RDA/DRP/CEN/MTL/MTL/32 | Rehabilitation / Improvement of Kandy Jaffna (A-009)(17+710 - 46+450), Thalgodapitiya - Yatawatta - Dombawela (B-409) (15+030 - 26+800), Palapathwela - Galewela Road B-346)(0+000 - 8+100) Roads | Central Province | Matale | Central Province | Matale | Matale | Emergency | DRRRP | Lahiru Construction and Consultants (Pvt) Ltd | Matale EE | 395635536.56 | 292279354.08 | Awarded | 68% | 2026-03-12 | 2026-10-30
RDA/DRP/CEN/MTL/MTL/33 | Rehabilitation / Improvement of Wattegama Matale Road (5+280 - 13+160) and Ukuwela Railway station (0+000 - 0+190) | Central Province | Matale | Central Province | Matale | Matale | Emergency | DRRRP | Jayasinghe Construction (Pvt) Ltd | Matale EE | 188777407.11 | 165006430.79 | Awarded | 30% | 2026-03-16 | 2026-07-31
RDA/DRP/CEN/MTL/MTL/35 | Rehabilitation / Improvement of Rattota Gammaduwa Road (7+100 - 11+260) | Central Province | Matale | Central Province | Matale | Matale | Emergency | DRRRP | Kanwel Constructions & Civil Engineering (Pvt) Ltd | Matale EE | 291904507.83 | 266607902.15 | Awarded | 63% | 2026-03-16 | 2026-10-30
RDA/DRP/CEN/MTL/MTL/38 | Rehabilitation / Improvement of Kalalpitiya Ukuwela Elkaduwa Road (B 180) (0+000 - 13+470) | Central Province | Matale | Central Province | Matale | Matale | Emergency | DRRRP | Ediriweera Construction | Matale EE | 304428814.88 | 281166339.8 | Awarded | 14% | 2026-07-06 | 2027-01-27
RDA/DRP/CEN/MTL/MTL/41 | Rehabilitation / Improvement of Matale Illukkumbura Laggala Road (B 274) (4+000 - 18+000) | Central Province | Matale | Central Province | Matale | Matale | Emergency | DRRRP | Vikum Construction | Matale EE | 265809486.28 | 276683432.37 | Awarded | 11% | 2026-08-14 | 2027-03-02
RDA/DRP/CEN/MTL/NAL/48R | Rehabilitation/Improvement of surfacing (ASphalt) hard shoulder,Shoulder, drain construction at Beligamuwa - Hebarawa- Wilgamuwa Road (B-577) (6+260 -11+950) | Central Province | Matale | Central Province | Matale | Nalanda | Emergency | DRRRP | S A P Engineering (Pvt) Ltd | Nalanda EE | 42736925.8 | 50471466.08 | Awarded | 5% | 2026-08-31 | 2027-03-04
RDA/DRP/CEN/MTL/NAL/49 | Rehabilitation /Improvement of Drains,Hard shoulder & Cash barrier at Naula- Elahera- Pallegama- Hettipola Road (B-312) (8+200-61+240) | Central Province | Matale | Central Province | Matale | Nalanda | Emergency | DRRRP | Platinum Holdings Lanka (Private) Limited | Nalanda EE | 56512677.41 | 44706119.13 | Awarded | 70% | 2026-05-29 | 2026-11-18
RDA/DRP/CEN/MTL/NAL/51 | Rehabilitation /Improvement of Retaining wall , drains and shoulder construction Bowathenna Access Road (B-064) (0+000-2+410) | Central Province | Matale | Central Province | Matale | Nalanda | Emergency | DRRRP | Platinum Holdings Lanka (Private) Limited | Nalanda EE | 25992198.15 | 17458592.78 | Awarded | 90% | 2026-05-29 | 2026-10-14
RDA/DRP/CEN/NUE/HAN/57 | Rehabilitation / Improvement of Keerthibandarapura Naranthalawa Road ( B -511 ) ( 0+000 - 4+100 ) | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Hanguranketha | Emergency | DRRRP | Samindra Construction | Hanguranketha EE | 44694533.62 | 47755538.96 | Awarded | 30% | 2026-07-09 | 2026-10-28
RDA/DRP/CEN/NUE/NUE/60R | Rehabilitation / Improvement of Peradeniya Badulla Chenkaladi Road (A005) (40+750 - 42+850) | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Nuwara Eliya | Emergency | DRRRP | KSJ Construction (Pvt) Ltd | Team Leader | 338287510.33 | 336313078.73 | Awarded | 10% | 2026-09-21 | 2027-04-06
RDA/DRP/CEN/NUE/NUE/66 | Rehabilitation / Improvement of Nuwara Eliya Town Road (0+000 - 1+695 ) (0+000 - 0+240 ) | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Nuwara Eliya | Emergency | DRRRP | KSJ Construction (Pvt) Ltd | Team Leader | 205630098.81 | 161841095.7 | Awarded | 69% | 2026-03-12 | 2026-07-31
RDA/DRP/CEN/NUE/NUE/67 | Rehabilitation / Improvement of Harangala - Kalapitiya - Kumbaloluwa Road (10+480 km - 17+140 km) | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Nuwara Eliya | Emergency | DRRRP | KSJ Construction (Pvt) Ltd | Nuwara Eliya EE | 302933613.6 | 239417811.34 | Awarded | 78% | 2026-03-17 | 2026-10-30
RDA/DRP/CEN/NUE/NUE/68 | Rehabilitation / Improvement of Thawalanthenna Thalawakelle Road (0+000 - 8+000) & (10+000 - 33+200) | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Nuwara Eliya | Emergency | DRRRP | Green Scene Construction (Pvt) Ltd | Nuwara Eliya EE | 296813201.99 | 213999600.01 | Awarded | 40% | 2026-03-24 | 2026-10-30
RDA/DRP/CEN/NUE/NUE/69 | Rehabilitation / Improvement of Ulapane Pussallawa Road (6+440 - 15+950) | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Nuwara Eliya | Emergency | DRRRP | Southern Group Civil Construction (Pvt) Ltd | Nuwara Eliya EE | 365868062.33 | 266045892.19 | Awarded | 56% | 2026-03-16 | 2026-10-30
RDA/DRP/CEN/NUE/NUE/86 | Rehabilitation / Improvement of Approch road to R'way station (Watagoda/ Thalawakele) Road | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Nuwara Eliya | Emergency | DRRRP | Pragathi Civil Construction | Nuwara Eliya EE | 41996395.31 | 33765626.86 | Awarded | 20% | 2026-05-19 | 2026-09-10
RDA/DRP/CEN/NUE/NUR/97 | Rehabilitation/Improvement of Nawalapitiya Ginigathena Road (B-319)(7+200-12+200) | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Norwood | Emergency | DRRRP | Jayawansa Construction (Pvt) Ltd | Norwood EE | 104490700.33 | 93758217.76 | Awarded | 62% | 2026-05-19 | 2026-09-15
RDA/DRP/CEN/NUE/NUR/98 | Rehabilitation/Improvement Harangala Kalapitiya Road (B-148) (0+000-10+700), Approach Road to Hrangala Dam Crest Road (B-491) (0+000-3+820), Nawalapitiya Harangala Road (B-306) (0+000-10+700) | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Norwood | Emergency | DRRRP | Pragathi Civil Construction | Norwood EE | 222691835.72 | 188617394.68 | Awarded | 44% | 2026-05-19 | 2026-12-16
RDA/DRP/CEN/NUE/NUR/101 | Rehabilitation/Improvement of Hatton Maskeliya Delhouse Road (B-149) (0+000-31+970) | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Norwood | Emergency | DRRRP | Sooriya Builders | Norwood EE | 108611538.67 | 86746198.17 | Awarded | 31% | 2026-05-19 | 2026-11-11
RDA/DC/DRP/CP/NE/NRW/02 | REHABILITATION/ IMPROVEMENT OF APPROCH ROAD TO LAXAPANA POWER HOUSE ROAD CH 6+100 - 12+000 | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Norwood | DC - Roads | DRRRP | U.K.S Lanka Engineering (Pvt) Ltd | Norwood EE | 348620000 | 374859845.1 | Awarded | 9% | 2026-07-16 | 2027-07-29
RDA/DC/DRP/CP/NE/NE/04 | REHABILITAION/ IMPROVEMENTS OF LADY MACALUMS DRIVE ROAD (2+850 - 5+600KM) | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Nuwara Eliya | DC - Roads | DRRRP | KDA Weerasinghe & Co (Pvt) Ltd | Team Leader | 560630000 | 636338397 | Awarded | 1% | 2026-08-20 | 2028-03-15
RDA/DC/DRP/SLOPE/CP/KDY/GAMPOLA-09 | MITIGATION OF FAILURES ALONG RDA ROADS DUE TO CYCLONE DITWAH GAMPOLA NAWALAPITIYA ROAD (AB013) CHAINAGE 10+350 KM | Central Province | Kandy | Central Province | Kandy | Gampola | DC - Slope | DRRRP | Sanguine Engineering (Pvt) Ltd | Team Leader | 479898195.86 | 386699553.58 | Awarded | 9.3% | 2026-08-19 | 2027-06-30
RDA/DC/DRP/CP/NE/NRW/03 | REHABILITATION/ IMPROVEMENT TO ROZELLA RAILWAY STATION ROAD (0+000 - 3+300) KM AND WATAWALA RAILWAY STATION ROAD (0+000 - 1+850) KM | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Norwood | DC - Roads | DRRRP | Nagma Engineering (Pvt) Ltd | Norwood EE | 509310000 | 604298969.28 | Awarded | 19% | 2026-08-20 | 2027-09-14
RDA/DRP/SAB/KEG/KEG/14 | Rehabilitation / Improvement of Damaged Locations in Colombo Kandy Road from 56+050-98+950 | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Kegalle | Emergency | DRRRP | Tudawe Brothers (Pvt) Ltd |  | 267884733.58 | 261228130.78 | Awarded | 65% | 2026-03-12 | 2026-08-05
RDA/DRP/UVA/BAD/BAD/02 | Rehabilitation / Improvement of Demodara SpringValley Badulla Road (16+145-20+800) - selected Sections) (B-097) | Uva Province | Badulla | Uva Province | Badulla | Badulla | Emergency | DRRRP | Priyankara Industries & Contractors |  | 286001165.69 | 241775532.44 | Awarded | 66% | 2026-03-12 | 2026-09-22
RDA/DRP/UVA/BAD/MAH/27 | Rehabilitation / Improvement of Dambagahapitiya Pinnagolla arawa Meegahakeula Road (8+200-8+250) (B-086)/ Bibile-Uraniya-Mahiyanganaya Road | Uva Province | Badulla | Uva Province | Badulla | Badulla | Emergency | DRRRP | EMA Construction (Pvt) Ltd |  | 103692871.49 | 73623757.9 | Awarded | 79.5% | 2026-03-12 | 2026-09-21
RDA/DRP/SAB/RAT/PEL/20 | Rehabilitation / Improvement of Pelmadulla - Pelmadulla - Embilipitiya - Nonagama (2+050 - 4+320) & Retaining wall Construction on Pelmadulla - Embilipitiya - Nonagama Road 5/4 - 5/5 (LHS) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | K.E.P. Construction |  | 224909805.06 | 194327188.51 | Awarded | 31% | 2026-03-12 | 2026-07-06
RDA/DRP/UVA/BAD/BAN/19 | Rehabilitation / Improvement of Bandarawela Liyangahawela Poonagala Road (5+000 -10+000) (B-042) | Uva Province | Badulla | Uva Province | Badulla | Badulla | Emergency | DRRRP | Senura Civil Engineering (Pvt) Ltd |  | 220745970.7 | 216526489.67 | Awarded | 40% | 2026-03-12 | 2026-09-23
RDA/DRP/UVA/BAD/BAN/15R | Rehabilitation / Improvement of Bandarawela Welimada Road (6+000-20+200) (B-044) | Uva Province | Badulla | Uva Province | Badulla | Badulla | Emergency | DRRRP | Subasingha Contractors (Pvt) Ltd |  | 237954791.68 | 228783135.84 | Awarded | 12% |  | 2027-03-05
RDA/DRP/SAB/KEG/KEG/16 | Rehabilitation / Improvement of Kegalle Siyambalapitiya Dewalegama Road, Polgahawela Kegalle Road and Mawanella Aranayaka Horewela Road | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Kegalle | Emergency | DRRRP | Creates Consultant and Construction |  | 278060284.2 | 258281578.64 | Awarded | 60% | 2026-03-12 | 2026-08-16
RDA/DRP/UVA/MON/MON/28 | Rehabilitation / Improvement of Colombo Galle Hambanthota Wellawaya Road (305+650-305+850) (AA-002), Wellawaya Ella Kumbalwela Road (0+800-1+825) (AA-023) and Kumbukkana Okkampitiya Maligawila Road (2+250-2+450) (B-513) | Uva Province | Monaragala | Uva Province | Monaragala | Monaragala | Emergency | DRRRP | EMA Construction (Pvt) Ltd |  | 118529679.67 | 86302421.23 | Awarded | 59% | 2026-03-12 | 2026-10-02
RDA/DRP/SAB/KEG/RUW/29 | Rehabilitation / Improvement of Dehiowita - Daraniyagala - Nooriya Road (From 13+845 to 23+850) | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Kegalle | Emergency | DRRRP | SSP Engineers (Pvt) Ltd |  | 227460547.85 | 217629047.45 | Awarded | 70% | 2026-03-12 | 2026-06-25
RDA/DRP/UVA/BAD/BAN/17R | Rehabilitation / Improvement of Welimada Boralanda Ohiya Horton Plains (0+000 -32+470)(B-508) | Uva Province | Badulla | Uva Province | Badulla | Badulla | Emergency | DRRRP | Shabi Lanka Construction |  | 116248771.28 | 148910781.64 | Awarded | 7% |  | 2027-01-07
RDA/DRP/UVA/BAD/BAD/01 | Rehabilitation / Improvement of Badulla Karametiya Andaulpotha Road (0+000-20+000 - Selected Sections) (B-036) | Uva Province | Badulla | Uva Province | Badulla | Badulla | Emergency | DRRRP | JD Builders |  | 292708768.01 | 210946129.78 | Awarded | 71% | 2026-03-16 | 2026-09-27
RDA/DRP/UVA/BAD/BAD/04 | Rehabilitation / Improvement of Dikwella Jagulla Thalpitigala Road (0+000-6+600 - Selected Sections) (B-100) | Uva Province | Badulla | Uva Province | Badulla | Badulla | Emergency | DRRRP | PH Engineering & Construction (Pvt) Ltd |  | 318107616.89 | 272601362.28 | Awarded | 67.5% | 2026-03-16 | 2026-09-27
RDA/DRP/UVA/BAD/BAD/05 | Rehabilitation / Improvement of Dikwella Jagulla Thalpitigala Road 6+600-15+000 - Selected Sections) (B-100) | Uva Province | Badulla | Uva Province | Badulla | Badulla | Emergency | DRRRP | PH Engineering & Construction (Pvt) Ltd |  | 259321056.45 | 219248828.55 | Awarded | 57.5% | 2026-03-13 | 2026-09-25
RDA/DRP/UVA/BAD/BAN/14 | Rehabilitation / Improvement of Bandarawela Welimada Road (0+000-6+000) (B-044) | Uva Province | Badulla | Uva Province | Badulla | Badulla | Emergency | DRRRP | Senarathna Contractors |  | 274546113.13 | 232880104.48 | Awarded | 73.5% | 2026-03-13 | 2026-09-24
RDA/DRP/SAB/RAT/EMB/04 | Rehabilitation / Improvement of Galle - Deniyaya-Madampe Road (88+000-95+000) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | SN Projects Lanka (Pvt) Ltd |  | 318792416.26 | 290799045.34 | Awarded | 22% | 2026-03-20 | 2026-07-07
RDA/DRP/SAB/RAT/EMB/12 | Rehabilitation / Improvement of Galle -Deniyaya-Madampe Road (95+000-100+000) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | SN Projects Lanka (Pvt) Ltd |  | 319465519.22 | 290733855.4 | Awarded | 26% | 2026-03-13 | 2026-07-07
RDA/DRP/SAB/KEG/KEG/13 | Rehabilitation / Improvement of damage locations at Ambepussa Kurunegala Trincomalee Road, Warakapola Kandalama Road, Warakapola Buypass Road, Morontota Arandara Road, Galigamuwa Ruwanwella Road, Gevilipitiya Hettimulla Road, Kegalle Bulattkohupitiya, Karawanella Road, Mawanella Hemmathagama Gampola Road and Rambukkana Mawanella Road in Kegalle Executive Engineers Division. | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Kegalle | Emergency | DRRRP | Senarath Engineering (Pvt) Ltd |  | 258512761.66 | 247437818.24 | Awarded | 75% | 2026-03-13 | 2026-08-29
RDA/DRP/SAB/RAT/RAT/22 | Rehabilitation / Improvement and Asphalt Overlaying on Ayagama Kukulegama Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | Keangnam Engineering & Construction (Pvt) Ltd |  | 316600518.19 | 280145000.74 | Awarded | 42.9% | 2026-03-13 | 2026-06-26
RDA/DRP/SAB/RAT/RAT/26 | Rehabilitation / Improvement of Malwala - Carney Road (Ch. 11+000 - Ch. 14+972) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | SSP Engineers (Pvt) Ltd |  | 199494622.85 | 184511228.94 | Awarded | 85.8% | 2026-03-13 | 2026-07-07
RDA/DRP/SAB/RAT/RAT/25 | Rehabilitation / Improvement and Asphalt Overlaying on Malwana Charney (6+020 - 11+000) & Construction of Gabion Wall at 2+510, 2+847 | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | Wijeratne Construction |  | 269615801.69 | 242356869.5 | Awarded | 62% | 2026-03-13 | 2026-07-07
RDA/DRP/UVA/BAD/BAD/03 | Rehabilitation / Improvement of Peradeniya Badulla Chenkaladi Road (90+000-123+000) (AA-005) | Uva Province | Badulla | Uva Province | Badulla | Badulla | Emergency | DRRRP | Kanwel Constructions & Civil Engineering (Pvt) Ltd |  | 282102670.39 | 277749116.37 | Awarded | 61% | 2026-03-12 | 2026-09-23
RDA/DRP/UVA/BAD/BAD/06 | Rehabilitation / Improvement of Baragala Haliela Road (25+525-38+000 - Selected Sections) (AA-016) and Bandarawela Uva Highland Etampitiya Road (5+000-16+100) (B-043) | Uva Province | Badulla | Uva Province | Badulla | Badulla | Emergency | DRRRP | Kanwel Constructions & Civil Engineering (Pvt) Ltd |  | 302416798.7 | 254882804.5 | Awarded | 57% | 2026-03-12 | 2026-09-24
RDA/DRP/SAB/RAT/PEL/21 | Rehabilitation / Improvement of Pabahinna - Kubalgama - Rajawaka - Kapugala Road (2+000-7+700) & Retaining wall Construction of Colombo - Rathnapura - Wellawaya- Batticaloa Road (156/2 (RHS), 155/6, 133/7 - 133/8 (RHS), 122/5- 122/4 (RHS) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | Samdam Engineering & Constructions (Pvt) Ltd |  | 215458780.2 | 184536305.86 | Awarded | 32% | 2026-03-13 | 2026-07-06
RDA/DRP/UVA/BAD/BAN/16 | Rehabilitation / Improvement of Rendapola Ambewela Road (0+000-1+435) (B-507) and Peradeniya Badulla Chenkaladi Road (76+000-90+000) (AA-005) | Uva Province | Badulla | Uva Province | Badulla | Badulla | Emergency | DRRRP | Subasingha Contractors (Pvt) Ltd |  | 293827930.5 | 297237284.97 | Awarded | 66% | 2023-03-19 | 2026-09-30
RDA/DRP/UVA/BAD/BAN/22 | REHABILITATION/IMPROVEMENT OF WELIMADA KIRKLEES ROAD ( From 0+000 to 17+250) | Uva Province | Badulla | Uva Province | Badulla | Badulla | Emergency | DRRRP | Suhada Enterprises |  | 288759369.79 | 246717227.79 | Awarded | 77% | 2026-03-13 | 2026-09-24
RDA/DRP/UVA/MON/BIB/25 | Rehabilitation / Improvement of Colombo Rathnapura Wellawaya Batticaloa Road (259+080-292+800) (AA-004), Siyabalanduwa damana Ampara Road (0+000-24+000) (AA-025) and Bibila Medagama Nakkala Road (0+000-33+240) (B-056) and Passara Monaragala Road (7+120-26+240) (AA-022) | Uva Province | Monaragala | Uva Province | Monaragala | Monaragala | Emergency | DRRRP | Ediriweera Construction |  | 103821878.45 | 74036604.05 | Awarded | 51% |  | 2026-10-05
RDA/DRP/SAB/RAT/RAT/24 | Rehabilitation / Improvement and Asphalt Overlaying on Kalawana - Deepdeen Rakwana (4+255-9+809) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | SSP Engineers (Pvt) Ltd |  | 264741911.81 | 236752750.59 | Awarded | 85% | 2026-03-19 | 2026-06-24
RDA/DRP/SAB/KEG/RUW/28 | Rehabilitation / Improvement of Bulathkohupitiya Dedugala Road, Warakapola Ruwanwella Road, Alawathura- Yatapana - Kotiyakumbura Road and Avissawella - Hatton - Nuwaraeliya Road | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Kegalle | Emergency | DRRRP | Southern Group Civil Construction (Pvt) Ltd |  | 284539377.98 | 260537133.84 | Awarded | 50% | 2026-03-26 | 2026-09-11
RDA/DRP/SAB/KEG/RUW/35 | Yatiyanthota - Poonagala - Meenagala Road (from 13+400 to 18+200) | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Kegalle | Emergency | DRRRP | Southern Group Civil Construction (Pvt) Ltd |  | 172314426.38 | 170714785.54 | Awarded | 25% | 2026-03-12 | 2026-09-11
RDA/DPR/NCP/ANU/ANU/02 | Rehabilitation / Improvement and Construction of Drainge Canal for Kumbichchan Kulama Spillway on Maitreepala Senanayake Mawatha (1+970 - 2+090 km) | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Emergency | DRRRP | SMA Construction (Pvt) Ltd |  | 178990814.77 | 138891057.65 | Awarded | 50% | 2026-04-06 | 2026-10-19
RDA/DPR/NCP/ANU/ANU/03 | Rehabilitation / Improvement Construction of Drainge Canal for Thambuttegama Tank Spill on Padeniya - Anuradhapura Road (59+420 - 59+610) & Construction of Drainge Canal for Protection Road on Andarawewa - Balaluwewa Road(16+580 - 16+680) | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Emergency | DRRRP | SMA Construction (Pvt) Ltd |  | 174596369.9 | 132437825.5 | Awarded | 38% | 2026-04-06 | 2026-10-19
RDA/DRP/WP/GAM/NEG/19 | Rehabilitation / Improvement of Negombo-Mirigama Road (5+000-6+000) and Negombo-Giriulla Road (29+000-34+000) | Western Province | Gampaha | Western Province | Gampaha | Gampaha | Emergency | DRRRP | Tudawe Brothers (Pvt) Ltd |  | 222010882.78 | 206184462.57 | Awarded | 20% | 2026-04-06 | 2026-11-02
RDA/DRP/WP/GAM/NIT/21 | Rehabilitation / Improvement of Hanwella Urapola Road (3+000 - 10+100), Structure Construction on Delgoda Dompe Giridara Road (0+000- 10+070) and Urapola Wathuragama Road (0+000- 7+080 ) and Drain Construction on Negombo-Mirigama road (21+000 - 30+580) | Western Province | Gampaha | Western Province | Gampaha | Gampaha | Emergency | DRRRP | Tudawe Brothers (Pvt) Ltd |  | 231075356.57 | 221768903.84 | Awarded | 28% | 2026-04-06 | 2026-11-02
RDA/DRP/WP/GAM/GAM/10 | Rehabilitation / Improvement of Old Minuwangoda Gampaha - Miriswatta Road (9+000 - 10+000) and Minuwangoda - Gampaha Road (0+000 - 5+300) | Western Province | Gampaha | Western Province | Gampaha | Gampaha | Emergency | DRRRP | Senarath Engineering (Pvt) Ltd |  | 110481340.2 | 92177672.52 | Awarded | 2% | 2026-04-06 | 2026-07-24
RDA/DRP/WP/GAM/GAM/12 | Rehabilitation / Improvement of Acces Road to Peliyagoda interchange (0+000 - 2+100), Colombo - Kandy Road (6+500-19+000) and Kelaniya - Waragoda Road (0+000-3+220) | Western Province | Gampaha | Western Province | Gampaha | Gampaha | Emergency | DRRRP | Senarath Engineering (Pvt) Ltd |  | 170010323.36 | 151956608.92 | Awarded | 2% | 2026-04-06 | 2026-07-24
RDA/DRP/WP/GAM/NIT/20 | Rehabilitation / Improvement of Bothale Mirigama Road (3+750-4+800), Warakapola Kandalama Road (7+000-8+000), (8+500-9+000) & (9+500-10+900), Negombo Mirigama Road and Construction of Gabion Wall on Colombo - Kandy Road at 54+950,Warakapola Kandalama Road at Culvert No. 10/4 LHS and Widening of Culvert Nos. 4/1 LHS 4/3 Bothsides and Reconstruction of Culvert No. 4/2 on Veyangoda Banduragoda Road | Western Province | Gampaha | Western Province | Gampaha | Gampaha | Emergency | DRRRP | Jeyanthan Construction |  | 245395696.16 | 217881464.96 | Awarded | 46% | 2026-04-06 | 2026-09-03
RDA/DRP/WP/GAM/NIT/22 | Rehabilitation / Improvement of Delgoda Dompe Giridara Road (Selected Sections between 2+000-12+100) | Western Province | Gampaha | Western Province | Gampaha | Gampaha | Emergency | DRRRP | Senarath Engineering (Pvt) Ltd |  | 294920837.23 | 264745054.48 | Awarded | 1% | 2026-04-06 | 2026-10-23
RDA/DRP/WP/GAM/NIT/23 | Rehabilitation / Improvement of Kalagedihena Veyangoda Road (0+000 -3+000), Pasyala Attanagalla Road (0+000 - 6+400) and Colombo - Kandy Road (38+620 -38+720) | Western Province | Gampaha | Western Province | Gampaha | Gampaha | Emergency | DRRRP | Senarath Engineering (Pvt) Ltd |  | 305207472.65 | 258218314.97 | Awarded | 1% | 2026-04-06 | 2026-10-23
RDA/DRP/SAB/KEG/RUW/30 | Rehabilitation of Dehiovita - Daraniyagala - Nooriya Road (from 23+850 to 27+960) due to catastrophic disaster cyclone Ditwa | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Kegalle | Emergency | DRRRP | Accon Engineering (Pvt) Ltd |  | 179826720.59 | 169223910.8 | Awarded | 68% | 2026-04-06 | 2026-08-21
RDA/DRP/SAB/KEG/RUW/31 | Rehabilitation of Kegalle - Bulathkohupitiya - Karawanella Road due to catastrophic disaster cyclone Ditwa | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Kegalle | Emergency | DRRRP | Tudawe Brothers (Pvt) Ltd |  | 284390126.9 | 269890586.86 | Awarded | 18% | 2026-04-06 | 2026-08-31
RDA/DRP/WP/COL/AVI/02 | Rehabilitation / Improvement of Damage Sections on Colombo - Hanwella Low Level Road (AB010) (23+000 - 26+715) & Hanwella Cross Road (B145) (0+000 - 0+800) | Western Province | Colombo | Western Province | Colombo | Colombo | Emergency | DRRRP | Keangnam Engineering & Construction (Pvt) Ltd |  | 299392762.2 | 279374027.9 | Awarded | 29% | 2026-04-07 | 2026-07-21
RDA/DRP/WP/COL/AVI/03 | Rehabilitation / Improvement and Asphalt Overlaying on Colombo - Horana Road (B084) (10+500 - 13+500) | Western Province | Colombo | Western Province | Colombo | Colombo | Emergency | DRRRP | Keangnam Engineering & Construction (Pvt) Ltd |  | 201633881.18 | 176739557.41 | Awarded | 3% | 2026-04-07 | 2026-06-23
RDA/DRP/WP/COL/AVI/04 | Rehabilitation / Improvement and Asphalt Overlaying on Mampe Kottawa Road (B267) (0+750 - 3+400) (5+100 - 6+120)) | Western Province | Colombo | Western Province | Colombo | Colombo | Emergency | DRRRP | Keangnam Engineering & Construction (Pvt) Ltd |  | 108030624.38 | 94697340.01 | Awarded | 65% | 2026-04-07 | 2026-06-23
RDA/DRP/WP/COL/AVI/05 | Rehabilitation / Improvement and Asphalt Overlaying on Panagoda Henpita Road (B354) (0+000 - 6+440) | Western Province | Colombo | Western Province | Colombo | Colombo | Emergency | DRRRP | Keangnam Engineering & Construction (Pvt) Ltd |  | 250078803.62 | 225228168.18 | Awarded | 3% | 2026-04-07 | 2026-06-23
RDA/DRP/NWP/KURU/KULI/01R | Rehabilitation / Improvement of Selected Sections on Pannala Kuliyapitiya Road (B356) (0+000-6+000), Dandagamuwa Udawela Road (B088) (4+000 - 6+000), Marawila Udubaddawa Road (B272) (11+000 - 12+000), Kurunegala Narammala Madampe Road (B247) (52+000 - 54+000), Narammala Dankotuwa Road (B308) (16+000-37+000) and Alawwa Maharagama Road (B009) (1+000 - 14+200) in Kuliyapitiya EE Division | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | Emergency | DRRRP | Can Construction and Consultancy (Pvt) Ltd |  |  | 181456551.09 | Awarded | 12% |  | 2026-12-25
RDA/DRP/NWP/KURU/KURU/04 | Rehabilitation / Improvement of Muththettugala Hiripitiya Road (B300) (10+880 - 11+080) & Vilakatupotha Ganewatta Kumbukgete road (B478) (9+100 - 9+400) | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | Emergency | DRRRP | TMC Construction (Pvt) Ltd |  | 105193927.73 | 97503423.17 | Awarded | 62% | 2026-04-07 | 2026-07-22
RDA/DRP/NWP/KURU/MAHO/05 | Rehabilitation / Improvement of Galgamuwa - Nikawewa Road (B126) (6+000-20+000), Danikithawa - Ambanpola Road (B089) (20+925 - 21+000), Nikaweratiya - Moragollagama - Siyambalangamuwa Road (B326) (40+760 - 48+240), Malsiripura - Rambe Road (B610) (7+500 - 9+650), Ibbagamuwa - Kumbukgate - Madagalla Road (B159) (16+450 - 28+680), Hiripitiya - Galtenwewa Road (B609) (9+580-9+680), Padeniya - Anuradapura Road (AA028) (8+480-8+800) and Katugasthota - Kurunegala - Puththalama Road (AA010) (73+745-73 -870) in Maho EE Division | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | Emergency | DRRRP | St. Anthony's Construction |  | 166163663.09 | 151515024.36 | Awarded | 70% | 2026-04-07 | 2026-09-01
RDA/DRP/SAB/RAT/EMB/01 | Rehabilitation / Improvement of Kalawana - Deepdeen - Rakwana Road (15+000-46+000) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | SSP Engineers (Pvt) Ltd |  | 291908137.8 | 287333615.63 | Awarded | 62% | 2026-04-07 | 2026-08-14
RDA/DRP/SAB/RAT/EMB/02 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya - Nonagama Road (40+500-43+300) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | Anura Construction |  | 297894808.58 | 260511600.34 | Awarded | 21% | 2026-04-07 | 2026-07-24
RDA/DRP/SAB/RAT/EMB/03R | Rehabilitation / Improvement of Embilipitiya - Panamura - Buluthota Road (0+000-39+000) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | Samarasinghe Construction Pvt Ltd |  | 294962216.95 | 288699729.18 | Awarded | 3% |  | 2027-03-12
RDA/DRP/EAS/TRI/TRI/06 | Rehabilitation / Improvement of Trincomalee - Pulmoddai Road (47+500 - 49+500) | Eastern Province | Trincomalee | Eastern Province | Trincomalee |  | Emergency | DRRRP | Southern Group Civil Construction (Pvt) Ltd |  | 138997580.74 | 131314798.09 | Awarded | 20% | 2022-04-22 | 2026-11-02
RDA/DRP/EAS/TRI/TRI/07 | Rehabilitation / Improvement of Retaining Walls of Bridges at Upparu, Ralkuli, and Gangai | Eastern Province | Trincomalee | Eastern Province | Trincomalee |  | Emergency | DRRRP | Nathans Construction |  | 99606470.35 | 85089780.29 | Awarded | 82% | 2026-04-22 | 2026-11-02
RDA/DRP/WP/COL/COL/06 | Rehabilitation / Improvement of Allen Avenue (B011) (0+000- 2+000) | Western Province | Colombo | Western Province | Colombo | Colombo | Emergency | DRRRP | Jayasinghe Construction (Pvt) Ltd |  | 146669652.6 | 144822585.09 | Awarded | 5% | 2026-04-22 | 2026-08-09
RDA/DRP/WP/COL/COL/09 | Rehabilitation / Improvement of Koralawella Egodauyana Road (B235) section 2 (3+000 - 6+300) | Western Province | Colombo | Western Province | Colombo | Colombo | Emergency | DRRRP | Jayasinghe Construction (Pvt) Ltd |  | 160664947.64 | 155082468.4 | Awarded | 5% | 2026-04-22 | 2026-08-09
RDA/DRP/WP/COL/AVI/01 | Rehabilitation / Improvement and Drain and Shoulder Construction at Locations Within 38+200 - 60+950 on Colombo - Ratnapura - Wellawaya - Batticaloa Road (AA004) | Western Province | Colombo | Western Province | Colombo | Colombo | Emergency | DRRRP | Greenwawe Construction (Pvt) Ltd |  | 239974678.56 | 210347639.08 | Awarded | 26% | 2026-04-22 | 2026-07-12
RDA/DRP/UVA/BAD/BAN/18 | Rehabilitation / Improvement and Retainning Wall Construction Construction on Palugama Boralanda Haputhala Road (B353) (0+000 - 26+550), Haputale Dambatanna Road (B147) (1+700 - 1+735 RHS and 0+220 - 0+240 LHS) and Colombo Rathnapura Wellawaya Batticaloa Road (AA004) (167+750 - 213+750) | Uva Province | Badulla | Uva Province | Badulla | Badulla | Emergency | DRRRP | Kanwel Constructions & Civil Engineering (Pvt) Ltd |  | 153768755.88 | 147759561.52 | Awarded | 50% | 2026-04-22 | 2026-11-03
RDA/DRP/UVA/BAD/BAN/21 | Rehabilitation / Improvement of Wellawaya - Ella - Kumbalwela (14+000-30+0000 (AA-023), Ella - Passara (B113) (0+000 -5+000) and Beragala Hali-Ela (A016) (0+000 -25+000) | Uva Province | Badulla | Uva Province | Badulla | Badulla | Emergency | DRRRP | Suhada Enterprises |  | 321810896.4 | 321850877.98 | Awarded | 56% | 2026-04-22 | 2026-11-03
RDA/DRP/NCP/POL/POL/09 | Rehabilitation / Improvement and Reconstruction of Culvert No. 104/2, Construction of New Drainage At 83km, and Concrete Hard Shoulder at 83 Km on Maradankadawala - Habarana - Thirikkondiyadumadu Road (A-11) (82+110 - 82+860 (B/S) | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Polonnaruwa | Emergency | DRRRP | Abeywardhana Construction |  | 119605688.26 | 94457054.66 | Awarded | 56% | 2026-04-22 | 2026-05-08
RDA/DRP/SAB/RAT/EMB/08 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya - Naonagama Road (AA018) (43+700-47+000) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | Anura Construction |  | 286890596.52 | 259436963.35 | Awarded | 15% | 2026-04-22 | 2026-08-09
RDA/DRP/SAB/RAT/EMB/10 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya - Nonagama Road (AA018) (50+500 - 53+100) & Embilipitiya - Moraketiya - Kiriibbanara - Uda Mauara Road (B549) (0+000-5+500) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | Kanwel Constructions & Civil Engineering (Pvt) Ltd |  | 271949863.68 | 260776583.43 | Awarded | 23.7% | 2026-04-22 | 2026-08-11
RDA/DRP/EAS/BAT/BAT/01 | Rehabilitation / Improvement and Surfacing from 56+900 km to 58+300km and from 58+640 km to 59+440 km on Bitticaloa - Thurukkondamadu - Trincomalee Road | Eastern Province | Batticaloa | Eastern Province | Batticaloa |  | Emergency | DRRRP | S S K Construction |  | 144552679.21 | 113074919.76 | Awarded | 70% | 2026-05-11 | 2026-08-24
RDA/DRP/UVA/BAD/BAD/11 | Rehabilitation / Improvement of (1) PASSARA MADULSIMA METIGAHATENNA ROAD (18+030-26+430) | Uva Province | Badulla | Uva Province | Badulla | Badulla | Emergency | DRRRP | Jayanetti Construction |  | 159486625.18 | 149405885.14 | Awarded | 70% | 2026-05-11 | 2026-11-22
RDA/DRP/UVA/BAD/BAD/09 | Rehabilitation / Improvement of (1) ELLA PASSARA ROAD (23+800-27+080) | Uva Province | Badulla | Uva Province | Badulla | Badulla | Emergency | DRRRP | Nimsara Construction & Engineering (Pvt) Ltd |  | 257551081.92 | 254650056.89 | Awarded | 66% | 2026-05-11 | 2026-11-22
RDA/DRP/UVA/BAD/BAD/08 | Rehabilitation / Improvement of Dikwella Jagulla Thalpitigala Road (B100) (15+000 - 23+665) and Badulla Kandy (New Rajamawatha) Road (0+000 - 6+000) | Uva Province | Badulla | Uva Province | Badulla | Badulla | Emergency | DRRRP | SF Construction (Pvt) Ltd |  | 177976215.86 | 188749480 | Awarded | 48.5% | 2026-05-11 | 2026-12-20
RDA/DRP/UVA/BAD/BAD/13 | Rehabilitation / Improvement of Ella Passara Road (B113) (9+500 - 27+000) | Uva Province | Badulla | Uva Province | Badulla | Badulla | Emergency | DRRRP | SF Construction (Pvt) Ltd |  | 292073080.75 | 290901643.58 | Awarded | 66.5% | 2026-05-11 | 2026-11-22
RDA/DRP/SAB/RAT/EMB/05 | Rehabilitation / Improvement of Pelmadulla-Embilipitiya-Nonagama Road (30+000-32+850) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | Anura Construction |  | 272308017.25 | 248600718.52 | Awarded | 10% | 2026-05-11 | 2026-09-28
RDA/DRP/SAB/RAT/EMB/06 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya-Nonagama Road (33+500-36+500) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | Anura Construction |  | 258434888.71 | 237998681.32 | Awarded | 10% | 2026-05-11 | 2026-09-28
RDA/DRP/SAB/RAT/EMB/07 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya-Nonagama Road (37+000-40+000) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | Anura Construction |  | 299052002.52 | 276583785.23 | Awarded | 15% | 2026-05-11 | 2026-09-28
RDA/DRP/SAB/RAT/EMB/09 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya - Naonagama Road (47+100 - 50+400) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | Anura Construction |  | 290570516.98 | 269913795.48 | Awarded | 6% | 2026-05-11 | 2026-08-28
RDA/DRP/SAB/RAT/EMB/11 | Rehabilitation / Improvement of Weligepola-Hadagiriya - Kapugala (2+000-11+000) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | D K S Construction |  | 328908478.03 | 273586576.22 | Awarded | 42% | 2026-05-11 | 2026-09-30
RDA/DRP/WP/COL/COL/07 | Rehabilitation / Improvement of Colombo Hanwella Road (0+370 - 20+400) | Western Province | Colombo | Western Province | Colombo | Colombo | Emergency | DRRRP | INK Engineering |  | 140313104.48 | 146665907.47 | Awarded | 12% | 2026-05-11 | 2026-08-24
RDA/DRP/EAS/TRI/TRI/03 | Rehabilitation / Improvement of Town & Gravets Road (B140) (Fort Fredrick Road) (0+020 - 0+210) | Eastern Province | Trincomalee | Eastern Province | Trincomalee |  | Emergency | DRRRP | Motec Engineering & Construction |  | 42948657.31 | 37828051.78 | Awarded | 40% | 2026-05-19 | 2026-12-01
RDA/DRP/EAS/TRI/TRI/04 | Rehabilitation / Improvement of Town & Gravets Road (B140) (Inner Harbour Road) (0+200 - 0+560) | Eastern Province | Trincomalee | Eastern Province | Trincomalee |  | Emergency | DRRRP | Motec Engineering & Construction |  | 45878059.68 | 40407339.17 | Awarded | 65% | 2026-05-20 | 2026-08-04
RDA/DRP/NWP/KURU/MAHO/06R | Rehabilitation / Improvement of Kadigawa Bridge Approaches on Pahala Mawathagama - Kadigawa Road (0+000-0+175) | North Western Province | Kurunegala | North Western Province | Kurunegala |  | Emergency | DRRRP | RCDC Construction Company (Pvt) Ltd |  | 60148814.16 | 75025358.95 | Awarded | 6% |  | 2027-02-09
RDA/DRP/NWP/CHI/CHI/08 | Rehabilitation / Improvement of Baththuluoya - Udappuwa - Andimunai Road (B614) at 6+100 in Chilaw EE Division | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | Emergency | DRRRP | ST MARY Construction |  | 84197870.47 | 83944711.21 | Awarded | 56% | 2026-05-20 | 2026-08-15
RDA/DPR/NCP/ANU/ANU/01 | Rehabilitation / Improvement of Andarawewa - Balaluwewa Road (B501) (21+330 - 21+ 580 km) | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Emergency | DRRRP | Ranuja Construction |  | 85106787.1 | 99497834.48 | Awarded | 16% |  | 2026-10-22
RDA/DRP/NCP/POL/HAB/04 | Rehabilitation / Improvement of washed out section between 30/1 & 30/2 Bridges on Dambulla - Bakamoona - Kalagahawela Road (B-615) & at 27/5 Bridge (26+500-27+000) on Naula - Elahera - Pallegama -Hettipola Road (B-312) | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Polonnaruwa | Emergency | DRRRP | Lahiru Construction and Consultants (Pvt) Ltd |  | 51855122.27 | 49203550.22 | Awarded | 90% | 2026-05-20 | 2026-01-09
RDA/DRP/NCP/ANU/MAR/05R | Rehabilitation / Improvement and Rectification of Flood Damage on Thonigala - Kalawewa - Galewela Road (B423) (14+000-14+085 km) & Rectification of Flood Damage on Madatugama Pubbogama Andiyagala Road (B556) (11+930 -12+250 km) | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Emergency | DRRRP | NMST Contractors |  | 93874634.26 | 89094024.31 | Awarded | 12% | 2026-08-14 | 2026-11-27
RDA/DRP/NCP/ANU/MAR/06 | Rehabilitation / Improvement and Retaining wall Construction of bridge No. 3/1 & Gabion wall Construction on Madatugama Pubbogama Andiyagala Road (B-556) (1+900km) RHS | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Emergency | DRRRP | W.M.B. Contractors & Transporter |  | 91709767.42 | 112693093.11 | Awarded | 90% | 2026-06-16 | 2026-09-29
RDA/DRP/NCP/ANU/MED/07 | Rehabilitation / Improvement of Flood Damaged - Shoulder & Embankment Protection for Puttalam - Trincomalee Road (AA012) (131+100-131+400 LHS/RHS) (139+020-139+100 LHS) , Kandy -Jaffna Road (AA009) ( 148+775-149+050) and Kebithigollewa - Padaviya Road (B211) (17+400-17+550) | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Emergency | DRRRP | The Crown Construction |  | 45054035.76 | 38223285.38 | Awarded | 47% | 2026-05-19 | 2026-01-09
RDA/DRP/SAB/RAT/PEL/17 | Rehabilitation / Improvement of Balangoda - Bowatta -Kalthota Road (B038) (24+000-26+000) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | DKS Nishantha Construction |  | 101146022.11 | 92061086.61 | Awarded | 60% | 2026-05-20 | 2026-09-12
RDA/DRP/SAB/RAT/RAT/23 | Rehabilitation / Improvement Construction of Retaining structures on Thiruwanaketiya Agalawatta Road (B421) (27/7-27/8) (27/8-27-9) (29/2-29/3) and Kalawana Deepdeen Rakwana Road (B181) (7 km) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Emergency | DRRRP | AKC Construction |  | 59067809.52 | 52340066.9 | Awarded | 45% | 2026-05-19 | 2026-12-11
RDA/DRP/NWP/CHI/CHI/07 | Rehabilitation / Improvement of Nainamadama – Iranavila - Chilaw Road (B640) (6+200 - 32+200), Bangadeniya - Adigama – Anamaduwa Road (B045) (2+200 - 13+400) and Peliyagoda - Puttala Road (A003) (78+100 - 93+200) in Chilaw EE Division | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | Emergency | DRRRP | Jayawansa Construction (Pvt) Ltd |  | 248319499.59 | 214608362.18 | Awarded | 28% | 2026-08-07 | 2027-01-20
RDA/DRP/NWP/CHI/PUT/09R | Rehabilitation / Improvement of Peliyagoda Puttalam Road ((A003)) (95+000 - 97+000), Slope Protection by Concrete on Anamaduwa Uswewa Galgamauwa Road (B019) and Slope Protection by Concrete on Kiriyankalli Andigama Road (B227) | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | Emergency | DRRRP | RCDC Construction Company (Pvt) Ltd |  | 160051970.56 | 219322470.61 | Awarded | 5% |  | 2027-03-29
RDA/DRP/NWP/CHI/PUT/10 | Rehabilitation / Improvement of Palavi - Kalpitiya Road (B349) and Etalai - Talawila (Jubily Mawatha) Road (B516) (0+900-1+200) Puttalam EE Division | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | Emergency | DRRRP | ST MARY Construction |  | 147930527.03 | 136011633.11 | Awarded | 14% | 2026-05-19 | 2026-12-01
RDA/DRP/NWP/CHI/PUT/11 | Rehabilitation / Improvement of Town Roads (Saltern Road, Marikkar Street, Poles Road, Rest House Road, Good Shed Road) and Puttalam Trincomalee Road (AA012) in Puttalam EE Division | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | Emergency | DRRRP | Omega Construction Company (Pvt) Ltd |  | 290051718.48 | 303043337.3 | Awarded | 35% | 2026-05-19 | 2026-12-01
RDA/DRP/UVA/BAD/BAN/20 | Rehabilitation / Improvement of Bandarawela - Liyangahawela - Poonagala Road (B042) (10+000 -15+000) | Uva Province | Badulla | Uva Province | Badulla |  | Emergency | DRRRP | D K S Construction |  | 301203263.92 | 283401035.13 | Awarded | 44.5% | 2026-05-19 | 2026-10-17
RDA/DRP/NCP/POL/POL/10 | Rehabilitation / Improvement and Construction of New Drainage At 65-78km on Maradankadawala Habarana Thirikkondiyadumadu Road (A011)Road | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Polonnaruwa | Emergency | DRRRP | A.D.M Construction |  | 33973362.07 | 29767050.53 | Awarded | 55% | 2026-05-19 | 2026-01-09
RDA/DRP/UVA/BAD/BAN/24 | Rehabilitation / Improvement of Rendapola Ambewela Road | Uva Province | Badulla | Uva Province | Badulla |  | Emergency | DRRRP | Gamage Builders |  | 271955137.78 | 290409872.96 | Awarded | 36% | 2026-05-29 | 2026-12-30
RDA/DRP/EAS/AMP/AMP/01 | Rehabilitation / Improvement of Ampara Uhana Mahoya Road (from 2+400 to 2+800) & (from 3+700 to 3+900), Siyambalanduwa Damana Ampara Road (from 43+000 to 45+000), (from 33+000 to 34+000), (from 35+500 to 36+500) & (from 52+000 to 53+000) and Chadayanthalawa Uhana Road (from 11+100 to 11+500) | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Ampara |  | Emergency | DRRRP | Ediriweera Construction |  | 31793559.86 | 27878955.02 | Awarded | 90% | 2026-05-29 | 2026-09-10
RDA/DRP/EAS/AKK/AKK/04 | Rehabilitation / Improvement of Newguna – Manikkamadu – Irakkamam Road (0+000-1+250) & (1+300-2+600), Akkaraipattu Degavapi Vangamam Road (8+500-21+500) and Reconstruction of Culvert No. 368/2 on Colombo-Ratnapura-Wellawaya-Batticaloa Road | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Akkaraipattu |  | Emergency | DRRRP | Jeezan Trading and Transport |  | 196038211.02 | 171572395.05 | Awarded | 29% | 2026-05-29 | 2026-12-10
RDA/DRP/EAS/AKK/KAL/05 | Rehabilitation / Improvement and Reconstruction of Box Culvert at 9+780, Construction of Mass Concrete Retaining Wall (9+550 -9+600) & (9+600-11+000) on Sammanthurai - Malkampiddi - Deegawapi Road, Construction of Concrete Drain & rock blasting with utility shifting on Varaipathanchenai - Deegawapi Road (0+880 - 0+980 RHS), Construction of Concrete Drain on Deegawapi Temple Road (1+100 1+230 RHS), Construction of Mass Concete Retaining wall on Ampilanthurai - Veeramunai Road (25+600 - 26+000 LHS & RHS), Reconstruction of Wing Walls (at 375/2, 375/3, 375/4, 375/6) & Construction of Concrete Drain (384+000-389+000) on Colombo Ratnepura Wellawaya Batticoala Road, Construction of Concrete Drain (15+400 - 15+550 LHS) on Karaitivu - Ampara Road, Construction of Mass Concete Retaining Wall (5+700 -5+730) & on Construction of Hard Shoulder (Concrete) (13+200 - 13+600 LHS & RHS Selected Section) on Weeragoda - Central Camp Road, Construction of Hard Shoulder (Concete) (0+600 - 0+800 LHS & RHS) on Approach Road to Public Buildings | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Ampara |  | Emergency | DRRRP | Nazeeha Hardware and Construction |  | 236184712.99 | 196448155.48 | Awarded | 23% | 2026-05-29 | 2026-12-10
RDA/DRP/NWP/CHI/PUT/12 | Rehabilitation / Improvement of Puttalam Marichchikaddi Road in Puttalam 6+100-9+000 | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | Emergency | DRRRP | Omega Construction Company (Pvt) Ltd |  | 143347737.52 | 141404654.67 | Awarded | 26% | 2026-05-29 | 2026-12-17
RDA/DRP/WP/GAM/GAM/13 | Rehabilitation / Improvement and Culvert Constructions on Aluthgama- Vigoda Road at 1+650, on Katunayake - Veyangoda Road at 15+940, on Minuwangoda - Miriswatta - Katana Road at 3+700, on Dunagaha- Nilpanagoda Road at 4+900, on Kadawatha - Mawaramandiya Road at 2+800 and on Makola - Udupila Road at 3+200 | Western Province | Gampaha | Western Province | Gampaha | Gampaha | Emergency | DRRRP | Venus Enterprise |  | 39535250.16 | 34489854.85 | Awarded | 60% | 2026-05-29 | 2026-09-17
RDA/DRP/NCP/POL/POL/11 | Rehabilitation / Improvement and Construction of New Drainage on Polonnaruwa-Thambala -Sungawila -Somawathiya- Road | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Polonnaruwa | Emergency | DRRRP | A.D.M Construction |  | 57461708.21 | 44474738.82 | Awarded | 40% |  | 2026-09-11
RDA/DRP/UVA/BAD/BAN/23 | Rehabilitation / Improvement of Colombo Rathnapura Wellawaya Batticaloa Road (AA004) (201+000 - 204+000) | Uva Province | Badulla | Uva Province | Badulla |  | Emergency | DRRRP | D K S Construction |  | 325833013.16 | 322192938.69 | Awarded | 21% | 2026-06-16 | 2027-01-07
RDA/DRP/SP/GAL/HIN/03 | Rehabilitation / Improvement of Gabbion Walls along Udugama - Hiniduma (9+920- 9+938-LHS), (7+450-7+472-LHS), (5+150-5+17 LHS) | Southern Province | Galle | Southern Province | Galle | Galle | Emergency | DRRRP | Ceylon Construction Industry Development (Pvt) Ltd |  | 22102879.06 | 19453314.54 | Awarded | 98% | 2026-06-15 | 2026-10-05
RDA/DRP/UVA/BAD/BAN/31 | Rehabilitation / Improvement of Colombo Rathnapura Wellawaya Batticaloa Road (AA004) (212+000 - 213+500) | Uva Province | Badulla | Uva Province | Badulla |  | Emergency | DRRRP | Nimna Holdings (Pvt) Ltd |  | 232794296.45 | 239935072.9 | Awarded | 16% |  | 2027-03-05
RDA/DRP/NOR/MUL/KIL/07 | Rehabilitation / Improvement of Sholder of 1. Kandy - Jaffna Road (251+000 - 252+200), 2.0Kandy - Jaffna Road (260+000 - 270+000), 3.Nawatkuly - Kerativu - Mannar Road(54+000 - 57+000), 4.Paranthan - Karachchi - Mullaitivu (0+000 - 1+000, 6+000- 8+000, 9+000-11+000, 12+500-14+500, 16+000-17+500, 19+400-19+800) 5.Paranthan - Ponakary Road (9+000-16+000) 6.Soranpattu - Thalaiyadi road (2+500-5+000) | Northern Province | Kilinochchi | Northern Province | Mullaitivu |  | Emergency | DRRRP | SSK Construction |  | 55617040.01 | 62162612.7 | Awarded | 6% |  | 2026-12-07
RDA/DRP/NOR/MUL/MUL/09 | Rehabilitation /Improvement & Rectification of flood damages in Mullaitivu ( Mankulam-Mullaitivu Road (AA034), Mankulam-Vellankulam Road (B269), Mullaitivu-Kokkilai Road (B297), Kandy-Jaffna Road (AA009), Paranthan-Karachchi-Mullaitivu Road (AA035)) | Northern Province | Mullaitivu | Northern Province | Mullaitivu | Mullaitivu | Emergency | DRRRP | Jana Civil Work Contractors & Material Suppliers |  | 50474039.9 | 37338982.74 | Awarded | 10% |  | 2026-11-25
RDA/DRP/NOR/VOU/VOU/15 | Rehabilitation /Improvement of Kandy-Jaffna Road (AA009) & Madawachchiya-Mannar-Thalaimannar Road (AA014) | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Emergency | DRRRP | Jana Civil Work Contractors & Material Suppliers |  | 46307621.71 | 42832926.51 | Awarded | 18% |  | 2026-12-23