## Weekly Progress
Weekly Physical Progress
Date: 2026-11-04
# | Contract No | Contract Name | Contractor | Days Left | Planned % | Prev Week Progress 2026-10-30 | Progress Up To This Week 2026-11-06
1 | RDA/DRP/CEN/KDY/KAD/11 | Rehabilitation / Improvement of Nawalapitiya - Dolosbage Road ( B -318) ( 10+500 - 19+350 ), Dedugala Dolosbage Road ( B -588) ( 10+100 - 12+410 ) | Tiasa Construction (Pvt) Ltd | 42 Days in Delay | 100% | 26.5%
2 | RDA/DRP/CEN/KDY/KAN/14 | Rehabilitation /Improvement of Katugasthota Medawala road ( B 0206)( 0 + 000 - 9+370) | Alucon Industries (Pvt) Ltd | 117 days left | 29.1% | 9%
3 | RDA/DRP/CEN/KDY/KDY/15 | Rehabilitation / Improvement of Galagedara Rambukkana ( B 122) ( 0+000 - 18+000) | Jayawansa Construction (Pvt) Ltd | 125 days left | 23.2% | 6%
4 | RDA/DRP/CEN/KDY/KDY/19 | Rehabilitation / Improvement of Poojapitiya Alawathugoda road ( B 377) ( 0+000 - 8+000) | Jayawansa Construction (Pvt) Ltd | 134 days left | 18.2% | 5%
5 | RDA/DRP/CEN/KDY/KUN/20 | Rehabilitation / Improvement to Structures on Madolkelle - Kabaragala - Kandenuwara Road (B 257) (4+000 - 8+000) | Samindra Construction | 11 days left | 95.6% | 53%
6 | RDA/DRP/CEN/KDY/KUN/21 | Improvement of Pitiyegedara-Waththegama-Iriyagasthenna Road (0+000-5+400) | Jayasinghe Construction (Pvt) Ltd | 7 Days in Delay | 100% | 12%
7 | RDA/DRP/CEN/KDY/KUN/22 | Improvement to Damaged Road Section on Weeragantota - Randenigala Road. (From CH 19+000 To CH 27+200) | SD Civil Construction (Pvt) Ltd | 42 Days in Delay | 100% | 67%
8 | RDA/DRP/CEN/KDY/KUN/24R | Rehabilitation / Improvement of Flood damage on Katugastota - Madawala - Bamberella Road (B205) (0-000 - 7+200 and 13+000 - 13+045) | Nimsara Construction & Engineering (Pvt) Ltd | 130 days left | 18.2% | 5%
9 | RDA/DRP/CEN/KDY/KUN/25 | Construction of Gabion Retaining Wall on Katugastota Madawala Bamberella Road(LHS 9+600 - 9+655), (15+450 - 15+500), (10+235 - 10+300) and Wattegama Matale road (0+400 - 0+435) | S N O Builders (Pvt) Ltd | 3 Days in Delay | 100% | 59%
10 | RDA/DRP/CEN/KDY/KUN/26R | Improvement to Structures on Kandy - Jaffna Road 11+700 - 11+850 | SD Civil Construction (Pvt) Ltd | No schedule |  |  | 0%
11 | RDA/DRP/CEN/KDY/KUN/27 | Improvement to Structures on Kandy - Jaffna Road 6+500 - 9+910 | Gihan Enterprise | 8 Days in Delay | 100% | 66%
12 | RDA/DRP/CEN/KDY/KUN/29 | Improvement to Structures on Kandy - Mahiyanganaya - Padiyaththalawa Road (24+000-71+500) and Moragahamula victoria damtop | S N O Builders (Pvt) Ltd | 60 days left | 81.8% | 61%
13 | RDA/DRP/CEN/MTL/MTL/31R | Rehabilitation / Improvement of Matale - Udupihilla Road (AB026) (0+000 - 6+000) | Alucon Industries (Pvt) Ltd | 26 days left | 81.5%
14 | RDA/DRP/CEN/MTL/MTL/32 | Rehabilitation / Improvement of Kandy Jaffna (A-009)(17+710 - 46+450), Thalgodapitiya - Yatawatta - Dombawela (B-409) (15+030 - 26+800), Palapathwela - Galewela Road B-346)(0+000 - 8+100) Roads | Lahiru Construction and Consultants (Pvt) Ltd | 5 Days in Delay | 100% | 68%
15 | RDA/DRP/CEN/MTL/MTL/33 | Rehabilitation / Improvement of Wattegama Matale Road (5+280 - 13+160) and Ukuwela Railway station (0+000 - 0+190) | Jayasinghe Construction (Pvt) Ltd | 96 Days in Delay | 100% | 30%
16 | RDA/DRP/CEN/MTL/MTL/35 | Rehabilitation / Improvement of Rattota Gammaduwa Road (7+100 - 11+260) | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 5 Days in Delay | 100% | 63%
17 | RDA/DRP/CEN/MTL/MTL/38 | Rehabilitation / Improvement of Kalalpitiya Ukuwela Elkaduwa Road (B 180) (0+000 - 13+470) | Ediriweera Construction | 84 days left | 64.4% | 14%
18 | RDA/DRP/CEN/MTL/MTL/41 | Rehabilitation / Improvement of Matale Illukkumbura Laggala Road (B 274) (4+000 - 18+000) | Vikum Construction | 118 days left | 29.1% | 11%
19 | RDA/DRP/CEN/MTL/NAL/48R | Rehabilitation/Improvement of surfacing (ASphalt) hard shoulder,Shoulder, drain construction at Beligamuwa - Hebarawa- Wilgamuwa Road (B-577) (6+260 -11+950) | S A P Engineering (Pvt) Ltd | 120 days left | 16.9% | 5%
20 | RDA/DRP/CEN/MTL/NAL/49 | Rehabilitation /Improvement of Drains,Hard shoulder & Cash barrier at Naula- Elahera- Pallegama- Hettipola Road (B-312) (8+200-61+240) | Platinum Holdings Lanka (Private) Limited | 14 days left | 98.5% | 70%
21 | RDA/DRP/CEN/MTL/NAL/51 | Rehabilitation /Improvement of Retaining wall , drains and shoulder construction Bowathenna Access Road (B-064) (0+000-2+410) | Platinum Holdings Lanka (Private) Limited | 21 Days in Delay | 100% | 90%
22 | RDA/DRP/CEN/NUE/HAN/57 | Rehabilitation / Improvement of Keerthibandarapura Naranthalawa Road ( B -511 ) ( 0+000 - 4+100 ) | Samindra Construction | 7 Days in Delay | 100% | 30%
23 | RDA/DRP/CEN/NUE/NUE/60R | Rehabilitation / Improvement of Peradeniya Badulla Chenkaladi Road (A005) (40+750 - 42+850) | KSJ Construction (Pvt) Ltd | 153 days left | 7.4% | 10%
24 | RDA/DRP/CEN/NUE/NUE/66 | Rehabilitation / Improvement of Nuwara Eliya Town Road (0+000 - 1+695 ) (0+000 - 0+240 ) | KSJ Construction (Pvt) Ltd | 96 Days in Delay | 100% | 69%
25 | RDA/DRP/CEN/NUE/NUE/67 | Rehabilitation / Improvement of Harangala - Kalapitiya - Kumbaloluwa Road (10+480 km - 17+140 km) | KSJ Construction (Pvt) Ltd | 5 Days in Delay | 100% | 78%
26 | RDA/DRP/CEN/NUE/NUE/68 | Rehabilitation / Improvement of Thawalanthenna Thalawakelle Road (0+000 - 8+000) & (10+000 - 33+200) | Green Scene Construction (Pvt) Ltd | 5 Days in Delay | 100% | 40%
27 | RDA/DRP/CEN/NUE/NUE/69 | Rehabilitation / Improvement of Ulapane Pussallawa Road (6+440 - 15+950) | Southern Group Civil Construction (Pvt) Ltd | 5 Days in Delay | 100% | 56%
28 | RDA/DRP/CEN/NUE/NUE/86 | Rehabilitation / Improvement of Approch road to R'way station (Watagoda/ Thalawakele) Road | Pragathi Civil Construction | 55 Days in Delay | 100% | 20%
29 | RDA/DRP/CEN/NUE/NUR/97 | Rehabilitation/Improvement of Nawalapitiya Ginigathena Road (B-319)(7+200-12+200) | Jayawansa Construction (Pvt) Ltd | 50 Days in Delay | 100% | 62%
30 | RDA/DRP/CEN/NUE/NUR/98 | Rehabilitation/Improvement Harangala Kalapitiya Road (B-148) (0+000-10+700), Approach Road to Hrangala Dam Crest Road (B-491) (0+000-3+820), Nawalapitiya Harangala Road (B-306) (0+000-10+700) | Pragathi Civil Construction | 42 days left | 92.6% | 44%
31 | RDA/DRP/CEN/NUE/NUR/101 | Rehabilitation/Improvement of Hatton Maskeliya Delhouse Road (B-149) (0+000-31+970) | Sooriya Builders | 7 days left | 100% | 31%
32 | RDA/DC/DRP/CP/NE/NRW/02 | REHABILITATION/ IMPROVEMENT OF APPROCH ROAD TO LAXAPANA POWER HOUSE ROAD CH 6+100 - 12+000 | U.K.S Lanka Engineering (Pvt) Ltd | 267 days left | 4.2% | 9%
33 | RDA/DC/DRP/CP/NE/NE/04 | REHABILITAION/ IMPROVEMENTS OF LADY MACALUMS DRIVE ROAD (2+850 - 5+600KM) | KDA Weerasinghe & Co (Pvt) Ltd | 497 days left | 0% | 1%
34 | RDA/DC/DRP/SLOPE/CP/KDY/GAMPOLA-09 | MITIGATION OF FAILURES ALONG RDA ROADS DUE TO CYCLONE DITWAH GAMPOLA NAWALAPITIYA ROAD (AB013) CHAINAGE 10+350 KM | Sanguine Engineering (Pvt) Ltd | 238 days left | 3.6% | 9.3%
35 | RDA/DC/DRP/CP/NE/NRW/03 | REHABILITATION/ IMPROVEMENT TO ROZELLA RAILWAY STATION ROAD (0+000 - 3+300) KM AND WATAWALA RAILWAY STATION ROAD (0+000 - 1+850) KM | Nagma Engineering (Pvt) Ltd | 314 days left | 0.6% | 19%
36 | RDA/DC/DRP/CP/NE/NE/14 | Rehabilitation/ Improvement of Lady Macalums Drive (0+000 - 2+700) | K.D.A. Weerasinghe & Co. (Pvt) Ltd | No schedule |  |  | 0%
37 | RDA/DC/DRP/CP/NE/NE/05 | Rehabilitation/ Improvement of Blackpool Ambewela Pattipola Hortan Plains (5+200 - 12+000) | Asset Engineering (Pvt) Ltd | No schedule |  |  | 0%
38 | RDA/DC/DRP/CP/NE/NE/01 | Rehabilitation/ Improvement of Blackpool Ambewela Pattipola Hortan Plains (12+500 - 18+000) | Asset Engineering (Pvt) Ltd | No schedule |  |  | 0%
39 | RDA/DC/DRP/CP/NE/NE/09 | Rehabilitation/ Improvement to Blackpool Ambewela Pattipola Hortan Plains ( 19+000 - 23+000) | Asset Engineering (Pvt) Ltd | No schedule |  |  | 0%
40 | RDA/DC/DRP/CP/NE/NE/07 | Rehabilitation/ Improvement to Gomburuoya - Balapokuna Road 0+000-8+500Without 5+250-5+450 & 6+900-7+150 | Nagma Engineering (Pvt) Ltd | No schedule |  |  | 0%
41 | RDA/DC/DRP/SLOPE/PD(CP)/KDY/GPL/01 | Construction of Slope failure mitigation measures along Peradeniya-Badulla-Chenkaladi Road (A005) at Ch 0+030 km | Weebadda Construction | No schedule |  |  | 0%
42 | RDA/DC/DRP/SLOPE/PD(CP)/KDY/GPL/11 | Construction of Slope failure mitigation measures along Galaha-Pupuressa-Delpitiya Road (B125) at Ch 5+700 km | J. Kodithuwakkuarachchi & Sons (Pvt) Ltd | No schedule |  |  | 0%
43 | RDA/DC/DRP/SLOPE/PD(CP)/KDY/GPL/14 | Construction of Slope failure mitigation measures along Atabage-Ulapane Road (B 490) at Ch 4+000 km | Bandaranayake Builders and Construction | No schedule |  |  | 0%
44 | RDA/DC/DRP/SLOPE/PD(CP)/KDY/GPL/29 | Construction of Slope failure mitigation measures along Peradeniya-Badulla-Chenkaladi Road (A005) at Ch 21+550 km | Weebadda Construction | No schedule |  |  | 0%
45 | RDA/DC/DRP/SLOPE/PD(CP)/KDY/KUN/26A | Construction of Slope failure mitigation measures along Kandy-Mahiyangana-Padiyathalawa Road (A026) at Culvert No 58/6 -58/5. | J. Kodithuwakkuarachchi & Sons (Pvt) Ltd | No schedule |  |  | 0%
46 | RDA/DC/DRP/SLOPE/PD(CP)/KDY/KUN/18,19&20 | Construction of Slope failure mitigation measures along Kandy – Mahiyangana – Padiyatalawa Road (A026) at Culvert No 47/5 Culvert No47/10, Culvert No 50/6-51+200 km and Culvert No 52/3-Culvert No 52/5 | J. Kodithuwakkuarachchi & Sons (Pvt) Ltd | No schedule |  |  | 0%
47 | RDA/DC/DRP/SLOPE/PD(CP)/KDY/KUN/1A | Construction of Slope failure mitigation measures along KandyMahiyanganaPadiyathalawa Road (A026) at Culvert No 25/3. | J. Kodithuwakkuarachchi & Sons (Pvt) Ltd | No schedule |  |  | 0%
48 | RDA/DC/DRP/SLOPE/PD(CP)/KDY/KAD/35 | Construction of Slope failure mitigation measures along Aladeniya-Eriyagama Road (B005) at Ch 3+700 RHS. | Weebadda Construction | No schedule |  |  | 0%
49 | RDA/DRP/SAB/KEG/KEG/14 | Rehabilitation / Improvement of Damaged Locations in Colombo Kandy Road from 56+050-98+950 | Tudawe Brothers (Pvt) Ltd | 91 Days in Delay | 100% | 65%
50 | RDA/DRP/UVA/BAD/BAD/02 | Rehabilitation / Improvement of Demodara SpringValley Badulla Road (16+145-20+800) - selected Sections) (B-097) | Priyankara Industries & Contractors | 43 Days in Delay | 100% | 66%
51 | RDA/DRP/UVA/BAD/MAH/27 | Rehabilitation / Improvement of Dambagahapitiya Pinnagolla arawa Meegahakeula Road (8+200-8+250) (B-086)/ Bibile-Uraniya-Mahiyanganaya Road | EMA Construction (Pvt) Ltd | 44 Days in Delay | 100% | 79.5%
52 | RDA/DRP/SAB/RAT/PEL/20 | Rehabilitation / Improvement of Pelmadulla - Pelmadulla - Embilipitiya - Nonagama (2+050 - 4+320) & Retaining wall Construction on Pelmadulla - Embilipitiya - Nonagama Road 5/4 - 5/5 (LHS) | K.E.P. Construction | 121 Days in Delay | 100% | 31%
53 | RDA/DRP/UVA/BAD/BAN/19 | Rehabilitation / Improvement of Bandarawela Liyangahawela Poonagala Road (5+000 -10+000) (B-042) | Senura Civil Engineering (Pvt) Ltd | 42 Days in Delay | 100% | 40%
54 | RDA/DRP/UVA/BAD/BAN/15R | Rehabilitation / Improvement of Bandarawela Welimada Road (6+000-20+200) (B-044) | Subasingha Contractors (Pvt) Ltd | 121 days left | 29.1% | 12%
55 | RDA/DRP/SAB/KEG/KEG/16 | Rehabilitation / Improvement of Kegalle Siyambalapitiya Dewalegama Road, Polgahawela Kegalle Road and Mawanella Aranayaka Horewela Road | Creates Consultant and Construction | 80 Days in Delay | 100% | 60%
56 | RDA/DRP/UVA/MON/MON/28 | Rehabilitation / Improvement of Colombo Galle Hambanthota Wellawaya Road (305+650-305+850) (AA-002), Wellawaya Ella Kumbalwela Road (0+800-1+825) (AA-023) and Kumbukkana Okkampitiya Maligawila Road (2+250-2+450) (B-513) | EMA Construction (Pvt) Ltd | 33 Days in Delay | 100% | 59%
57 | RDA/DRP/SAB/KEG/RUW/29 | Rehabilitation / Improvement of Dehiowita - Daraniyagala - Nooriya Road (From 13+845 to 23+850) | SSP Engineers (Pvt) Ltd | 132 Days in Delay | 100% | 70%
58 | RDA/DRP/UVA/BAD/BAN/17R | Rehabilitation / Improvement of Welimada Boralanda Ohiya Horton Plains (0+000 -32+470)(B-508) | Shabi Lanka Construction | 64 days left | 58.2% | 7%
59 | RDA/DRP/UVA/BAD/BAD/01 | Rehabilitation / Improvement of Badulla Karametiya Andaulpotha Road (0+000-20+000 - Selected Sections) (B-036) | JD Builders | 38 Days in Delay | 100% | 71%
60 | RDA/DRP/UVA/BAD/BAD/04 | Rehabilitation / Improvement of Dikwella Jagulla Thalpitigala Road (0+000-6+600 - Selected Sections) (B-100) | PH Engineering & Construction (Pvt) Ltd | 38 Days in Delay | 100% | 67.5%
61 | RDA/DRP/UVA/BAD/BAD/05 | Rehabilitation / Improvement of Dikwella Jagulla Thalpitigala Road 6+600-15+000 - Selected Sections) (B-100) | PH Engineering & Construction (Pvt) Ltd | 40 Days in Delay | 100% | 57.5%
62 | RDA/DRP/UVA/BAD/BAN/14 | Rehabilitation / Improvement of Bandarawela Welimada Road (0+000-6+000) (B-044) | Senarathna Contractors | 41 Days in Delay | 100% | 73.5%
63 | RDA/DRP/SAB/RAT/EMB/04 | Rehabilitation / Improvement of Galle - Deniyaya-Madampe Road (88+000-95+000) | SN Projects Lanka (Pvt) Ltd | 120 Days in Delay | 100% | 22%
64 | RDA/DRP/SAB/RAT/EMB/12 | Rehabilitation / Improvement of Galle -Deniyaya-Madampe Road (95+000-100+000) | SN Projects Lanka (Pvt) Ltd | 120 Days in Delay | 100% | 26%
65 | RDA/DRP/SAB/KEG/KEG/13 | Rehabilitation / Improvement of damage locations at Ambepussa Kurunegala Trincomalee Road, Warakapola Kandalama Road, Warakapola Buypass Road, Morontota Arandara Road, Galigamuwa Ruwanwella Road, Gevilipitiya Hettimulla Road, Kegalle Bulattkohupitiya, Karawanella Road, Mawanella Hemmathagama Gampola Road and Rambukkana Mawanella Road in Kegalle Executive Engineers Division. | Senarath Engineering (Pvt) Ltd | 67 Days in Delay | 100% | 75%
66 | RDA/DRP/SAB/RAT/PEL/19 | Rehabilitation / Improvement and Retaining wall Construction of (Galle - Deniyaya - Madampe Road 144/1 - 144/2 RHS, 135-136/1 LHS & RHS, 137/5-137/4 LHS) & Pelmadulla - Embilipitiya - Nonagama Road 10/4 LHS, 18/1-18/2 LHS) | Solinro Builders | Completed | 100% |  | 100%
67 | RDA/DRP/SAB/RAT/RAT/22 | Rehabilitation / Improvement and Asphalt Overlaying on Ayagama Kukulegama Road | Keangnam Engineering & Construction (Pvt) Ltd | 131 Days in Delay | 100% | 42.9%
68 | RDA/DRP/SAB/RAT/RAT/26 | Rehabilitation / Improvement of Malwala - Carney Road (Ch. 11+000 - Ch. 14+972) | SSP Engineers (Pvt) Ltd | 120 Days in Delay | 100% | 85.8%
69 | RDA/DRP/SAB/RAT/RAT/25 | Rehabilitation / Improvement and Asphalt Overlaying on Malwana Charney (6+020 - 11+000) & Construction of Gabion Wall at 2+510, 2+847 | Wijeratne Construction | 120 Days in Delay | 100% | 62%
70 | RDA/DRP/UVA/BAD/BAD/03 | Rehabilitation / Improvement of Peradeniya Badulla Chenkaladi Road (90+000-123+000) (AA-005) | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 42 Days in Delay | 100% | 61%
71 | RDA/DRP/UVA/BAD/BAD/06 | Rehabilitation / Improvement of Baragala Haliela Road (25+525-38+000 - Selected Sections) (AA-016) and Bandarawela Uva Highland Etampitiya Road (5+000-16+100) (B-043) | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 41 Days in Delay | 100% | 57%
72 | RDA/DRP/SAB/RAT/PEL/21 | Rehabilitation / Improvement of Pabahinna - Kubalgama - Rajawaka - Kapugala Road (2+000-7+700) & Retaining wall Construction of Colombo - Rathnapura - Wellawaya- Batticaloa Road (156/2 (RHS), 155/6, 133/7 - 133/8 (RHS), 122/5- 122/4 (RHS) | Samdam Engineering & Constructions (Pvt) Ltd | 121 Days in Delay | 100% | 32%
73 | RDA/DRP/UVA/BAD/BAN/16 | Rehabilitation / Improvement of Rendapola Ambewela Road (0+000-1+435) (B-507) and Peradeniya Badulla Chenkaladi Road (76+000-90+000) (AA-005) | Subasingha Contractors (Pvt) Ltd | 35 Days in Delay | 100% | 66%
74 | RDA/DRP/UVA/BAD/BAN/22 | REHABILITATION/IMPROVEMENT OF WELIMADA KIRKLEES ROAD ( From 0+000 to 17+250) | Suhada Enterprises | 41 Days in Delay | 100% | 77%
75 | RDA/DRP/UVA/MON/BIB/25 | Rehabilitation / Improvement of Colombo Rathnapura Wellawaya Batticaloa Road (259+080-292+800) (AA-004), Siyabalanduwa damana Ampara Road (0+000-24+000) (AA-025) and Bibila Medagama Nakkala Road (0+000-33+240) (B-056) and Passara Monaragala Road (7+120-26+240) (AA-022) | Ediriweera Construction | 30 Days in Delay | 100% | 51%
76 | RDA/DRP/SAB/RAT/RAT/24 | Rehabilitation / Improvement and Asphalt Overlaying on Kalawana - Deepdeen Rakwana (4+255-9+809) | SSP Engineers (Pvt) Ltd | 133 Days in Delay | 100% | 85%
77 | RDA/DRP/SAB/KEG/RUW/28 | Rehabilitation / Improvement of Bulathkohupitiya Dedugala Road, Warakapola Ruwanwella Road, Alawathura- Yatapana - Kotiyakumbura Road and Avissawella - Hatton - Nuwaraeliya Road | Southern Group Civil Construction (Pvt) Ltd | 54 Days in Delay | 100% | 50%
78 | RDA/DRP/SAB/KEG/RUW/33R | Yatiyanthota - Poonagala - Meenagala Road (from 3+760 to 6+760) | KENT Engineering (Pvt) Ltd | 100 days left | 35%
79 | RDA/DRP/SAB/KEG/RUW/34R | Yatiyanthota - Poonagala - Meenagala Road (from 6+760 to 9+000) | KENT Engineering (Pvt) Ltd | 128 days left | 23.2%
80 | RDA/DRP/SAB/KEG/RUW/35 | Yatiyanthota - Poonagala - Meenagala Road (from 13+400 to 18+200) | Southern Group Civil Construction (Pvt) Ltd | 54 Days in Delay | 100% | 25%
81 | RDA/DPR/NCP/ANU/ANU/02 | Rehabilitation / Improvement and Construction of Drainge Canal for Kumbichchan Kulama Spillway on Maitreepala Senanayake Mawatha (1+970 - 2+090 km) | SMA Construction (Pvt) Ltd | 16 Days in Delay | 100% | 50%
82 | RDA/DPR/NCP/ANU/ANU/03 | Rehabilitation / Improvement Construction of Drainge Canal for Thambuttegama Tank Spill on Padeniya - Anuradhapura Road (59+420 - 59+610) & Construction of Drainge Canal for Protection Road on Andarawewa - Balaluwewa Road(16+580 - 16+680) | SMA Construction (Pvt) Ltd | 16 Days in Delay | 100% | 38%
83 | RDA/DRP/WP/GAM/NEG/19 | Rehabilitation / Improvement of Negombo-Mirigama Road (5+000-6+000) and Negombo-Giriulla Road (29+000-34+000) | Tudawe Brothers (Pvt) Ltd | 2 Days in Delay | 100% | 20%
84 | RDA/DRP/WP/GAM/NIT/21 | Rehabilitation / Improvement of Hanwella Urapola Road (3+000 - 10+100), Structure Construction on Delgoda Dompe Giridara Road (0+000- 10+070) and Urapola Wathuragama Road (0+000- 7+080 ) and Drain Construction on Negombo-Mirigama road (21+000 - 30+580) | Tudawe Brothers (Pvt) Ltd | 2 Days in Delay | 100% | 28%
85 | RDA/DRP/WP/GAM/GAM/10 | Rehabilitation / Improvement of Old Minuwangoda Gampaha - Miriswatta Road (9+000 - 10+000) and Minuwangoda - Gampaha Road (0+000 - 5+300) | Senarath Engineering (Pvt) Ltd | 103 Days in Delay | 100% | 2%
86 | RDA/DRP/WP/GAM/GAM/12 | Rehabilitation / Improvement of Acces Road to Peliyagoda interchange (0+000 - 2+100), Colombo - Kandy Road (6+500-19+000) and Kelaniya - Waragoda Road (0+000-3+220) | Senarath Engineering (Pvt) Ltd | 103 Days in Delay | 100% | 2%
87 | RDA/DRP/WP/GAM/NIT/20 | Rehabilitation / Improvement of Bothale Mirigama Road (3+750-4+800), Warakapola Kandalama Road (7+000-8+000), (8+500-9+000) & (9+500-10+900), Negombo Mirigama Road and Construction of Gabion Wall on Colombo - Kandy Road at 54+950,Warakapola Kandalama Road at Culvert No. 10/4 LHS and Widening of Culvert Nos. 4/1 LHS 4/3 Bothsides and Reconstruction of Culvert No. 4/2 on Veyangoda Banduragoda Road | Jeyanthan Construction | 62 Days in Delay | 100% | 46%
88 | RDA/DRP/WP/GAM/NIT/22 | Rehabilitation / Improvement of Delgoda Dompe Giridara Road (Selected Sections between 2+000-12+100) | Senarath Engineering (Pvt) Ltd | 12 Days in Delay | 100% | 1%
89 | RDA/DRP/WP/GAM/NIT/23 | Rehabilitation / Improvement of Kalagedihena Veyangoda Road (0+000 -3+000), Pasyala Attanagalla Road (0+000 - 6+400) and Colombo - Kandy Road (38+620 -38+720) | Senarath Engineering (Pvt) Ltd | 12 Days in Delay | 100% | 1%
90 | RDA/DRP/SAB/KEG/RUW/30 | Rehabilitation of Dehiovita - Daraniyagala - Nooriya Road (from 23+850 to 27+960) due to catastrophic disaster cyclone Ditwa | Accon Engineering (Pvt) Ltd | 75 Days in Delay | 100% | 68%
91 | RDA/DRP/SAB/KEG/RUW/31 | Rehabilitation of Kegalle - Bulathkohupitiya - Karawanella Road due to catastrophic disaster cyclone Ditwa | Tudawe Brothers (Pvt) Ltd | 65 Days in Delay | 100% | 18%
92 | RDA/DRP/WP/COL/AVI/02 | Rehabilitation / Improvement of Damage Sections on Colombo - Hanwella Low Level Road (AB010) (23+000 - 26+715) & Hanwella Cross Road (B145) (0+000 - 0+800) | Keangnam Engineering & Construction (Pvt) Ltd | 106 Days in Delay | 100% | 29%
93 | RDA/DRP/WP/COL/AVI/03 | Rehabilitation / Improvement and Asphalt Overlaying on Colombo - Horana Road (B084) (10+500 - 13+500) | Keangnam Engineering & Construction (Pvt) Ltd | 134 Days in Delay | 100% | 3%
94 | RDA/DRP/WP/COL/AVI/04 | Rehabilitation / Improvement and Asphalt Overlaying on Mampe Kottawa Road (B267) (0+750 - 3+400) (5+100 - 6+120)) | Keangnam Engineering & Construction (Pvt) Ltd | 134 Days in Delay | 100% | 65%
95 | RDA/DRP/WP/COL/AVI/05 | Rehabilitation / Improvement and Asphalt Overlaying on Panagoda Henpita Road (B354) (0+000 - 6+440) | Keangnam Engineering & Construction (Pvt) Ltd | 134 Days in Delay | 100% | 3%
96 | RDA/DRP/NWP/KURU/KULI/01R | Rehabilitation / Improvement of Selected Sections on Pannala Kuliyapitiya Road (B356) (0+000-6+000), Dandagamuwa Udawela Road (B088) (4+000 - 6+000), Marawila Udubaddawa Road (B272) (11+000 - 12+000), Kurunegala Narammala Madampe Road (B247) (52+000 - 54+000), Narammala Dankotuwa Road (B308) (16+000-37+000) and Alawwa Maharagama Road (B009) (1+000 - 14+200) in Kuliyapitiya EE Division | Can Construction and Consultancy (Pvt) Ltd | 51 days left | 70.2% | 12%
97 | RDA/DRP/NWP/KURU/KURU/02R | Rehabilitation / Improvement and Structure Improvement of Mallawapitiya Rambodagalla Keppitigala Road (30+943 - 33+858), Katugasthota Kurunegala Puttalam Road (AA010) (30+000 - 34+600) and Mawathagama Muwankanda Road (B281) (0+000 - 7+000) | Can Construction and Consultancy (Pvt) Ltd | 127 days left | 73.3%
98 | RDA/DRP/NWP/KURU/KURU/03R | Rehabilitation / Improvement of Thalgodapitiya Yatawaththa Road (B409) (9+100 - 14+650) | Jayawansa Construction (Pvt) Ltd | 145 days left | 45.2%
99 | RDA/DRP/NWP/KURU/KURU/04 | Rehabilitation / Improvement of Muththettugala Hiripitiya Road (B300) (10+880 - 11+080) & Vilakatupotha Ganewatta Kumbukgete road (B478) (9+100 - 9+400) | TMC Construction (Pvt) Ltd | 105 Days in Delay | 100% | 62%
100 | RDA/DRP/NWP/KURU/MAHO/05 | Rehabilitation / Improvement of Galgamuwa - Nikawewa Road (B126) (6+000-20+000), Danikithawa - Ambanpola Road (B089) (20+925 - 21+000), Nikaweratiya - Moragollagama - Siyambalangamuwa Road (B326) (40+760 - 48+240), Malsiripura - Rambe Road (B610) (7+500 - 9+650), Ibbagamuwa - Kumbukgate - Madagalla Road (B159) (16+450 - 28+680), Hiripitiya - Galtenwewa Road (B609) (9+580-9+680), Padeniya - Anuradapura Road (AA028) (8+480-8+800) and Katugasthota - Kurunegala - Puththalama Road (AA010) (73+745-73 -870) in Maho EE Division | St. Anthony's Construction | 64 Days in Delay | 100% | 70%
101 | RDA/DRP/SAB/RAT/EMB/01 | Rehabilitation / Improvement of Kalawana - Deepdeen - Rakwana Road (15+000-46+000) | SSP Engineers (Pvt) Ltd | 82 Days in Delay | 100% | 62%
102 | RDA/DRP/SAB/RAT/EMB/02 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya - Nonagama Road (40+500-43+300) | Anura Construction | 103 Days in Delay | 100% | 21%
103 | RDA/DRP/SAB/RAT/EMB/03R | Rehabilitation / Improvement of Embilipitiya - Panamura - Buluthota Road (0+000-39+000) | Samarasinghe Construction Pvt Ltd | 128 days left | 23.2% | 3%
104 | RDA/DRP/EAS/TRI/TRI/06 | Rehabilitation / Improvement of Trincomalee - Pulmoddai Road (47+500 - 49+500) | Southern Group Civil Construction (Pvt) Ltd | 2 Days in Delay | 100% | 20%
105 | RDA/DRP/EAS/TRI/TRI/07 | Rehabilitation / Improvement of Retaining Walls of Bridges at Upparu, Ralkuli, and Gangai | Nathans Construction | 2 Days in Delay | 100% | 82%
106 | RDA/DRP/WP/COL/COL/06 | Rehabilitation / Improvement of Allen Avenue (B011) (0+000- 2+000) | Jayasinghe Construction (Pvt) Ltd | 87 Days in Delay | 100% | 5%
107 | RDA/DRP/WP/COL/COL/09 | Rehabilitation / Improvement of Koralawella Egodauyana Road (B235) section 2 (3+000 - 6+300) | Jayasinghe Construction (Pvt) Ltd | 87 Days in Delay | 100% | 5%
108 | RDA/DRP/WP/COL/AVI/01 | Rehabilitation / Improvement and Drain and Shoulder Construction at Locations Within 38+200 - 60+950 on Colombo - Ratnapura - Wellawaya - Batticaloa Road (AA004) | Greenwawe Construction (Pvt) Ltd | 115 Days in Delay | 100% | 26%
109 | RDA/DRP/UVA/BAD/BAN/18 | Rehabilitation / Improvement and Retainning Wall Construction Construction on Palugama Boralanda Haputhala Road (B353) (0+000 - 26+550), Haputale Dambatanna Road (B147) (1+700 - 1+735 RHS and 0+220 - 0+240 LHS) and Colombo Rathnapura Wellawaya Batticaloa Road (AA004) (167+750 - 213+750) | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 1 Day in Delay | 100% | 50%
110 | RDA/DRP/UVA/BAD/BAN/21 | Rehabilitation / Improvement of Wellawaya - Ella - Kumbalwela (14+000-30+0000 (AA-023), Ella - Passara (B113) (0+000 -5+000) and Beragala Hali-Ela (A016) (0+000 -25+000) | Suhada Enterprises | 1 Day in Delay | 100% | 56%
111 | RDA/DRP/NCP/POL/POL/09 | Rehabilitation / Improvement and Reconstruction of Culvert No. 104/2, Construction of New Drainage At 83km, and Concrete Hard Shoulder at 83 Km on Maradankadawala - Habarana - Thirikkondiyadumadu Road (A-11) (82+110 - 82+860 (B/S) | Abeywardhana Construction | 180 Days in Delay | 100% | 56%
112 | RDA/DRP/SAB/RAT/EMB/08 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya - Naonagama Road (AA018) (43+700-47+000) | Anura Construction | 87 Days in Delay | 100% | 15%
113 | RDA/DRP/SAB/RAT/EMB/10 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya - Nonagama Road (AA018) (50+500 - 53+100) & Embilipitiya - Moraketiya - Kiriibbanara - Uda Mauara Road (B549) (0+000-5+500) | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 85 Days in Delay | 100% | 23.7%
114 | RDA/DRP/EAS/BAT/BAT/01 | Rehabilitation / Improvement and Surfacing from 56+900 km to 58+300km and from 58+640 km to 59+440 km on Bitticaloa - Thurukkondamadu - Trincomalee Road | S S K Construction | 72 Days in Delay | 100% | 70%
115 | RDA/DRP/UVA/BAD/BAD/11 | Rehabilitation / Improvement of (1) PASSARA MADULSIMA METIGAHATENNA ROAD (18+030-26+430) | Jayanetti Construction | 18 days left | 98.1% | 70%
116 | RDA/DRP/UVA/BAD/BAD/09 | Rehabilitation / Improvement of (1) ELLA PASSARA ROAD (23+800-27+080) | Nimsara Construction & Engineering (Pvt) Ltd | 18 days left | 98.1% | 66%
117 | RDA/DRP/UVA/BAD/BAD/08 | Rehabilitation / Improvement of Dikwella Jagulla Thalpitigala Road (B100) (15+000 - 23+665) and Badulla Kandy (New Rajamawatha) Road (0+000 - 6+000) | SF Construction (Pvt) Ltd | 46 days left | 93.8% | 48.5%
118 | RDA/DRP/UVA/BAD/BAD/13 | Rehabilitation / Improvement of Ella Passara Road (B113) (9+500 - 27+000) | SF Construction (Pvt) Ltd | 18 days left | 98.1% | 66.5%
119 | RDA/DRP/SAB/RAT/EMB/05 | Rehabilitation / Improvement of Pelmadulla-Embilipitiya-Nonagama Road (30+000-32+850) | Anura Construction | 37 Days in Delay | 100% | 10%
120 | RDA/DRP/SAB/RAT/EMB/06 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya-Nonagama Road (33+500-36+500) | Anura Construction | 37 Days in Delay | 100% | 10%
121 | RDA/DRP/SAB/RAT/EMB/07 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya-Nonagama Road (37+000-40+000) | Anura Construction | 37 Days in Delay | 100% | 15%
122 | RDA/DRP/SAB/RAT/EMB/09 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya - Naonagama Road (47+100 - 50+400) | Anura Construction | 68 Days in Delay | 100% | 6%
123 | RDA/DRP/SAB/RAT/EMB/11 | Rehabilitation / Improvement of Weligepola-Hadagiriya - Kapugala (2+000-11+000) | D K S Construction | 35 Days in Delay | 100% | 42%
124 | RDA/DRP/WP/COL/COL/07 | Rehabilitation / Improvement of Colombo Hanwella Road (0+370 - 20+400) | INK Engineering | 72 Days in Delay | 100% | 12%
125 | RDA/DRP/EAS/TRI/TRI/03 | Rehabilitation / Improvement of Town & Gravets Road (B140) (Fort Fredrick Road) (0+020 - 0+210) | Motec Engineering & Construction | 27 days left | 96.7% | 40%
126 | RDA/DRP/EAS/TRI/TRI/04 | Rehabilitation / Improvement of Town & Gravets Road (B140) (Inner Harbour Road) (0+200 - 0+560) | Motec Engineering & Construction | 92 Days in Delay | 100% | 65%
127 | RDA/DRP/NWP/KURU/MAHO/06R | Rehabilitation / Improvement of Kadigawa Bridge Approaches on Pahala Mawathagama - Kadigawa Road (0+000-0+175) | RCDC Construction Company (Pvt) Ltd | 97 days left | 35.6% | 6%
128 | RDA/DRP/NWP/CHI/CHI/08 | Rehabilitation / Improvement of Baththuluoya - Udappuwa - Andimunai Road (B614) at 6+100 in Chilaw EE Division | ST MARY Construction | 81 Days in Delay | 100% | 56%
129 | RDA/DPR/NCP/ANU/ANU/01 | Rehabilitation / Improvement of Andarawewa - Balaluwewa Road (B501) (21+330 - 21+ 580 km) | Ranuja Construction | 13 Days in Delay | 100% | 16%
130 | RDA/DRP/NCP/POL/HAB/04 | Rehabilitation / Improvement of washed out section between 30/1 & 30/2 Bridges on Dambulla - Bakamoona - Kalagahawela Road (B-615) & at 27/5 Bridge (26+500-27+000) on Naula - Elahera - Pallegama -Hettipola Road (B-312) | Lahiru Construction and Consultants (Pvt) Ltd | 299 Days in Delay | 100% | 90%
131 | RDA/DRP/NCP/ANU/MAR/05R | Rehabilitation / Improvement and Rectification of Flood Damage on Thonigala - Kalawewa - Galewela Road (B423) (14+000-14+085 km) & Rectification of Flood Damage on Madatugama Pubbogama Andiyagala Road (B556) (11+930 -12+250 km) | NMST Contractors | 23 days left | 88.7% | 12%
132 | RDA/DRP/NCP/ANU/MAR/06 | Rehabilitation / Improvement and Retaining wall Construction of bridge No. 3/1 & Gabion wall Construction on Madatugama Pubbogama Andiyagala Road (B-556) (1+900km) RHS | W.M.B. Contractors & Transporter | 36 Days in Delay | 100% | 90%
133 | RDA/DRP/NCP/ANU/MED/07 | Rehabilitation / Improvement of Flood Damaged - Shoulder & Embankment Protection for Puttalam - Trincomalee Road (AA012) (131+100-131+400 LHS/RHS) (139+020-139+100 LHS) , Kandy -Jaffna Road (AA009) ( 148+775-149+050) and Kebithigollewa - Padaviya Road (B211) (17+400-17+550) | The Crown Construction | 299 Days in Delay | 100% | 47%
134 | RDA/DRP/SAB/RAT/PEL/17 | Rehabilitation / Improvement of Balangoda - Bowatta -Kalthota Road (B038) (24+000-26+000) | DKS Nishantha Construction | 53 Days in Delay | 100% | 60%
135 | RDA/DRP/SAB/RAT/RAT/23 | Rehabilitation / Improvement Construction of Retaining structures on Thiruwanaketiya Agalawatta Road (B421) (27/7-27/8) (27/8-27-9) (29/2-29/3) and Kalawana Deepdeen Rakwana Road (B181) (7 km) | AKC Construction | 37 days left | 94.8% | 45%
136 | RDA/DRP/NWP/CHI/CHI/07 | Rehabilitation / Improvement of Nainamadama – Iranavila - Chilaw Road (B640) (6+200 - 32+200), Bangadeniya - Adigama – Anamaduwa Road (B045) (2+200 - 13+400) and Peliyagoda - Puttala Road (A003) (78+100 - 93+200) in Chilaw EE Division | Jayawansa Construction (Pvt) Ltd | 77 days left | 70.9% | 28%
137 | RDA/DRP/NWP/CHI/PUT/09R | Rehabilitation / Improvement of Peliyagoda Puttalam Road ((A003)) (95+000 - 97+000), Slope Protection by Concrete on Anamaduwa Uswewa Galgamauwa Road (B019) and Slope Protection by Concrete on Kiriyankalli Andigama Road (B227) | RCDC Construction Company (Pvt) Ltd | 145 days left | 10.3% | 5%
138 | RDA/DRP/NWP/CHI/PUT/10 | Rehabilitation / Improvement of Palavi - Kalpitiya Road (B349) and Etalai - Talawila (Jubily Mawatha) Road (B516) (0+900-1+200) Puttalam EE Division | ST MARY Construction | 27 days left | 96.7% | 14%
139 | RDA/DRP/NWP/CHI/PUT/11 | Rehabilitation / Improvement of Town Roads (Saltern Road, Marikkar Street, Poles Road, Rest House Road, Good Shed Road) and Puttalam Trincomalee Road (AA012) in Puttalam EE Division | Omega Construction Company (Pvt) Ltd | 27 days left | 96.7% | 35%
140 | RDA/DRP/UVA/BAD/BAN/20 | Rehabilitation / Improvement of Bandarawela - Liyangahawela - Poonagala Road (B042) (10+000 -15+000) | D K S Construction | 18 Days in Delay | 100% | 44.5%
141 | RDA/DRP/NCP/POL/POL/08 | Rehabilitation / Improvement and Reconstruction of 31/1 Culvert, Construction Of Retaining Walls At 31/2 (RHS) on Manampitiya Aralaganwila Maduruoya Road | Sawsiri Construction | Completed | 100% |  | 100%
142 | RDA/DRP/NCP/POL/POL/10 | Rehabilitation / Improvement and Construction of New Drainage At 65-78km on Maradankadawala Habarana Thirikkondiyadumadu Road (A011)Road | A.D.M Construction | 299 Days in Delay | 100% | 55%
143 | RDA/DRP/UVA/BAD/BAN/24 | Rehabilitation / Improvement of Rendapola Ambewela Road | Gamage Builders | 56 days left | 86.1% | 36%
144 | RDA/DRP/EAS/AMP/AMP/01 | Rehabilitation / Improvement of Ampara Uhana Mahoya Road (from 2+400 to 2+800) & (from 3+700 to 3+900), Siyambalanduwa Damana Ampara Road (from 43+000 to 45+000), (from 33+000 to 34+000), (from 35+500 to 36+500) & (from 52+000 to 53+000) and Chadayanthalawa Uhana Road (from 11+100 to 11+500) | Ediriweera Construction | 55 Days in Delay | 100% | 90%
145 | RDA/DRP/EAS/AKK/AKK/04 | Rehabilitation / Improvement of Newguna – Manikkamadu – Irakkamam Road (0+000-1+250) & (1+300-2+600), Akkaraipattu Degavapi Vangamam Road (8+500-21+500) and Reconstruction of Culvert No. 368/2 on Colombo-Ratnapura-Wellawaya-Batticaloa Road | Jeezan Trading and Transport | 36 days left | 94.8% | 29%
146 | RDA/DRP/EAS/AKK/KAL/05 | Rehabilitation / Improvement and Reconstruction of Box Culvert at 9+780, Construction of Mass Concrete Retaining Wall (9+550 -9+600) & (9+600-11+000) on Sammanthurai - Malkampiddi - Deegawapi Road, Construction of Concrete Drain & rock blasting with utility shifting on Varaipathanchenai - Deegawapi Road (0+880 - 0+980 RHS), Construction of Concrete Drain on Deegawapi Temple Road (1+100 1+230 RHS), Construction of Mass Concete Retaining wall on Ampilanthurai - Veeramunai Road (25+600 - 26+000 LHS & RHS), Reconstruction of Wing Walls (at 375/2, 375/3, 375/4, 375/6) & Construction of Concrete Drain (384+000-389+000) on Colombo Ratnepura Wellawaya Batticoala Road, Construction of Concrete Drain (15+400 - 15+550 LHS) on Karaitivu - Ampara Road, Construction of Mass Concete Retaining Wall (5+700 -5+730) & on Construction of Hard Shoulder (Concrete) (13+200 - 13+600 LHS & RHS Selected Section) on Weeragoda - Central Camp Road, Construction of Hard Shoulder (Concete) (0+600 - 0+800 LHS & RHS) on Approach Road to Public Buildings | Nazeeha Hardware and Construction | 36 days left | 94.8% | 23%
147 | RDA/DRP/NWP/CHI/PUT/12 | Rehabilitation / Improvement of Puttalam Marichchikaddi Road in Puttalam 6+100-9+000 | Omega Construction Company (Pvt) Ltd | 43 days left | 92.6% | 26%
148 | RDA/DRP/WP/GAM/GAM/13 | Rehabilitation / Improvement and Culvert Constructions on Aluthgama- Vigoda Road at 1+650, on Katunayake - Veyangoda Road at 15+940, on Minuwangoda - Miriswatta - Katana Road at 3+700, on Dunagaha- Nilpanagoda Road at 4+900, on Kadawatha - Mawaramandiya Road at 2+800 and on Makola - Udupila Road at 3+200 | Venus Enterprise | 48 Days in Delay | 100% | 60%
149 | RDA/DRP/NCP/POL/POL/11 | Rehabilitation / Improvement and Construction of New Drainage on Polonnaruwa-Thambala -Sungawila -Somawathiya- Road | A.D.M Construction | 54 Days in Delay | 100% | 40%
150 | RDA/DRP/SAB/RAT/PEL/18 | Rehabilitation / Improvement of Oluganthota - Pinnawala - Bagawanthalawa (26+000-30+000) & Retaining wall construction (Oluganthota - Pinnawala - Bagawanthalawa Road 26/1-26/2 LHS | Anura Construction | 37 days left | 100% | 0%
151 | RDA/DRP/UVA/BAD/BAN/23 | Rehabilitation / Improvement of Colombo Rathnapura Wellawaya Batticaloa Road (AA004) (201+000 - 204+000) | D K S Construction | 64 days left | 86.1% | 21%
152 | RDA/DRP/SP/GAL/GAL/02 | Rehabilitation of Gabbion Walls along Galle - Deniyaya - Madampe Road (from7+700-7+730) | Ceylon Construction Industry Development (Pvt) Ltd | Completed | 100% |  | 100%
153 | RDA/DRP/SP/GAL/HIN/03 | Rehabilitation / Improvement of Gabbion Walls along Udugama - Hiniduma (9+920- 9+938-LHS), (7+450-7+472-LHS), (5+150-5+17 LHS) | Ceylon Construction Industry Development (Pvt) Ltd | 30 Days in Delay | 100% | 98%
154 | RDA/DRP/UVA/BAD/BAN/31 | Rehabilitation / Improvement of Colombo Rathnapura Wellawaya Batticaloa Road (AA004) (212+000 - 213+500) | Nimna Holdings (Pvt) Ltd | 121 days left | 29.1% | 16%
155 | RDA/DRP/NOR/MUL/KIL/07 | Rehabilitation / Improvement of Sholder of 1. Kandy - Jaffna Road (251+000 - 252+200), 2.0Kandy - Jaffna Road (260+000 - 270+000), 3.Nawatkuly - Kerativu - Mannar Road(54+000 - 57+000), 4.Paranthan - Karachchi - Mullaitivu (0+000 - 1+000, 6+000- 8+000, 9+000-11+000, 12+500-14+500, 16+000-17+500, 19+400-19+800) 5.Paranthan - Ponakary Road (9+000-16+000) 6.Soranpattu - Thalaiyadi road (2+500-5+000) | SSK Construction | 33 days left | 73.3%
156 | RDA/DRP/NOR/VOU/MAN/08 | Rehabilitation / Improvement of 85/3 Bridge Approach Reconstruction with Gabion Walls & Damaged Shoulder Construction in between Ch (65+500-79+150km) and Reconstruction of Embankment, shoulder & Improvement to Concrete Shoulder on Navatkuli-Kerativu-Mannar Road (AA032) | Asset Engineering (Pvt) Ltd | 49 days left | 70.2%
157 | RDA/DRP/NOR/MUL/MUL/09 | Rehabilitation /Improvement & Rectification of flood damages in Mullaitivu ( Mankulam-Mullaitivu Road (AA034), Mankulam-Vellankulam Road (B269), Mullaitivu-Kokkilai Road (B297), Kandy-Jaffna Road (AA009), Paranthan-Karachchi-Mullaitivu Road (AA035)) | Jana Civil Work Contractors & Material Suppliers | 21 days left | 88.7%
158 | RDA/DRP/NOR/VOU/VOU/15 | Rehabilitation /Improvement of Kandy-Jaffna Road (AA009) & Madawachchiya-Mannar-Thalaimannar Road (AA014) | Jana Civil Work Contractors & Material Suppliers | 49 days left | 70.2%
159 | RDA/DRP/NOR/JAF/POI/10 | REHABILITATION/IMPROVEMENT OF FLOOD DAMAGES IN CHAVAKACHCHERI-PULOLY ROAD (B075) IN BETWEEN (7+500-9+000 &10+500-12+000) | S S K Construction | 139 days left | 5.7%
160 | RDA/DRP/NOR/JAF/JAF/06 | REHABILITATION / IMPROVEMENT OF FLOOD DAMAGES IN KARAINAGAR CIRCULAR ROAD (B 197) FROM CHAINAGE (5+000-7+030) AND RECONSTRUCTION OF 3/1 CULVERT & RETAINING WALL IN KARAINAGAR CIRCULAR ROAD (B197) FROM CHAINAGE (3+700-3+800) | Nimna Holdings (Pvt) Ltd | No schedule |  |  | 0%
161 | RDA/DRP/EAS/TRI/TRI/08 | REHABILITATION/ IMPROVEMENT OF ALLAI - KANTALE(B010) ROAD, SHOULDER & RETAINING WALL CONSTRUCTION FROM CHAINAGE 24+000 TO 34+500 | A.D.M Construction | No schedule |  |  | 0%
162 | RDA/DC/DRP/WP/GAM/NEG/11 | Rehabilitation/ Improvement - Kadawatha - Ragama - Welisara Road (3+000 - 8+050) | Komuthi Engineering Services (Pvt) Ltd | No schedule |  |  | 0%
163 | RDA/DC/DRP/SLOPE/CP/MAT/MAT/PACKAGE-23 | REHABILITATION OF SELECTED ROAD SECTIONS ON KALALPITIYA UKUWELA-ELKADUWA ROAD (12th KM) AND SLOPE FAILURES DUE TO DITWAH CYCLONE -PACKAGE -23 | Sanguine Engineering (Pvt) Ltd | No schedule |  |  | 0%
164 | RDA/DC/DRP/SLOPE/CP/NUE/NUE/PACKAGE-31 | REHABILITATION OF SELECTED ROADSECTIONS ON PERADENIYA-BADULLA-CHENKALADI ROAD(44TH KM) AND SLOPE FAILURES DUE TO DITWAH CYCLONE | Sanguine Engineering (Pvt) Ltd | No schedule |  |  | 0%
165 | RDA/DC/DRP/SLOPE/CP/KDY/KUN/PACKAGE 06A | REHABILITATION OF SELECTED ROAD SECTIONS ON KANDY-MAHIYANGANA-PADIYATHALAWA ROAD (34th & 35th KM) & MORAGAHAMULA VICTORIA DAMTOP ROAD (6TH KM) AND SLOPE FAILURES DUE TO "DITWAH" CYCLONE- PACKAGE 06A | Finex Engineering (Pvt) Ltd | No schedule |  |  | 0%
166 | RDA/DC/DRP/SLOPE/CP/NUE/NOR/PACKAGE 33 | MITIGATION FOR FAILURE LOCATIONS ALONG NORTON MASKELIYA ROAD (B328) (7+020 7+510) AND SLOPE FAILURES DUE TO "DITWAH" CYCLONE -PACKAGE 33 | HMA Enterprises (Pvt) Ltd | No schedule |  |  | 0%
167 | RDA/DC/DRP/SLOPE/CP/NUE/NUE/PACKAGE-03 | MITIGATION OF SLOPE FAILURE LOCATIONS ALONG GOMBURU OYA-BALAPOKUNA ROAD (B582) 6+900 KM-7+100 KM DUE TO DITWAH CYCLONE - PACKAGE 03 | Nagma Engineering (Pvt) Ltd | No schedule |  |  | 0%
168 | RDA/DC/DRP/SLOPE/CP/KDY/KAD/PACKAGE 14B | MITIGATION FOR FAILURE LOCATIONS ALONG NAWALAPITIYA DOLOSBAGE ROAD (B318) (15+000 - 16+000) DUE TO "DITWAH" CYCLONE - PACKAGE 14B | HMA Enterprises (Pvt) Ltd | No schedule |  |  | 0%
169 | RDA/DC/DRP/SLOPE/CP/NUE/HAN/PACKAGE 26E | REHABILITATION OF SELECTED ROAD SECTIONS ON THENNEKUMBURA RIKILLAGASKADA RAGALA ROAD (B413) (50+100-70+950 ) AND SLOPE FAILURES DUE TO "DITWAH" CYCLONE-PACKAGE 26E | Nagma Engineering (Pvt) Ltd | No schedule |  |  | 0%
170 | RDA/DC/DRP/SLOPE/CP/NUE/HAN/PACKAGE 26C | MITIGATION FOR FAILURE LOCATIONS ALONG THENNEKUMBURA RIKILLAGASKADA RAGALA ROAD (B413) (48/11 - 48/12) & (67/10 - 67 km) DUE TO "DITWAH" CYCLONE-PACKAGE 26C | Finex Engineering (Pvt) Ltd | No schedule |  |  | 0%
171 | RDA/DC/DRP/SLOPE/CP/NUE/NOR/PACKAGE 28A | MITIGATION FOR FAILURE LOCATIONS ALONG AWISSAWELLA HATTON NUWARAELIYA ROAD (A007) (41+800 & 42+960) DUE TO "DITWAH" CYCLONE - PACKAGE 28A | Finex Engineering (Pvt) Ltd | No schedule |  |  | 0%