## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | Contract Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Commenced | Scheduled End
RDA/DRP/CEN/NUE/NUR/97 | Rehabilitation/Improvement of Nawalapitiya Ginigathena Road (B-319)(7+200-12+200) | NuwaraEliya | Norwood | Jayawansa Construction (Pvt) Ltd | 40% | 93758217.76 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-17 | 2026-09-15
RDA/DRP/CEN/NUE/NUR/98 | Rehabilitation/Improvement Harangala Kalapitiya Road (B-148) (0+000-10+700), Approach Road to Hrangala Dam Crest Road (B-491) (0+000-3+820), Nawalapitiya Harangala Road (B-306) (0+000-10+700) | NuwaraEliya | Norwood | Pragathi Civil Construction | 22% | 188617394.68 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-18 | 2026-12-16
RDA/DRP/CEN/NUE/NUR/101 | Rehabilitation/Improvement of Hatton Maskeliya Delhouse Road (B-149) (0+000-31+970) | NuwaraEliya | Norwood | Sooriya Builders | 11% | 86746198.17 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-18 | 2026-11-11
RDA/DC/DRP/CP/NE/NRW/02 | REHABILITATION/ IMPROVEMENT OF APPROCH ROAD TO LAXAPANA POWER HOUSE ROAD CH 6+100 - 12+000 | NuwaraEliya | Norwood | U.K.S Lanka Engineering (Pvt) Ltd | 3% | 374859845.1 | Awarded | DC | Yes | Yes | Yes | 2026-07-30 | 2027-07-29
RDA/DC/DRP/CP/NE/NRW/03 | REHABILITATION/ IMPROVEMENT TO ROZELLA RAILWAY STATION ROAD (0+000 - 3+300) KM AND WATAWALA RAILWAY STATION ROAD (0+000 - 1+850) KM | NuwaraEliya | Norwood | Nagma Engineering (Pvt) Ltd | 3% | 604298969.28 | Awarded | DC | Yes | Yes | Yes | 2026-09-16 | 2027-09-14