## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | Contract Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Commenced | Scheduled End
RDA/DRP/CEN/KDY/KAD/11 | Rehabilitation / Improvement of Nawalapitiya - Dolosbage Road ( B -318) ( 10+500 - 19+350 ), Dedugala Dolosbage Road ( B -588) ( 10+100 - 12+410 ) | Kandy | Kadugannawa | Tiasa Construction (Pvt) Ltd | 23% | 193404194.96 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-25 | 2026-09-23
RDA/DRP/CEN/KDY/KAN/14 | Rehabilitation /Improvement of Katugasthota Medawala road ( B 0206)( 0 + 000 - 9+370) | Kandy | Kandy | Alucon Industries (Pvt) Ltd | 0% | 74836014.77 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-01 | 2027-03-01
RDA/DRP/CEN/KDY/KDY/15 | Rehabilitation / Improvement of Galagedara Rambukkana ( B 122) ( 0+000 - 18+000) | Kandy | Kandy | Jayawansa Construction (Pvt) Ltd | 3.5% | 79071437.68 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-09 | 2027-03-09
RDA/DRP/CEN/KDY/KDY/19 | Rehabilitation / Improvement of Poojapitiya Alawathugoda road ( B 377) ( 0+000 - 8+000) | Kandy | Kandy | Jayawansa Construction (Pvt) Ltd | 0% | 67935586.77 | Awarded | Emergency |  | Yes |  | 2026-09-17 | 2027-03-18
RDA/DRP/CEN/KDY/KUN/20 | Rehabilitation / Improvement to Structures on Madolkelle - Kabaragala - Kandenuwara Road (B 257) (4+000 - 8+000) | Kandy | Kundasale | Samindra Construction | 29% | 31558227.98 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-20 | 2026-11-15
RDA/DRP/CEN/KDY/KUN/21 | Improvement of Pitiyegedara-Waththegama-Iriyagasthenna Road (0+000-5+400) | Kandy | Kundasale | Jayasinghe Construction (Pvt) Ltd | 11.5% | 257721453.96 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-30 | 2026-10-28
RDA/DRP/CEN/KDY/KUN/22 | Improvement to Damaged Road Section on Weeragantota - Randenigala Road. (From CH 19+000 To CH 27+200) | Kandy | Kundasale | SD Civil Construction (Pvt) Ltd | 45% | 224968435.78 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-25 | 2026-09-23
RDA/DRP/CEN/KDY/KUN/24R | Rehabilitation / Improvement of Flood damage on Katugastota - Madawala - Bamberella Road (B205) (0-000 - 7+200 and 13+000 - 13+045) | Kandy | Kundasale | Nimsara Constructions & Holdings (Pvt) Ltd | 0.4% | 79507501.11 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-14 | 2027-03-14
RDA/DRP/CEN/KDY/KUN/25 | Construction of Gabion Retaining Wall on Katugastota Madawala Bamberella Road(LHS 9+600 - 9+655), (15+450 - 15+500), (10+235 - 10+300) and Wattegama Matale road (0+400 - 0+435) | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 36% | 157909825.01 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-06 | 2026-11-01
RDA/DRP/CEN/KDY/KUN/27 | Improvement to Structures on Kandy - Jaffna Road 6+500 - 9+910 | Kandy | Kundasale | Gihan Enterpriese | 47% | 113434139.4 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-30 | 2026-10-27
RDA/DRP/CEN/KDY/KUN/29 | Improvement to Structures on Kandy - Mahiyanganaya - Padiyaththalawa Road (24+000-71+500) and Moragahamula victoria damtop | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 39% | 91559621.04 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-06 | 2027-01-03
RDA/DC/DRP/SLOPE/CP/KDY/GAMPOLA-09 | MITIGATION OF FAILURES ALONG RDA ROADS DUE TO CYCLONE DITWAH GAMPOLA NAWALAPITIYA ROAD (AB013) CHAINAGE 10+350 KM | Kandy | Gampola | Sanguine Engineering (Pvt) Ltd | 2.3% | 386699553.58 | Awarded | DC - Slope | Yes | Yes | Yes | 2026-09-03 | 2027-06-30