## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | Contract Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Commenced | Scheduled End
RDA/DRP/CEN/KDY/KAN/14 | Rehabilitation /Improvement of Katugasthota Medawala road ( B 0206)( 0 + 000 - 9+370) | Kandy | Kandy | Alucon Industries (Pvt) Ltd | 0% | 74836014.77 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-01 | 2027-03-01
RDA/DRP/CEN/KDY/KDY/19 | Rehabilitation / Improvement of Poojapitiya Alawathugoda road ( B 377) ( 0+000 - 8+000) | Kandy | Kandy | Jayawansa Construction (Pvt) Ltd | 0% | 67935586.77 | Awarded | Emergency |  | Yes |  | 2026-09-17 | 2027-03-18
RDA/DC/DRP/SLOPE/PD(CP)/KDY/GPL/01 | Construction of Slope failure mitigation measures along Peradeniya-Badulla-Chenkaladi Road (A005) at Ch 0+030 km | Kandy | Gampola | Weebadda Construction | 0% | 22481370 | Awarded | PD(CP)
RDA/DC/DRP/SLOPE/PD(CP)/KDY/GPL/14 | Construction of Slope failure mitigation measures along Atabage-Ulapane Road (B 490) at Ch 4+000 km | Kandy | Gampola | Bandaranayake Builders and Construction | 0% | 24796315.46 | Awarded | PD(CP)
RDA/DC/DRP/SLOPE/PD(CP)/KDY/GPL/29 | Construction of Slope failure mitigation measures along Peradeniya-Badulla-Chenkaladi Road (A005) at Ch 21+550 km | Kandy | Gampola | Weebadda Construction | 0% | 28806688.5 | Awarded | PD(CP)
RDA/DC/DRP/SLOPE/PD(CP)/KDY/KUN/18,19&20 | Construction of Slope failure mitigation measures along Kandy – Mahiyangana – Padiyatalawa Road (A026) at Culvert No 47/5 Culvert No47/10, Culvert No 50/6-51+200 km and Culvert No 52/3-Culvert No 52/5 | Kandy | Kundasale | J. Kodithuwakkuarachchi & Sons (Pvt) Ltd | 0% | 19636680 | Awarded | PD(CP)