## Progress Ministry
Progress status - Ditwah
Date | 2026-09-27
Serial No | Tender Batch No | Contract No | District | EE Division | Contractor | Project Duration (Days) | Planned Work Start Date | Planned Work Finish Date | LOA Issued? (Yes/No) | Agreement? (Yes/No) | Account Open? (Yes/No) | Advance Paid? (Yes/No) | Kick Off? (Yes/No) | Mobilized to site (Yes/No) | In Progress (Yes/No) | Actual Progress % (Physical) | Financial Progress (Mn) | Critical Issues
11 | 3 | RDA/DRP/CEN/KDY/KAD/11 | Kandy | Kadugannawa | Tiasa Construction (Pvt) Ltd | 182 | 2026-03-25 | 2026-09-23 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 23 | 42.62
14 |  | RDA/DRP/CEN/KDY/KAN/14 | Kandy | Kandy | Alucon Industries (Pvt) Ltd | 182 | 2026-09-01 | 2027-03-01 | Yes |  |  |  | Yes | Yes | Yes | 0 | 0
15 |  | RDA/DRP/CEN/KDY/KDY/15 | Kandy | Kandy | Jayawansa Construction (Pvt) Ltd | 182 | 2026-09-09 | 2027-03-09 | Yes |  |  |  | Yes | Yes | Yes | 3.5 | 0
19 |  | RDA/DRP/CEN/KDY/KDY/19 | Kandy | Kandy | Jayawansa Construction (Pvt) Ltd | 182 | 2026-09-17 | 2027-03-18 | Yes |  |  |  | Yes |  |  | 0 | 0
20 |  | RDA/DRP/CEN/KDY/KUN/20 | Kandy | Kundasale | Samindra Construction | 119 | 2026-07-20 | 2026-11-15 | Yes | Yes |  | No | Yes | Yes | Yes | 29 | 0
21 | 4 | RDA/DRP/CEN/KDY/KUN/21 | Kandy | Kundasale | Jayasinghe Construction (Pvt) Ltd | 182 | 2026-04-30 | 2026-10-28 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 11.5 | 54.55 | In the process of Termination
22 | 4 | RDA/DRP/CEN/KDY/KUN/22 | Kandy | Kundasale | SD Civil Construction (Pvt) Ltd | 182 | 2026-03-25 | 2026-09-23 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 45 | 47.43
24 | 12 | RDA/DRP/CEN/KDY/KUN/24R | Kandy | Kundasale | Nimsara Constructions & Holdings (Pvt) Ltd | 182 | 2026-09-14 | 2027-03-14 |  |  |  |  | Yes | Yes | Yes | 0.4 | 0
25 | 12 | RDA/DRP/CEN/KDY/KUN/25 | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 119 | 2026-07-06 | 2026-11-01 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 36 | 42.68 | NOT YET MOBILIZED
27 | 12 | RDA/DRP/CEN/KDY/KUN/27 | Kandy | Kundasale | Gihan Enterpriese | 119 | 2026-06-30 | 2026-10-27 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 47 | 23.75 | NOT YET MOBILIZED
29 | 12 | RDA/DRP/CEN/KDY/KUN/29 | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 182 | 2026-07-06 | 2027-01-03 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 39 | 26.08 | NOT YET MOBILIZED
31 | 9 | RDA/DRP/CEN/MTL/MTL/31R | Matale | Matale | Alucon Industries (Pvt) Ltd | 91 | 2026-09-01 | 2026-11-30 |  |  |  |  | Yes | Yes | Yes | 0 | 0
32 | 3 | RDA/DRP/CEN/MTL/MTL/32 | Matale | Matale | Lahiru Construction and Consultants (Pvt) Ltd | 182 | 2026-05-02 | 2026-10-30 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 64 | 67.15
33 | 4 | RDA/DRP/CEN/MTL/MTL/33 | Matale | Matale | Jayasinghe Construction (Pvt) Ltd | 91 | 2026-05-02 | 2026-07-31 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 25 | 34.3 | In the process of Termination
35 | 4 | RDA/DRP/CEN/MTL/MTL/35 | Matale | Matale | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 182 | 2026-05-02 | 2026-10-30 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 59 | 54.69
38 | 12 | RDA/DRP/CEN/MTL/MTL/38 | Matale | Matale | Ediriweera Construction | 182 | 2026-07-30 | 2027-01-27 | Yes | Yes | Yes |  | Yes | Yes | Yes | 9 | 0
41 |  | RDA/DRP/CEN/MTL/MTL/41 | Matale | Matale | Vikum Construction | 182 | 2026-09-02 | 2027-03-02 |  |  |  |  | Yes | Yes | Yes | 6 | 0
48 | 11 | RDA/DRP/CEN/MTL/NAL/48R | Matale | Nalanda | S A P Engineering (Pvt) Ltd | 154 | [9 empty] | 0 | 0
49 | 11 | RDA/DRP/CEN/MTL/NAL/49 | Matale | Nalanda | Platinum Holdings Lanka (Private) Limited | 154 | 2026-06-18 | 2026-11-18 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 70 | 14.55
51 | 11 | RDA/DRP/CEN/MTL/NAL/51 | Matale | Nalanda | Platinum Holdings Lanka (Private) Limited | 119 | 2026-06-18 | 2026-10-14 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 68 | 5.64
57 | 12 | RDA/DRP/CEN/NUE/HAN/57 | NuwaraEliya | Hanguranketha | Samindra Construction | 91 | 2026-07-30 | 2026-10-28 | Yes | Yes |  |  | Yes | Yes | Yes | 10 | 0
60 | 10 | RDA/DRP/CEN/NUE/NUE/60R | NuwaraEliya | NuwaraEliya | KSJ Construction (Pvt) Ltd | 182 | [9 empty] | 0 | 0
66 | 3 | RDA/DRP/CEN/NUE/NUE/66 | NuwaraEliya | NuwaraEliya | KSJ Construction (Pvt) Ltd | 91 | 2026-05-02 | 2026-07-31 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 60 | 51.43
67 | 3 | RDA/DRP/CEN/NUE/NUE/67 | NuwaraEliya |  | KSJ Construction (Pvt) Ltd | 182 | 2026-05-02 | 2026-10-30 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 70 | 78.16
68 | 4 | RDA/DRP/CEN/NUE/NUE/68 | NuwaraEliya | NuwaraEliya | Green Scene Construction (Pvt) Ltd | 182 | 2026-05-02 | 2026-10-30 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 30 | 45.28
69 | 4 | RDA/DRP/CEN/NUE/NUE/69 | NuwaraEliya |  | Southern group civil construction (Pvt) Ltd | 182 | 2026-05-02 | 2026-10-30 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 47 | 90.79
86 | 10 | RDA/DRP/CEN/NUE/NUE/86 | NuwaraEliya | NuwaraEliya | Pragathi Civil Construction | 91 | 2026-06-12 | 2026-09-10 | Yes | Yes |  |  | Yes | Yes | Yes | 8 | 0
97 | 10 | RDA/DRP/CEN/NUE/NUR/97 | NuwaraEliya | Norwood | Jayawansa Construction (Pvt) Ltd | 91 | 2026-06-17 | 2026-09-15 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 40 | 16.7
98 | 10 | RDA/DRP/CEN/NUE/NUR/98 | NuwaraEliya | Norwood | Pragathi Civil Construction | 182 | 2026-06-18 | 2026-12-16 | Yes | Yes |  |  | Yes | Yes | Yes | 22 | 0
101 | 10 | RDA/DRP/CEN/NUE/NUR/101 | NuwaraEliya | Norwood | Sooriya Builders | 147 | 2026-06-18 | 2026-11-11 | Yes | Yes |  |  | Yes | Yes | Yes | 11 | 0
102 |  | RDA/DC/DRP/CP/NE/NRW/02 | NuwaraEliya | Norwood | U.K.S Lanka Engineering (Pvt) Ltd | 365 | 2026-07-30 | 2027-07-29 | Yes |  |  |  | Yes | Yes | Yes | 3 | 0
103 |  | RDA/DC/DRP/CP/NE/NE/04 | NuwaraEliya | NuwaraEliya | KDA Weerasinghe & Co (Pvt) Ltd | 546 |  |  | Yes | [6 empty] | 0 | 0
104 |  | RDA/DC/DRP/SLOPE/CP/KDY/GAMPOLA-09 | Kandy | Gampola | Sanguine Engineering (Pvt) Ltd | 301 | 2026-09-03 | 2027-06-30 | Yes |  |  |  | Yes | Yes | Yes | 2.3 | 0
105 |  | RDA/DC/DRP/CP/NE/NRW/03 | NuwaraEliya | Norwood | Nagma Engineering (Pvt) Ltd | 364 | 2026-09-16 | 2027-09-14 | Yes |  |  |  | Yes | Yes | Yes | 3 | 0
129 |  | RDA/DC/DRP/SLOPE/PD(CP)/KDY/GPL/01 | Kandy | Gampola | Weebadda Construction | 105 | [9 empty] | 0 | 0
131 |  | RDA/DC/DRP/SLOPE/PD(CP)/KDY/GPL/14 | Kandy | Gampola | Bandaranayake Builders and Construction | 105 | [9 empty] | 0 | 0
132 |  | RDA/DC/DRP/SLOPE/PD(CP)/KDY/GPL/29 | Kandy | Gampola | Weebadda Construction | 105 | [9 empty] | 0 | 0
141 |  | RDA/DC/DRP/SLOPE/PD(CP)/KDY/KUN/18,19&20 | Kandy | Kundasale | J. Kodithuwakkuarachchi & Sons (Pvt) Ltd | 105 | [9 empty] | 0 | 0