## Physical Progress
Contract No. | Road Name | District | EE Division | Contractor | Commencement Date | Completion Date | Progress (%) | Critical Issues | Mobilization % | Surveying % | Site Clearing % | Base Construction % | Asphalt % | Structure Construction % | Drainage Construction % | Contract Amount (LKR)
RDA/DRP/CEN/KDY/KUN/20 | Madolkelle - Kabaragala - Kandenuwara Road 5/4 and 8/1 | Kandy | Kundasale | Samindra Construction |  |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 31558227.98
RDA/DRP/CEN/KDY/KUN/21 | Pitiyegedara-Waththegama-Iriyagasthenna Road (B369) | Kandy | Kundasale | Jayasinghe Construction (Pvt) Ltd. | 2026-04-30 | 2026-10-28 | 5% | In the process of Termination | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 257721453.96
RDA/DRP/CEN/KDY/KUN/22 | Weraganthota-Randenigala Road (B474) | Kandy | Kundasale | SD Civil Construction (Pvt) Ltd | 2026-03-25 | 2026-09-23 | 35% |  | 100% | 100% | 100% | 0% | 0% | 28% | 0% | 224968435.78
RDA/DRP/CEN/KDY/KUN/25 | Katugastota - Madawala - Bamberella Road | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 2026-07-06 | 2026-11-01 | 10% | NOT YET MOBILIZED | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 157909825.01
RDA/DRP/CEN/KDY/KUN/27 | Kandy - Jaffna Road | Kandy | Kundasale | Gihan Enterpriese | 2026-06-30 | 2026-10-27 | 0% | NOT YET MOBILIZED | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 113434139.4
RDA/DRP/CEN/KDY/KUN/29 | Kandy - Mahiyanganaya - Padiyaththalawa Road (24+000-71+500) A026 and Moragahamula victoria damtop B493 | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 2026-07-06 | 2027-01-03 | 8% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 91559621.04