## Physical Progress
Contract No. | Road Name | District | EE Division | Contractor | Commencement Date | Completion Date | Progress (%) | Critical Issues | Mobilization % | Surveying % | Site Clearing % | Base Construction % | Asphalt % | Structure Construction % | Drainage Construction % | Contract Amount (LKR)
RDA/DRP/CEN/KDY/KUN/21 | Pitiyegedara-Waththegama-Iriyagasthenna Road (B369) | Kandy | Kundasale | Jayasinghe Construction (Pvt) Ltd. | 2026-04-30 | 2026-10-28 | 5% | In the process of Termination | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 257721453.96