## Physical Progress
Contract No. | Road Name | District | EE Division | Contractor | Commencement Date | Completion Date | Progress (%) | Critical Issues | Mobilization % | Surveying % | Site Clearing % | Base Construction % | Asphalt % | Structure Construction % | Drainage Construction % | Contract Amount (LKR)
RDA/DRP/CEN/KDY/KUN/22 | Weraganthota-Randenigala Road (B474) | Kandy | Kundasale | SD Civil Construction (Pvt) Ltd | 2026-03-25 | 2026-09-23 | 35% |  | 100% | 100% | 100% | 0% | 0% | 28% | 0% | 224968435.78