## Physical Progress
Contract No. | Road Name | District | EE Division | Contractor | Commencement Date | Completion Date | Progress (%) | Critical Issues | Mobilization % | Surveying % | Site Clearing % | Base Construction % | Asphalt % | Structure Construction % | Drainage Construction % | Contract Amount (LKR)
RDA/DRP/CEN/KDY/KUN/25 | Katugastota - Madawala - Bamberella Road | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 2026-07-06 | 2026-11-01 | 10% | NOT YET MOBILIZED | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 157909825.01