## Physical Progress
Contract No. | Road Name | District | EE Division | Contractor | Commencement Date | Completion Date | Progress (%) | Critical Issues | Mobilization % | Surveying % | Site Clearing % | Base Construction % | Asphalt % | Structure Construction % | Drainage Construction % | Contract Amount (LKR)
RDA/DRP/CEN/MTL/MTL/32 | Kandy Jaffna Road A 009 (17+710 - 46+450), Thalgodapitiya Yatawatta Dombawela road B 409 (15+030 - 26+800),Palapathwela Galewela road B 346 (0+000 - 8+100) | Matale | Matale | Lahiru Construction and Consultants (Pvt) Ltd | 2026-05-02 | 2026-10-30 | 55% |  | 100% | 70% | 50% | 0% | 0% | 30% | 50% | 292279354.08