## Physical Progress
Contract No. | Road Name | District | EE Division | Contractor | Commencement Date | Completion Date | Progress (%) | Critical Issues | Mobilization % | Surveying % | Site Clearing % | Base Construction % | Asphalt % | Structure Construction % | Drainage Construction % | Contract Amount (LKR)
RDA/DRP/CEN/MTL/MTL/33 | Wattegama Matale Road B 462,Approch road to Ukuwela Railway station B 027 | Matale | Matale | Jayasinghe Contractors (Pvt) Ltd | 2026-05-02 | 2026-07-31 | 18% | In the process of Termination | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 165006430.79