## Physical Progress
Contract No. | Road Name | District | EE Division | Contractor | Commencement Date | Completion Date | Progress (%) | Critical Issues | Mobilization % | Surveying % | Site Clearing % | Base Construction % | Asphalt % | Structure Construction % | Drainage Construction % | Contract Amount (LKR)
RDA/DRP/CEN/MTL/MTL/35 | Rattota Gammaduwa Road B 392 | Matale | Matale | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 2026-05-02 | 2026-10-30 | 50% |  | 100% | 100% | 100% | 0% | 0% | 15% | 27% | 266607902.15