## Physical Progress
Contract No. | Road Name | District | EE Division | Contractor | Commencement Date | Completion Date | Progress (%) | Critical Issues | Mobilization % | Surveying % | Site Clearing % | Base Construction % | Asphalt % | Structure Construction % | Drainage Construction % | Contract Amount (LKR)
RDA/DRP/CEN/MTL/NAL/49 | Naula- Elahera-Pallegama-Hettipola Road (B-312) (8+200-61+240) | Matale | Nalanda | Platinum Holdings Lanka (Private) Limited | 2026-06-18 | 2026-11-18 | 42% |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 44706119.13
RDA/DRP/CEN/MTL/NAL/51 | Bowathenna Access Road (B-064) (0+000-2+410) | Matale | Nalanda | Platinum Holdings Lanka (Private) Limited | 2026-06-18 | 2026-10-14 | 42% |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 17458592.78