## Physical Progress
Contract No. | Road Name | District | EE Division | Contractor | Commencement Date | Completion Date | Progress (%) | Critical Issues | Mobilization % | Surveying % | Site Clearing % | Base Construction % | Asphalt % | Structure Construction % | Drainage Construction % | Contract Amount (LKR)
RDA/DRP/CEN/NUE/NUR/97 | Nawalapitiya Ginigathena Road (B-319) | NuwaraEliya | Norwood | Jayawansa Construction (Pvt) Ltd | 2026-06-17 | 2026-09-15 | 15% |  | 100% | 0% | 20% | 0% | 0% | 0% | 0% | 93758217.76
RDA/DRP/CEN/NUE/NUR/98 | Harangala Kalapitiya Road (B-148) (0+000-10+700), Approach Road to Harangala Dam Crest Road (B-491) (0+000-3+820), Nawalapitiya Harangala Road (B-306) (0+000-10+700) | NuwaraEliya | Norwood | Pragathi Civil Construction | 2026-06-18 | 2026-12-16 | 5% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 188617394.68
RDA/DRP/CEN/NUE/NUR/101 | Hatton Maskeliya Delhouse Road (B-149) | NuwaraEliya | Norwood | Sooriya Builders | 2026-06-18 | 2026-11-11 | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 86746198.17