## Physical Progress
Contract No. | Road Name | District | EE Division | Contractor | Commencement Date | Completion Date | Progress (%) | Critical Issues | Mobilization % | Surveying % | Site Clearing % | Base Construction % | Asphalt % | Structure Construction % | Drainage Construction % | Contract Amount (LKR)
RDA/DRP/CEN/NUE/NUE/66 | Nuwara Eliya Town Road (B331) | NuwaraEliya | NuwaraEliya | KSJ Construction (Pvt) Ltd | 2026-05-02 | 2026-07-31 | 45% |  | 100% | 100% | 100% | 0% | 0% | 50% | 30% | 161841095.7
RDA/DRP/CEN/NUE/NUE/67 | Harangala - Kalapitiya - Kumbaloluwa Road (B148) | NuwaraEliya | NuwaraEliya | KSJ Construction (Pvt) Ltd | 2026-05-02 | 2026-10-30 | 47% |  | 100% | 90% | 80% | 0% | 0% | 30% | 40% | 239417811.34
RDA/DRP/CEN/NUE/NUE/68 | Thawalanthenna Thalawakelle Road (B412) | NuwaraEliya | NuwaraEliya | Green Scene Construction (Pvt) Ltd | 2026-05-02 | 2026-10-30 | 17% |  | 100% | 50% | 30% | 0% | 0% | 5% | 0% | 213999600.01
RDA/DRP/CEN/NUE/NUE/69 | Ulapane Pussallawa Road (B431) | NuwaraEliya | NuwaraEliya | Southern group civil construction (Pvt) Ltd | 2026-05-02 | 2026-10-30 | 36% |  | 100% | 80% | 80% | 0% | 0% | 20% | 45% | 266045892.19
RDA/DRP/CEN/NUE/NUE/86 | Approch road to R'way station (Watagoda) Road | NuwaraEliya | NuwaraEliya | Pragathi Civil Construction | 2026-06-12 | 2026-09-10 | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33765626.86