## Physical Progress
Contract No. | Road Name | District | EE Division | Contractor | Commencement Date | Completion Date | Progress (%) | Critical Issues | Mobilization % | Surveying % | Site Clearing % | Base Construction % | Asphalt % | Structure Construction % | Drainage Construction % | Contract Amount (LKR)
RDA/DRP/CEN/KDY/KAD/11 | Nawalapitiya - Dolosbage Road ( B -318) ( 10+500 - 19+350 ), Dedugala Dolosbage Road ( B -588) ( 10+100 - 12+410 ) | Kandy | Kadugannawa | Tiasa Construction (Pvt) Ltd | 2026-03-25 | 2026-09-23 | 22% |  | 100% | 45% | 100% | 0% | 0% | 10% | 10% | 193404194.96
RDA/DRP/CEN/KDY/KUN/20 | Madolkelle - Kabaragala - Kandenuwara Road 5/4 and 8/1 | Kandy | Kundasale | Samindra Construction |  |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 31558227.98
RDA/DRP/CEN/KDY/KUN/21 | Pitiyegedara-Waththegama-Iriyagasthenna Road (B369) | Kandy | Kundasale | Jayasinghe Construction (Pvt) Ltd. | 2026-04-30 | 2026-10-28 | 5% | In the process of Termination | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 257721453.96
RDA/DRP/CEN/KDY/KUN/22 | Weraganthota-Randenigala Road (B474) | Kandy | Kundasale | SD Civil Construction (Pvt) Ltd | 2026-03-25 | 2026-09-23 | 35% |  | 100% | 100% | 100% | 0% | 0% | 28% | 0% | 224968435.78
RDA/DRP/CEN/KDY/KUN/25 | Katugastota - Madawala - Bamberella Road | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 2026-07-06 | 2026-11-01 | 10% | NOT YET MOBILIZED | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 157909825.01
RDA/DRP/CEN/KDY/KUN/27 | Kandy - Jaffna Road | Kandy | Kundasale | Gihan Enterpriese | 2026-06-30 | 2026-10-27 | 0% | NOT YET MOBILIZED | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 113434139.4
RDA/DRP/CEN/KDY/KUN/29 | Kandy - Mahiyanganaya - Padiyaththalawa Road (24+000-71+500) A026 and Moragahamula victoria damtop B493 | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 2026-07-06 | 2027-01-03 | 8% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 91559621.04
RDA/DRP/CEN/MTL/MTL/32 | Kandy Jaffna Road A 009 (17+710 - 46+450), Thalgodapitiya Yatawatta Dombawela road B 409 (15+030 - 26+800),Palapathwela Galewela road B 346 (0+000 - 8+100) | Matale | Matale | Lahiru Construction and Consultants (Pvt) Ltd | 2026-05-02 | 2026-10-30 | 55% |  | 100% | 70% | 50% | 0% | 0% | 30% | 50% | 292279354.08
RDA/DRP/CEN/MTL/MTL/33 | Wattegama Matale Road B 462,Approch road to Ukuwela Railway station B 027 | Matale | Matale | Jayasinghe Contractors (Pvt) Ltd | 2026-05-02 | 2026-07-31 | 18% | In the process of Termination | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 165006430.79
RDA/DRP/CEN/MTL/MTL/35 | Rattota Gammaduwa Road B 392 | Matale | Matale | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 2026-05-02 | 2026-10-30 | 50% |  | 100% | 100% | 100% | 0% | 0% | 15% | 27% | 266607902.15
RDA/DRP/CEN/MTL/NAL/49 | Naula- Elahera-Pallegama-Hettipola Road (B-312) (8+200-61+240) | Matale | Nalanda | Platinum Holdings Lanka (Private) Limited | 2026-06-18 | 2026-11-18 | 42% |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 44706119.13
RDA/DRP/CEN/MTL/NAL/51 | Bowathenna Access Road (B-064) (0+000-2+410) | Matale | Nalanda | Platinum Holdings Lanka (Private) Limited | 2026-06-18 | 2026-10-14 | 42% |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 17458592.78
RDA/DRP/CEN/NUE/NUE/66 | Nuwara Eliya Town Road (B331) | NuwaraEliya | NuwaraEliya | KSJ Construction (Pvt) Ltd | 2026-05-02 | 2026-07-31 | 45% |  | 100% | 100% | 100% | 0% | 0% | 50% | 30% | 161841095.7
RDA/DRP/CEN/NUE/NUE/67 | Harangala - Kalapitiya - Kumbaloluwa Road (B148) | NuwaraEliya | NuwaraEliya | KSJ Construction (Pvt) Ltd | 2026-05-02 | 2026-10-30 | 47% |  | 100% | 90% | 80% | 0% | 0% | 30% | 40% | 239417811.34
RDA/DRP/CEN/NUE/NUE/68 | Thawalanthenna Thalawakelle Road (B412) | NuwaraEliya | NuwaraEliya | Green Scene Construction (Pvt) Ltd | 2026-05-02 | 2026-10-30 | 17% |  | 100% | 50% | 30% | 0% | 0% | 5% | 0% | 213999600.01
RDA/DRP/CEN/NUE/NUE/69 | Ulapane Pussallawa Road (B431) | NuwaraEliya | NuwaraEliya | Southern group civil construction (Pvt) Ltd | 2026-05-02 | 2026-10-30 | 36% |  | 100% | 80% | 80% | 0% | 0% | 20% | 45% | 266045892.19
RDA/DRP/CEN/NUE/NUE/86 | Approch road to R'way station (Watagoda) Road | NuwaraEliya | NuwaraEliya | Pragathi Civil Construction | 2026-06-12 | 2026-09-10 | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33765626.86
RDA/DRP/CEN/NUE/NUR/97 | Nawalapitiya Ginigathena Road (B-319) | NuwaraEliya | Norwood | Jayawansa Construction (Pvt) Ltd | 2026-06-17 | 2026-09-15 | 15% |  | 100% | 0% | 20% | 0% | 0% | 0% | 0% | 93758217.76
RDA/DRP/CEN/NUE/NUR/98 | Harangala Kalapitiya Road (B-148) (0+000-10+700), Approach Road to Harangala Dam Crest Road (B-491) (0+000-3+820), Nawalapitiya Harangala Road (B-306) (0+000-10+700) | NuwaraEliya | Norwood | Pragathi Civil Construction | 2026-06-18 | 2026-12-16 | 5% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 188617394.68
RDA/DRP/CEN/NUE/NUR/101 | Hatton Maskeliya Delhouse Road (B-149) | NuwaraEliya | Norwood | Sooriya Builders | 2026-06-18 | 2026-11-11 | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 86746198.17