## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/STA II/16/25/04/AKK/AKK | RR/RDA/STA II/16/25/04 | Lahugala Hulannuge Roundabout road | Ampara | Akkaraipattu | Zaka Engineering Consultancy | 100% | 26597958.2 | 36508598.9 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-16 | 2026-03-16 | 2026-03-16
RR/RDA/16/25/10KM/06/AKK/AKK | RR/RDA/16/25/10KM/06 | Hulannuge School Road | Ampara | Akkaraipattu | Gama Construction & Consultant pvt Ltd | 100% | 11406166.73 | 17414587.68 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-24 | 2026-04-27
RR/RDA/16/25/10KM/09/AKK/AKK | RR/RDA/16/25/10KM/09 | Road behind Necode Institute (Navatkadu Akkarapattu) | Ampara | Akkaraipattu | SMA Careem Engineering Consultancy Services & Suppliers (Pvt) Ltd | 100% | 15228903.25 | 24614649.47 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-26 | 2026-04-29
RR/RDA/16/25/05 |  | Jannah Road from Annor Road to Jannah Mosque Junction | Ampara | Akkaraipattu |  | 100% | 15746511.36 | 15746511.36 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-21 | 2025-09-30