## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/22/25/01/UP/BDL | RR/RDA/22/25/01 | Kirikoonthenna Gamata piwisena Margaya | Badulla | Mahiyanganaya | Ema Constructions (Pvt) Ltd | 100% | 15276800 | 22562884.94 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-06 | 2026-02-05
RR/RDA/22/25/02/UP/BDL | RR/RDA/22/25/02 | 23 Ela Krushi Margaya | Badulla | Mahiyanganaya | Priyankara Industries and Contractors | 100% | 22422274.05 | 34734403.93 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-06 | 2026-02-05
RR/RDA/22/25/04/UP/BDL | RR/RDA/22/25/04 | Buluwa Margaya | Badulla | Mahiyanganaya | Samadhi Construction | 100% | 19800000 | 27796703.13 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-06 | 2026-02-05
RR/RDA/22/25/32 |  | Asphalt laying and Development of Haddaththawa 80 Acre road | Badulla | Mahiyanganaya |  | 100% | 93242250.14 | 93242250.14 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-15
RR/RDA/22/25/03 |  | Hubaslinda Meda Margaya | Badulla | Mahiyanganaya |  | 100% | 19159838.84 | 19159838.84 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-25 | 2025-10-31