## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/16/25/04/AKK/AMP | RR/RDA/16/25/04 | Pokunugama near Mr. Dinesh Tharaga House to Road (From Pokunugama Pre School to up to Mr. Dinesh Tharaga House) | Ampara | Ampara | Harischandra Idikirim | 100% | 6435000 | 10039653.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2025-12-10 | 2025-12-19
RR/RDA/16/25/01/AKK/AMP | RR/RDA/16/25/01 | Samanalathenna- Road from House No.63 To the Monastery Muwagammana -From First Lane to Cemetry | Ampara | Dehiaattakandiya | Vithu Construction | 100% | 21336681.87 | 36719169.87 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2025-12-24 | 2025-12-24
RR/RDA/STA II/16/25/02/AKK/AMP | RR/RDA/STA II/16/25/02 | Concreting entrance road with culvert at Dehiaththakandiya Kelegama | Ampara | Dehiaattakandiya | Vithu Construction | 100% | 30737790.6 | 47778623.73 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-16 | 2026-03-16 | 2026-03-25
RR/RDA/STA II/16/25/04/AKK/AKK | RR/RDA/STA II/16/25/04 | Lahugala Hulannuge Roundabout road | Ampara | Akkaraipattu | Zaka Engineering Consultancy | 100% | 26597958.2 | 36508598.9 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-16 | 2026-03-16 | 2026-03-16
RR/RDA/16/25/10KM/06/AKK/AKK | RR/RDA/16/25/10KM/06 | Hulannuge School Road | Ampara | Akkaraipattu | Gama Construction & Consultant pvt Ltd | 100% | 11406166.73 | 17414587.68 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-24 | 2026-04-27
RR/RDA/16/25/10KM/09/AKK/AKK | RR/RDA/16/25/10KM/09 | Road behind Necode Institute (Navatkadu Akkarapattu) | Ampara | Akkaraipattu | SMA Careem Engineering Consultancy Services & Suppliers (Pvt) Ltd | 100% | 15228903.25 | 24614649.47 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-26 | 2026-04-29
RR/RDA/15/25/01/EP/BTC | RR/RDA/15/25/01 | Concreting to Vipulananthar road | Batticaloa | Batticaloa | SSK Construction | 100% | 29074090.89 | 44424075.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-04 | 2026-02-08
RR/RDA/15/25/07/EP/BTC | RR/RDA/15/25/07 | Concreting to Thakwa masjith Cross Road | Batticaloa | Batticaloa | Nazeeha Hardware and Construction | 100% | 22206567.3 | 36804461.32 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-21 | 2026-02-20 | 2026-02-15
RR/RDA/17/25/01/EP/TRN | RR/RDA/17/25/01 | Pillayar Road Renovation | Trincomalee | Trincomalee | Rina Construction | 100% | 23425921.56 | 30058596.03 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-04 | 2025-12-15
RR/RDA/17/25/02/EP/TRN | RR/RDA/17/25/02 | Kathirkamathambi Road | Trincomalee | Trincomalee | Fareed | 100% | 28809738 | 38871590.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-04 | 2025-12-15
RR/RDA/17/25/03/EP/TRN | RR/RDA/17/25/03 | Hospital Road | Trincomalee | Trincomalee | Pragash Construction | 100% | 18557253.77 | 23553502.5 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-04 | 2025-12-15
RR/RDA/17/25/07/EP/TRN | RR/RDA/17/25/07 | Kanthamalawa Main Road | Trincomalee | Trincomalee | SSK Construction | 100% | 9161570 | 17579515.67 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-23 | 2026-07-23
RR/RDA/17/25/10/EP/TRN | RR/RDA/17/25/10 | From Medagama temple to Peramaduwa | Trincomalee | Trincomalee | Soyuru Sampath Construction & Suppliers | 100% | 24197635 | 31162876.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-21 | 2026-02-20 | 2026-01-30
RR/RDA/17/25/12/EP/TRN | RR/RDA/17/25/12 | Improvement of RDS Road | Trincomalee | Trincomalee | MTA Construction | 100% | 30166053 | 38673984.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-04 | 2026-02-03 | 2025-12-15
RR/RDA/17/25/13/EP/TRN | RR/RDA/17/25/13 | Concreting from School junction to Boovidya Office | Trincomalee | Trincomalee | Hana Construction (Pvt) Ltd. | 100% | 38264100 | 49104899.44 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-21 | 2026-02-19 | 2026-07-31
RR/RDA/17/25/14/EP/TRN | RR/RDA/17/25/14 | Amaithusha Road (School road to Vaithiyar road) | Trincomalee | Trincomalee | Shaniff Construction | 100% | 5006100 | 6650570.02 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-21 | 2026-02-19 | 2026-05-30
RR/RDA/17/25/15/EP/TRN | RR/RDA/17/25/15 | Cemetery Road (Sajahan Mowlavi's house to Thajudeen shop) | Trincomalee | Trincomalee | Soyuru Sampath Construction & Suppliers | 100% | 21774456 | 27637562.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-04 | 2026-02-04
RR/RDA/17/25/16/EP/TRN | RR/RDA/17/25/16 | Valuvar Road (Main road to Kovil road) | Trincomalee | Trincomalee | Shaniff Construction | 100% | 10783850 | 13997601.51 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-02 | 2026-03-02 | 2026-01-30
RR/RDA/17/25/18/EP/TRN | RR/RDA/17/25/18 | Sooranagar Main Road (Muththuchenai Junction to Thuvaraka Vithiyalayam)-Concrete | Trincomalee | Trincomalee | SSK Construction | 100% | 25155240 | 38483392.5 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-06-02 | 2026-09-01
RR/RDA/SP/17/25/01/EP/TRN | RR/RDA/SP/17/25/01 | Alankerny faisal Main Road (Koof Nagar) | Trincomalee | Trincomalee | NAS Construction | 100% | 26879843.97 | 35125795.85 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-02 | 2026-03-02 | 2026-01-30
RR/RDA/16/25/05 |  | Jannah Road from Annor Road to Jannah Mosque Junction | Ampara | Akkaraipattu |  | 100% | 15746511.36 | 15746511.36 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-21 | 2025-09-30
RR/RDA/16/25/06 |  | Improvement of Mosque Lane from beach Road to Jummah Mosque Lane (0+500)m | Ampara | Kalmunai |  | 100% | 22306322.17 | 22306322.17 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-23 | 2025-09-30
RR/RDA/SP/16/25/02 |  | Karana junction south pahalawela palanoya road (From near Pahalalanda post office junction to Karanagama) | Ampara | Ampara |  | 100% | 171722366.66 | 171722366.66 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-22 |  | 2025-11-15
RR/RDA/16/25/02 |  | Muwagammana First Lane to Cemetry | Ampara | Dehiaattakandiya |  | 100% | 37324257.12 | 37324257.12 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-16 | 2025-11-30
RR/RDA/STA II/17/25/01 |  | Hira Village Road | Ampara | Kalmunai |  | 100% | 48842501.78 | 48842501.78 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 |  | 2025-11-30
RR/RDA/16/25/10KM/10 |  | Imam Roomy School Road | Ampara | Kalmunai |  | 100% | 13946909.31 | 13946909.31 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-11-10 |  | 2026-03-15
RR/RDA/16/25/10KM/12 |  | Kalyana Road | Ampara | Kalmunai |  | 100% | 36778852.24 | 36778852.24 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-11-10 |  | 2026-03-15
RR/RDA/15/25/08 |  | Kumpila Madu Road | Batticaloa | Batticaloa |  | 100% | 32424899.67 | 32424899.67 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-15
RR/RDA/17/25/04 |  | Cemetry Road (Poompuhr) | Trincomalee | Trincomalee |  | 100% | 32194573.49 | 32194573.49 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-22
RR/RDA/17/25/17 |  | Furkaniya Marcus connection road (S.M.Unithu house to Market main road) | Trincomalee | Trincomalee |  | 100% | 15444993.23 | 15444993.23 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-09-30