## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/10/25/22/NP/JFN | RR/RDA/10/25/22 | Anaivilunthan Sudalai Road | Jaffna | Point Pedro | Yaso Engineering | 65% | 48082026.3 | 61126170.56 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-02 | 2026-04-03 | 2026-06-03
RR/RDA/10/25/25/NP/JFN | RR/RDA/10/25/25 | Palaiya Vaikal Veeethy | Jaffna | Point Pedro | Sun Constructions (Pvt) Ltd. | 50% | 54450000 | 79703717.02 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-02 | 2026-06-15