## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/09/25/08/SP/HMB | RR/RDA/09/25/08 | Carpeting Pissubedda Medagamgoda road | Hambantota | Tangalle | Samarasinghe Construction(Pvt)Ltd | 98% | 28923336.75 | 46881232.95 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-20 | 2026-06-19
RR/RDA/09/25/09/SP/HMB | RR/RDA/09/25/09 | Development of the road in front of Godawela School to Ambussa Wela | Hambantota | Tangalle | A.T.L. Construction | 60% | 34500631 | 47452621.54 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-07 | 2026-07-23 | 2026-08-31
RR/RDA/09/25/11/SP/HMB | RR/RDA/09/25/11 | Development of Walasmulla Daluwakgoda School Road | Hambantota | Tangalle | Samarasinghe Construction(Pvt)Ltd | 20% | 34814777.8 | 48463720.72 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-06-04 | 2026-09-03 | 2026-09-03
RR/RDA/09/25/13/SP/HMB | RR/RDA/09/25/13 | Development of the road from Puak Dandawa near Aligerappa house through Weerasijahagoda to Satinamaluwa Kapuduarawatta field. | Hambantota | Tangalle | A.T.L. Construction | 60% | 23847807.5 | 30673898.39 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-06 | 2026-07-22 | 2026-08-31
RR/RDA/08/25/05 |  | Koggalla bus stand to Sooriyawewa Road | Hambantota | Tangalle |  | 95% | 127573213.52 | 127573213.52 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-02-28