## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/07/25/02/SP/GAL | RR/RDA/07/25/02 | Delgahabedda-Kirimatiya Margaya | Galle | Galle | Dissanayaka Builders | 93% | 26404581.16 | 50069275.91 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2025-12-31
RR/RDA/07/25/05/SP/GAL | RR/RDA/07/25/05 | Atawalawatta Sri Rewatha Viduhala Idiripita Margaya | Galle | Galle | Dissanayaka Builders | 95% | 25809376.97 | 45727567.86 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-28
RR/RDA/07/25/09/SP/GAL | RR/RDA/07/25/09 | Panwila Hena Pradhana Margaya Lalith Mahathage Niwasa Asala Sita Manjula Jayaweera Mahathage Niwasa Dakwa Margaya | Galle | Hiniduma | DGSD Construction | 98% | 28039359.88 | 42959652.18 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-03-31
RR/RDA/07/25/17/SP/GAL | RR/RDA/07/25/17 | Dasa Kadaya Asala sita Jack Fruit Ceylon (Pvt) ayathanaya dakwa Margaya 1 Km carpert kirima | Galle | Galle | P.H. Engineering Construction (Pvt) Ltd | 47% | 20798250 | 33516218.38 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-30
RR/RDA/07/25/19/SP/GAL | RR/RDA/07/25/19 | SuriEla Margaya | Galle | Galle | A.D. Herath Engineering | 96% | 14387747 | 18573267.25 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2026-01-08 | 2026-02-27
RR/RDA/08/25/18/SP/MTR | RR/RDA/08/25/18 | Dekatukella Margaya Pethibemma sahithawa Sanwardanaya kirima | Matara | Matara | Dashodhaya (Pvt)Ltd | 0% | 4080866.9 | 6117703.11 | Awarded | Tender Below 50Mn |  |  |  | 2025-10-09 | 2026-01-08 | 2025-12-16
RR/RDA/09/25/08/SP/HMB | RR/RDA/09/25/08 | Carpeting Pissubedda Medagamgoda road | Hambantota | Tangalle | Samarasinghe Construction(Pvt)Ltd | 98% | 28923336.75 | 46881232.95 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-20 | 2026-06-19
RR/RDA/09/25/09/SP/HMB | RR/RDA/09/25/09 | Development of the road in front of Godawela School to Ambussa Wela | Hambantota | Tangalle | A.T.L. Construction | 60% | 34500631 | 47452621.54 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-07 | 2026-07-23 | 2026-08-31
RR/RDA/09/25/11/SP/HMB | RR/RDA/09/25/11 | Development of Walasmulla Daluwakgoda School Road | Hambantota | Tangalle | Samarasinghe Construction(Pvt)Ltd | 20% | 34814777.8 | 48463720.72 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-06-04 | 2026-09-03 | 2026-09-03
RR/RDA/09/25/13/SP/HMB | RR/RDA/09/25/13 | Development of the road from Puak Dandawa near Aligerappa house through Weerasijahagoda to Satinamaluwa Kapuduarawatta field. | Hambantota | Tangalle | A.T.L. Construction | 60% | 23847807.5 | 30673898.39 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-06 | 2026-07-22 | 2026-08-31
RR/RDA/08/25/05 |  | Koggalla bus stand to Sooriyawewa Road | Hambantota | Tangalle |  | 95% | 127573213.52 | 127573213.52 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-02-28
RR/RDA/09/25/07 |  | Carpeting Dabewelena Gravel Road | Hambantota | Hambantota |  | 98% | 54766473.95 | 54766473.95 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-10-18 | 2025-12-31 | 2026-03-31