## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/18/25/16/NWP/KRG | RR/RDA/18/25/16 | Development of concrete road from near Wadawa temple to the lake | Kurunegala | Kuliyapitiya | Jayawardana Constructions (Pvt) Ltd. | 100% | 25583393 | 31595236.77 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15 | 2025-12-15
RR/RDA/18/25/22/NWP/KRG | RR/RDA/18/25/22 | Paving of culverts and sidewalls at the necessary places on the road from near Moragane Samiti Hall to Siyambalaweva via Galkadulla. | Kurunegala | Kuliyapitiya | Jayasinghe Constructions (Pvt) Ltd. | 65% | 67074479.55 | 77881819.09 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-03 | 2026-06-04 | 2026-07-04
RR/RDA/18/25/24/NWP/KRG | RR/RDA/18/25/24 | Paving and developing the road from Seelarathana Mawatha to Girana Junction | Kurunegala | Kuliyapitiya | Senerath Engineering (pvt) Ltd | 100% | 37201129.8 | 57963603.67 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-03 | 2026-03-05 | 2026-04-02
RR/RDA/18/25/136/NWP/KRG | RR/RDA/18/25/136 | Ranasinghe Hotel Asalin Koralaya Waththe sita Panwala Kubura Dakwa Diwena Margaya Kapat Kirima | Kurunegala | Kuliyapitiya | Jayasinghe Contractors (Pvt) Ltd. | 100% | 21718130.5 | 22994794.21 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-07 | 2026-04-07 | 2026-04-07
| RR/RDA/18/25/308 | Wijekoon Mawatha near Narammala Bus Stand and Hospital Mawatha from Peralaswella | Kurunegala | Kuliyapitiya | Thushara roofing (pvt) ltd | 65% | 10696008.28 | 11985499.69 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-04 | 2026-08-02
RR/RDA/18/25/23 |  | Horagasagara Nawarathna handiye sita Ihala kadigamuwa handiya dakwa margaya (Bingiriya) | Kurunegala | Kuliyapitiya |  | 100% | 61588475.92 | 61588475.92 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-31
RR/RDA/18/25/17 |  | No. 245 from near Jeevan Lasantha's house no. 37 Development of the main road up to Mr. Nihal's house with five (5) side roads. | Kurunegala | Kuliyapitiya |  | 100% | 51911526.67 | 51911526.67 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-07 | 2025-10-30 | 2025-11-15