## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/25/24/01/SBP/RTP | RR/RDA/25/24/01 | From Delgas Junction To Vilehena Road | Ratnapura | Ratnapura | Siri Construction | 90% | 30346327.41 | 43303726.54 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15
RR/RDA/25/24/02/SBP/RTP | RR/RDA/25/24/02 | Thundola Varathenna Road | Ratnapura | Embilipitiya | Siri Construction | 35% | 123540895.5 | 122516687.81 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-05-02 | 2026-04-27
RR/RDA/25/24/03/SBP/RTP | RR/RDA/25/24/03 | From Thunaghahena To Temple Road | Ratnapura | Ratnapura | Siri Construction | 95% | 20065425.82 | 27753891.86 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15
RR/RDA/25/24/04/SBP/RTP | RR/RDA/25/24/04 | Keenagahawila Kanuggala Road | Ratnapura | Ratnapura | SSP Engineering | 100% | 33392908.77 | 49180179.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15 | 2025-12-15
RR/RDA/25/24/05/SBP/RTP | RR/RDA/25/24/05 | From Nadurana Kosgas Junction to Bathalakotuwa Via Kiriporuwa Road | Ratnapura | Ratnapura | SSP Engineering | 100% | 21592962.26 | 30993635.49 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15 | 2025-12-15
RR/RDA/25/24/06/SBP/RTP | RR/RDA/25/24/06 | Hewainna Koshenagama Road | Ratnapura | Ratnapura | Asela Construction | 100% | 18485912.16 | 26723132.29 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15 | 2025-12-15
RR/RDA/25/24/10/SBP/RTP | RR/RDA/25/24/10 | From Deniya kade Market to Henyaya Road Via Keenagahaella Road | Ratnapura | Pelmadulla | Sam Dam | 95% | 31673916.45 | 50516461.34 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-27
RR/RDA/25/24/13/SBP/RTP | RR/RDA/25/24/13 | Henyaya - Mirishena South Road | Ratnapura | Ratnapura | SSP Engineering | 100% | 10331554.6 | 13467295.53 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-17 | 2026-02-19
RR/RDA/25/24/14/SBP/RTP | RR/RDA/25/24/14 | Pimbura- Peelwatta Road | Ratnapura | Ratnapura | SSP Engineering | 100% | 15010646.74 | 19335843.37 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-17 | 2026-02-19 | 2026-02-19
RR/RDA/25/24/16/SBP/RTP | RR/RDA/25/24/16 | Kalawana Salgaha Yata Road | Ratnapura | Ratnapura | SSP Engineering | 100% | 34292579.12 | 50567711.43 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15 | 2025-12-15
RR/RDA/24/25/21/SBP/RTP | RR/RDA/24/25/21 | Sudagala Grama Seva Division, From Sudagala to Tunudola Road up the mountain to near the cooperative | Ratnapura | Ratnapura | DKS Construction | 0% | 35222472.34 | 42448062.24 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-15 | 2026-10-13
RR/RDA/24/25/25/SBP/RTP | RR/RDA/24/25/25 | From the point where the Bulathgama-Pallevela road starts from Rasagala Road | Ratnapura | Pelmadulla | Sathira Construction | 0% | 7273850 | 9080628.78 | Awarded | Tender Below 50Mn |  |  |  | 2026-08-24 | 2026-11-22
RR/RDA/24/25/28/SBP/RTP | RR/RDA/24/25/28 | From near Kalal Ella Rubber Store to Narangalla via Navinikanda Road | Ratnapura | Pelmadulla | KEP Construction | 0% | 18880633.26 | 24660700.4 | Awarded | Tender Below 50Mn |  |  |  | 2026-08-11 | 2026-11-09
RR/RDA/24/25/31/SBP/RTP | RR/RDA/24/25/31 | Development of Koratuwegoda Road from Main Road | Ratnapura | Pelmadulla | KEP Construction | 0% | 19882000.02 | 29632612.99 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-04 | 2026-12-03
RR/RDA/24/25/32/SBP/RTP | RR/RDA/24/25/32 | Weligepola to Nitta Kumbura Road | Ratnapura | Pelmadulla | Sasiri Construction | 0% | 14421268 | 18898027.21 | Awarded | Tender Below 50Mn |  |  |  | 2026-08-24 | 2026-11-22
RR/RDA/24/25/34/SBP/RTP | RR/RDA/24/25/34 | Matuwagala Mudun Kotu Road | Ratnapura | Ratnapura | DKS Construction | 0% | 0 | 33238726.51 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-15 | 2026-10-13
RR/RDA/24/25/35/SBP/RTP | RR/RDA/24/25/35 | Induruwa Junction to Kadawatha junction road joining Kuruwita - Siripagama road | Ratnapura | Ratnapura | Creates Consultant and Construction | 0% | 70340000 | 101561648.5 | Awarded | Tender Above 50Mn
RR/RDA/25/24/07 |  | Godawela Wela Middle Road (Const. side walls) | Ratnapura | Ratnapura |  | 100% | 21801991.89 | 21801991.89 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/25/24/15 |  | D03 Road Near the Yaka Poll | Ratnapura | Pelmadulla |  | 100% | 52683572.48 | 52683572.48 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/25/24/08 |  | From Mr.Ranjth's House to Mr.Premasiri's House in Maduwanwela Janapadaya 2nd Lane Road | Ratnapura | Embilipitiya |  | 100% | 39030233.29 | 39030233.29 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/25/24/12 |  | Siyabalagahayata Junction to Blue Mountain Housing Complex Road | Ratnapura | Ratnapura |  | 100% | 23571917.19 | 23571917.19 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-09-04 | 2025-10-10
RR/RDA/25/24/09 |  | From Koralegama to Labuwalwaththa Road (From Mr.Pushpananda House) | Ratnapura | Pelmadulla |  | 100% | 33251409.79 | 33251409.79 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-09-09 | 2025-11-15 | 2025-11-05
RR/RDA/25/24/11 |  | Cinema Hall Road to Dooliyangodella Pitawaththa Road | Ratnapura | Ratnapura |  | 100% | 27759052.36 | 27759052.36 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-02 | 2025-11-30 | 2025-11-15
RR/RDA/25/24/35 |  | Ilumba Kanda Road from Milinduthalawa Temple | Ratnapura | Embilipitiya |  | 30% | 24709638.71 | 24709638.71 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 | 2026-03-31 | 2026-04-10
RR/RDA/25/24/17 |  | Pahalawaththa to Batahenkanda Road | Ratnapura | Embilipitiya |  | 10% | 112040241.38 | 112040241.38 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 | 2026-03-31 | 2026-04-10
RR/RDA/25/24/19 |  | Wijeriya Iththekanda Margaya Sanwardanaya Kirima | Ratnapura | Embilipitiya |  | 35% | 72158727.69 | 72158727.69 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 | 2026-03-31 | 2026-04-10
RR/RDA/25/24/20 |  | Godawela Walakada margaya Sanwardanaya Kirima (Walakada Junction to Godawela Junction) | Ratnapura | Embilipitiya |  | 15% | 126132479.8 | 126132479.8 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 | 2026-03-31 | 2026-04-10