## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/16/25/03/AKK/AMP | RR/RDA/16/25/03 | Polbedda Junction to Galwalayaya Road | Ampara | Dehiaattakandiya | MOTEC Engineering & Construction | 52% | 17506335 | 24800970.39 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-10 | 2026-03-10 | 2026-03-16
RR/RDA/STA II/16/25/03/AKK/AMP | RR/RDA/STA II/16/25/03 | Padiyathalawa Navinna road from Navinna Junction A5 to Navinna Bridge | Ampara | Dehiaattakandiya | Vithu Construction | 65% | 39470000 | 60426139.14 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-25 | 2026-05-26
RR/RDA/16/25/10KM/01/AKK/AMP | RR/RDA/16/25/10KM/01 | The road from the bridge near Ridee ela Temple to Island Plot No. 197 | Ampara | Dehiaattakandiya | Sawsiri Construction | 17% | 24113338.37 | 34027781.43 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-25 | 2026-05-26
RR/RDA/16/25/10KM/03/AKK/AMP | RR/RDA/16/25/10KM/03 | On the road from Pulungasmulla to Padawala, the road from near Shanta Veladasala towards Padawala | Ampara | Dehiaattakandiya | Sawsiri Construction | 55% | 21202726.44 | 32963348.47 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-24 | 2026-05-25
RR/RDA/16/25/10KM/07/AKK/AMP | RR/RDA/16/25/10KM/07 | Bedirakka Malgastalawa Road | Ampara | Dehiaattakandiya | Pearl Construction | 0% | 16362791.5 | 28483156.49 | Awarded | Tender Below 50Mn |  |  |  | 2026-03-14 | 2026-05-15