## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/25/25/02/SBP/KGL | RR/RDA/25/25/02 | Elagapitiya Colany Road From Debathgama Pallebage to Tea Shakthi Praja Shalawa | Kegalle | Kegalle | EHL Constructions | 85% | 36210751.61 | 52222845.54 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-03 | 2026-05-04
RR/RDA/25/25/03/SBP/KGL | RR/RDA/25/25/03 | From Kehelpannala Junction to Pahala Kabawita Road | Kegalle | Kegalle | SF Constructions | 95% | 71786959.2 | 96478103.45 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-30
RR/RDA/25/25/05/SBP/KGL | RR/RDA/25/25/05 | Siyabalangamuwa Kudumbuwa Road | Kegalle | Kegalle | Shanho Engineering | 100% | 39262197.06 | 46027479.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-04
RR/RDA/25/25/06/SBP/KGL | RR/RDA/25/25/06 | From Dombemada Post Office to Sillugala Via Wedollamada well | Kegalle | Kegalle | Shanho Engineering | 100% | 37416631.86 | 45066393.95 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-04
RR/RDA/25/25/09/01/SBP/KGL | RR/RDA/25/25/09/01 | The first phase of the Matiyagane-Berawandare road from Mas Potha via Haliyagoda | Kegalle | Kegalle | Samindra construction | 100% | 26656967.36 | 28713235.52 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-04
RR/RDA/25/25/09/02/SBP/KGL | RR/RDA/25/25/09/02 | The first phase of the Gaitahpura road via Ambagala on the Warakapola Technical College Road | Kegalle | Kegalle |  | 0% | 0 | 47360768.89 | Awarded | Tender Below 50Mn
RR/RDA/25/25/10/SBP/KGL | RR/RDA/25/25/10 | Elipangamuwa School Road through Pananawaththa | Kegalle | Kegalle | DHP Construction | 100% | 23988665.8 | 33397400.45 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-03 | 2026-02-01
RR/RDA/25/25/17 |  | Na gahamula Junction to 28 Janapadaya Road | Kegalle | Kegalle |  | 100% | 30370502.56 | 30370502.56 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/25/25/18 |  | Concreting Beragala Army Camp to Beragala 3way Junction VIA Niyadagala | Kegalle | Kegalle |  | 100% | 34687905.11 | 34687905.11 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-26 | 2025-10-31 | 2025-10-25