## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/06/25/42/CP/NE | RR/RDA/06/25/42 | AC Overlaying from Polpitiya Junction to 04th Mile Post (CH 3+700 – 8+700 km) | Nuwara Eliya | Norwood | UKS Lanka Engineering Pvt Ltd. | 50% | 220116957.84 | 276005265.17 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-11-24 | 2026-08-22 | 2026-08-22