## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/12/25/01/NP/VVN | RR/RDA/12/25/01 | Thiruchchenthooran mill road NVSTE541 | Vavuniya | Vavuniya | TMC Constructions | 0% | 53290000 | 100688815.19 | Awarded | Tender Above 50Mn |  |  |  | 2026-07-01 | 2026-09-29
RR/RDA/12/25/03/NP/VVN | RR/RDA/12/25/03 | Puthiya manipuram, main road (NVSTE481) | Vavuniya | Vavuniya | Yaso Engineering | 35% | 32481108 | 41435979.42 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13
RR/RDA/12/25/04/NP/VVN | RR/RDA/12/25/04 | Suntharapuram main road | Vavuniya | Vavuniya | Sun Constructions (Pvt) Ltd. | 35% | 162703000 | 71964095.93 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-03
RR/RDA/12/25/07/NP/VVN | RR/RDA/12/25/07 | Tharanikulam main road | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 70% | 20876280.7 | 30580213.01 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/10/NP/VVN | RR/RDA/12/25/10 | Achchipuram amman temble road | Vavuniya | Vavuniya | Ancheneya Constructions | 70% | 19430799.3 | 28181354.24 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06
RR/RDA/12/25/12/NP/VVN | RR/RDA/12/25/12 | Nanthimiththiragama 1st | Vavuniya | Vavuniya | Ancheneya Constructions | 5% | 24583111.3 | 30752460 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-20 | 2026-05-22
RR/RDA/12/25/13/NP/VVN | RR/RDA/12/25/13 | Nanthimiththiragama 2nd | Vavuniya | Vavuniya | Ancheneya Constructions | 5% | 24829841.3 | 31291948.01 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-20 | 2026-04-22
RR/RDA/12/25/14/NP/VVN | RR/RDA/12/25/14 | Nanthimiththiragama 4th | Vavuniya | Vavuniya | Ancheneya Constructions | 5% | 25113641.3 | 30939872.36 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-20 | 2026-04-22
RR/RDA/12/25/43/NP/VVN | RR/RDA/12/25/43 | Pavatkulam tack 5 vaarikuttiyoor | Vavuniya | Vavuniya | North Construction (Pvt) Ltd | 70% | 17351705.25 | 25717072.9 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/48/NP/VVN | RR/RDA/12/25/48 | Mukaththankulam 7th lane (NVVPE173) | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 70% | 18900081.2 | 28294497.45 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/51/NP/VVN | RR/RDA/12/25/51 | Adappankulam aladi road | Vavuniya | Vavuniya | North Construction (Pvt) Ltd | 70% | 13383862.25 | 19573472.29 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/60/NP/VVN | RR/RDA/12/25/60 | Salalinigama lane 12 | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 15% | 23397220 | 33827661.22 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-03 | 2026-07-03
RR/RDA/12/25/62/NP/VVN | RR/RDA/12/25/62 | Periyavilathikulam | Vavuniya | Vavuniya | Omega Construction (Pvt) Ltd | 35% | 16916712.5 | 23338487.33 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-03 | 2026-07-03
RR/RDA/12/25/63/NP/VVN | RR/RDA/12/25/63 | 1st Cross Street Alakarai Road | Vavuniya | Vavuniya | North Construction | 30% | 38912500 | 55600429.77 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-20 | 2026-05-21
RR/RDA/12/25/64/NP/VVN | RR/RDA/12/25/64 | Nedunkulama | Vavuniya | Vavuniya | Arul Selvi Construction and Hardware | 70% | 15902966.56 | 22278087.37 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-03 | 2026-07-03